## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 2.0 BULK EARTHWORKS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 2.0 BULK EARTHWORKS
section | 2.0 BULK EARTHWORKS
checkpoint | 2.01 - Source Selection Criteria - Ballast
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.1; Table 2.1
label | SPECIFICATION DETAIL SUMMARY: Ballast shall comply with the requirements of KiwiRail C-ST-FO-4110 Formation, v.1 March 2019.
label | ○ If existing ballast material is proposed by the contractor to be stripped and re-used in construction, the ballast stockpile shall be inspected and approved by the Engineer prior to reinstatement.
label | ACCEPTANCE CRITERIA: Ballast material shall meet the requirements stated in document T-SP- MM-60140 Supply of Crushed and Screened Stone Ballast
label | TEST SPEC AND FREQUENCY: Spec and frequency must comply with Kiwirail C-ST- FO-4110
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.02 - Source Selection Criteria - Sub-ballast (GAP40)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.2;Table 2.1
label | SPECIFICATION DETAIL SUMMARY: The GAP40 shall comply with the NZTA M/4 specification for basecourse aggregate.
label | ○ Fill materials shall be sourced from areas of cut or from alternative sources. If the Contractor wishes to propose materials from alternative sources then they shall provide details of such sources for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Allowable Particle Size: < 40 mm
label | ○ (1*) Percentage Fines (0.07mm): <7%
label | ○ (2*) Weathering Quality Index: The aggregate shall have a quality index > or = to CA
label | ○ (3*) Crushing Resistance Test: <10% fines passing 2.36 mm sieve under test load of 130 kN
label | ○ (4*) Broken Face Content: 50% for >37.5 mm fraction and 19 mm – 37.5 mm fraction
label | TEST SPEC AND FREQUENCY: Min. 2 tests per source
label | 1* = Testing method NZS 4402:1986 Test 2.8.1
label | 2* = Testing method NZS 4407:2015 Test 3.11
label | 3* = Testing method NZS 4407:2015 Test 3.10
label | 4* = Testing method NZS 4407:2015 Test 3.14
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.03 - Source Selection Criteria - Structural Fill/Hardfill GAP65
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.5; Table 2.1
label | SPECIFICATION DETAIL SUMMARY: Defines a well graded aggregate, with slightly weathered to unweathered fragments of rock up to maximum 65 mm characteristic dimension and which is relatively free of fines and other mineral matter such that when compacted the rock fragments can achieve point-to-point contact.
label | ○ Fill materials shall be sourced from areas of cut or from alternative sources. If the Contractor wishes to propose materials from alternative sources then they shall provide details of such sources for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Allowable Particle Size: < 65 mm
label | ○ (1*) Percentage Fines (0.07mm): <7%
label | ○ (2*) Weathering Quality Index: The aggregate shall have a quality index > or = to CA
label | ○ (3*) Crushing Resistance Test: <10% fines passing 2.36 mm sieve under test load of 130 kN
label | ○ (4*) Broken Face Content: 50% for >37.5 mm fraction and 19 mm – 37.5 mm fraction
label | TEST SPEC AND FREQUENCY: Min. 2 tests per source
label | ○ 1* = Testing method NZS 4402:1986 Test 2.8.1
label | ○ 2* = Testing method NZS 4407:2015 Test 3.11
label | ○ 3* = Testing method NZS 4407:2015 Test 3.10
label | ○ 4* = Testing method NZS 4407:2015 Test 3.14
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.04 - Source Selection Criteria - Rockfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.3.6; Table 2.1
label | SPECIFICATION DETAIL SUMMARY: Defines a well graded aggregate with slightly weathered to unweathered fragments of rock up to maximum 300 mm characteristic dimension and which is relatively free of fines and other mineral matter such that when compacted the rock fragments can achieve point-to-point contact.
label | ○ Fill materials shall be sourced from areas of cut or from alternative sources. If the Contractor wishes to propose materials from alternative sources then they shall provide details of such sources for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Allowable Particle Size: < or = 300mm
label | ○ (1*) Percentage Fines: nil
label | ○ (2*) Weathering Quality Index: The aggregate shall have a quality index > or = to CA
label | ○ (3*) Crushing Resistance Test: <10% fines passing 2.36 mm sieve under test load of 130 kN
label | ○ (4*) Broken Face Content: nil
label | TEST SPEC AND FREQUENCY: Min. 2 tests per source
label | ○ 2* = Testing method NZS 4407:2015 Test 3.11
label | ○ 3* = Testing method NZS 4407:2015 Test 3.10
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Aggregate Test Report
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.05 - Earthworks Tolerances
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.4.9
label | SPECIFICATION DETAIL SUMMARY: All earthworks shall adhere to the lines, levels and grades shown on drawings or Engineer’s instruction.
label | ○ Accuracy of surfaces under metal courses or concrete structures must preserve min. thicknesses of overlying layers.
label | ACCEPTANCE CRITERIA: Tolerances shall otherwise be as follows:
label | ○ Subgrade surfaces 0mm to - 30mm
label | ○ Batters 0mm to +100mm
label | ○ Rockfill surfaces ±200mm
label | ○ Other surfaces 0mm to + 75mm
label | TEST SPEC AND FREQUENCY: For every section of earthworks completed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.06 - Inspection of stripped surface
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.4.10
label | SPECIFICATION DETAIL SUMMARY: The Engineer must be notified before any cut or fill begins.
label | ○ The Engineer will inspect the stripped surface and decide if additional excavation, undercutting, backfilling, or other works such as drainage are needed.
label | ○ No cut or fill can proceed in the area until the Engineer approves the commencement after necessary inspections and approvals have been completed.
label | ACCEPTANCE CRITERIA: The Engineer inspects and approves the stripped surface and any required works. No cut or fill is allowed until the Engineer gives approval.
label | TEST SPEC AND FREQUENCY: Inspect prior to any cut or fill begins
label | ○ Re-inspect after cut (prior to fill)
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineers approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.07 - Standards and Testing - General
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9
label | SPECIFICATION DETAIL SUMMARY: General Testing – The locations and levels of all in-situ tests shall be recorded within 0.2m horizontally and 0.1m vertically
label | ○ All testing, both in-situ and laboratory, is to be carried out using an IANZ accredited testing organisation. Full details of the proposed testing organisation(s) shall be submitted to the Engineer for their approval.
label | ACCEPTANCE CRITERIA: General Testing – The locations and levels of all in-situ tests shall be recorded within 0.2m horizontally and 0.1m vertically
label | ○ All testing, both in-situ and laboratory, is to be carried out using an IANZ accredited testing organisation. Full details of the proposed testing organisation(s) shall be submitted to the Engineer for their approval.
label | TEST SPEC AND FREQUENCY: For all compaction testing completed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineers approval of the proposed testing organization
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.08 - General Undercutting (Outside the track formation area)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.5.6
label | SPECIFICATION DETAIL SUMMARY: The requirements for general undercutting outside the track formation area, i.e. within gullies, for the fill foundations and below areas of cut
label | ○ All organic materials, other unsuitables, materials with an undrained shear strength of less than 75 kPa or less than 3 blows per 100 mm using a Scala penetrometer to 1.5 m depth, or otherwise shown on the drawings, or instructed by the Engineer, shall be undercut.
label | ○ The depth of the undercut in materials will be specified by the Engineer when the material at the subgrade level has been exposed and evaluated.
label | ACCEPTANCE CRITERIA:
label | ○ Shear Vane:
label | – Target Criteria: No individual reading less than 75 kPa
label | Or
label | ○ Scala Penetrometer:
label | – Target Criteria: 3 blows/100mm to a depth of 1.5m
label | TEST SPEC AND FREQUENCY: Shear vane and/or Scala testing, Frequency not specified – Engineer to confirm
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Written instruction by the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.09 - Formation Undercutting
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.5.7
label | SPECIFICATION DETAIL SUMMARY: Undercuts are required if the foundation soils do not meet the minimum design requirements.
label | ○ Prior to the placement of any fill the foundation shall be inspected and approved by the Engineer.
label | ○ Two stages to expedite testing and decision making on extents of undercut:
label | 1) Initial testing using the Scala penetrometer probes to a minimum of 1.5 m depth below the base of the foundation.
label | 2) Further testing to be undertaken after excavation to the depth of the proposed undercut surface (where required) using local test pitting or full excavation of identified soft soil then undertake Scala penetrometer and shear vane testing to confirm strength of founding layers and extent/depth of any remaining softer material and/or depth to competent material.
label | ACCEPTANCE CRITERIA: Rail Embankments
label | ○ Shear vane – No individual reading less than 80 kPa and average reading >100 kPa.
label | ○ Scala - 3 blows/100mm (for cohesive soils); 5 blows/100mm (for granular soils)
label | ○ Formation for ballast& trackset Scala/Shear vane – equivalent CBR value as set out in C-ST-FO-4110.
label | TEST SPEC AND FREQUENCY: Rail Embankments:
label | ○ Shear Vane:
label | – 1 test per 5m x 5m grid and minimum of 6 tests.
label | ○ Scala Penetrometer:
label | – 1 test per 5m x 5m grid and minimum of 6 tests.
label | – Formation for ballast & track set:
label | ○ Shear Vane / Scala Penetrometer:
label | – Three tests every 5m length of track
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Conditioning and Spreading of Fill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.7.2
label | SPECIFICATION DETAIL SUMMARY: Before fill is placed in any area, the Contractor shall notify the Engineer that the fill foundation has been stripped, drained, including subsoil drains and prepared as required by the drawings and Specification and is ready for the Engineer’s inspection and approval.
label | ACCEPTANCE CRITERIA: The fill foundation has been stripped, drained, including subsoil drains and prepared as required by the drawings and Specification.
label | TEST SPEC AND FREQUENCY: Engineer to inspect and approve before fill is placed in any area
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), Photos, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.11 - Pre-Construction Compaction Testing
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.3
label | SPECIFICATION DETAIL SUMMARY: Before placing any fill the Contractor shall carry out lab testing on any material to be used for testing to confirm the max dry density and optimum water content of each material type.
label | ACCEPTANCE CRITERIA: Test results shall be provided to the Geotech Engineer to confirm the target dry densities and water contents for each material
label | TEST SPEC AND FREQUENCY: Testing shall be undertaken by an IANZ accredited testing organization and undertaken according to the standards outline in Table 2.3
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: IANZ test results, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.12 - Compaction Requirements – Buttress Fill (cohesive)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.5, Table 2.4
label | SPECIFICATION DETAIL SUMMARY: Fill materials shall be compacted so as to achieve the minimum target criteria. Should any test result fail to meet the min. target criteria the Contractor shall propose remedial measures for the Engineer’s approval
label | ACCEPTANCE CRITERIA: Shear Vane: Target Criteria: Average reading over 10 consecutive readings shall not be less than 100 kPa with no individual readings less than 80 kPa.
label | ○ In-situ Dry Density: Target Criteria: ≥ 95% Maximum Dry Density.
label | ○ Air Voids: Target Criteria: Average reading over 10 consecutive readings shall not exceed 6%, with no single reading exceeding 8%.
label | TEST SPEC AND FREQUENCY: Shear Vane: Minimum Test Frequency: 1 set per 250 m3 of fill.
label | ○ In-situ Dry Density: Minimum Test Frequency: 1 set of NDM test per 250 m2 of fill lift
label | ○ Air Voids: Minimum Test Frequency: 1 set of NDM test per 250 m2 of fill lift
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), IANZ test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.13 - Compaction Requirements – Sub- ballast (GAP40)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.5, Table 2.5
label | SPECIFICATION DETAIL SUMMARY: Before placing any fill the Contractor shall carry out lab testing on any material to be used for testing to confirm the max dry density and optimum water content of each material type.
label | ACCEPTANCE CRITERIA: In-situ Dry Density: Target Criteria: ≥ 98% Maximum Dry Density.
label | ○ Clegg Hammer Test: Target Criteria: Single test minimum clegg impact value ≥ 18. Average CIV ≥ 22 (over 5 consecutive tests)
label | TEST SPEC AND FREQUENCY: In-situ Dry Density: Minimum Test Frequency: 1 set of NDM test per 50 m2 of fill lift.
label | ○ Clegg Hammer Test: Minimum Test Frequency: 1 test per 50 m2 of fill lift.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), IANZ test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.14 - Compaction Requirements – Structural Fill / Hardfill (GAP65) / Rockfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.5, Table 2.5
label | SPECIFICATION DETAIL SUMMARY: Fill materials shall be compacted so as to achieve the minimum target criteria. Should any test result fail to meet the min. target criteria the Contractor shall propose remedial measures for the Engineer’s approval
label | ACCEPTANCE CRITERIA: In-situ Dry Density: Target Criteria: ≥ 95% Maximum Dry Density.
label | ○ Clegg Hammer Test: Target Criteria: Single test minimum clegg impact value ≥ 18. Average CIV ≥ 22 (over 5 consecutive tests) (equivalent CBR of >15%).
label | TEST SPEC AND FREQUENCY: • In-situ Dry Density: Minimum Test Frequency: 1 set of NDM test per 50 m2 of fill lift and every 1m lift. Minimum of 3 tests per approach embankment.
label | ○ Clegg Hammer Test: Minimum Test Frequency: 1 test per 50 m2 of fill lift.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: QA Checksheet(s), IANZ test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 2.15 - Grassing
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 2.9.12
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall submit to the Engineer for approval their proposed seed mixture fertiliser type and respective application rates prior to commencement of the grassing
label | ACCEPTANCE CRITERIA: Engineer to approve the proposed seed mixture fertiliser type and respective application rates
label | TEST SPEC AND FREQUENCY: Prior to commencement of grassing
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Specification for the seed mixture fertiliser type & application rate, Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT