## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 4.0 SUBSOIL DRAINAGE - COUNTERFORT DRAINS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 4.0 SUBSOIL DRAINAGE - COUNTERFORT DRAINS
section | 4.0 SUBSOIL DRAINAGE - COUNTERFORT DRAINS
checkpoint | 4.01 - Pre-commencement
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.3
label | SPECIFICATION DETAIL SUMMARY: Before any subsoil or bored inclined drain installation is commenced or fill is placed in any area the Contractor shall advise the Engineer.
label | ACCEPTANCE CRITERIA: The Contractor shall be responsible for the correct setting out of the work and shall see that the specified locations, gradients, depths and levels are strictly adhered to.
label | TEST SPEC AND FREQUENCY: Engineer to be given at least one working days’ notice, so that they may inspect the area and confirm the requirements.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation from the Engineer
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.02 - Materials – Drainage Pipe
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.1.1
label | SPECIFICATION DETAIL SUMMARY: Drainage pipe material as per spec and or drawings or as instructed by the Engineer
label | ACCEPTANCE CRITERIA: Counterfort drainage pipes shall generally be 100 mm diameter. SDR 11 HDPE pipe, or as shown on the drawings or as instructed by the Engineer.
label | ○ The pipes shall be slotted as specified on the drawings with the slots carefully formed to 2 mm width (+/- 0.2 mm) and clear of all debris and swarf. The drainpipes shall comply with the relevant specifications referred to in TNZ F/2.
label | TEST SPEC AND FREQUENCY: Visual inspection and check pipe matches spec and or drawings prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Material Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.03 - Materials – Filter Material and Backfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.1.2
label | SPECIFICATION DETAIL SUMMARY: The counterfort drain pipe shall be surrounded and immediately overlain by filter materials as defined in TNZ F/2 and Table 4.1
label | ACCEPTANCE CRITERIA: Filter material shall be placed in the trench to the thickness shown on the drawings or as instructed by the Engineer.
label | ○ Backfill material for the remainder of the trench shall be either clean well graded 40/20 or 20/7 material; or filter material as defnied in TNZ F/2 and Table 4.1, or as instructed by the Engineer
label | – – – – – – – – – – – – – – – – – –
label | Table 4.1: Grading of backfill
label | Table sieve aperture ¦¦ Percentage passing
label | – – – – – – – – – – – – – – – – – –
label | 53 mm ¦¦ 100
label | 13.2 mm ¦¦ 10 maximum
label | 4.75 mm ¦¦ 0
label | – – – – – – – – – – – – – – – – – –
label | TEST SPEC AND FREQUENCY: Visual inspection and check materials match spec and or drawings and or Engineers instruction
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Material Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.04 - Trench Excavation
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.2
label | SPECIFICATION DETAIL SUMMARY: Trench grade and depth as shown on the drawings or as instructed by the Engineer.
label | ACCEPTANCE CRITERIA: Trench widths shall be a minimum of 300 mm increasing to a minimum of 600 mm for trenches greater than 1 m deep.
label | ○ Trenches shall be excavated to depth/grade as shown on drawings or as instructed by the Engineer
label | TEST SPEC AND FREQUENCY: For every section of trench excavated
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.05 - Bedding and Installation of Drainage Pipe
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.3
label | SPECIFICATION DETAIL SUMMARY: Installation of pipe and bedding material as per spec and or drawings
label | ACCEPTANCE CRITERIA: The drainage pipe lengths shall be joined following the manufacturer’s instructions or as approved by the Engineer, with the pipe jointing such as to leave a smooth flush internal surface.
label | ○ Min. 75mm of filter material which completely surrounds the drainage pipe
label | TEST SPEC AND FREQUENCY: For every section of pipe installed
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: WITNESS
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 4.06 - Backfilling
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.4.2.4
label | SPECIFICATION DETAIL SUMMARY: Contractor to propose, for the Engineers approval, a method of compaction and testing procedures to demonstrate that relative density has been achieved.
label | ACCEPTANCE CRITERIA: The drain pipe installation shall be inspected and approved prior to backfilling.
label | ○ Backfill above the filter material shall be carefully placed in 300mm layers and compacted into a min Relative Density of 70%
label | TEST SPEC AND FREQUENCY: Method of compaction and testing to be reviewed by the Engineer. Each length of pipe installed to be inspected and approved by the Engineer.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s), Compaction methodology
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT