## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 6.0 SUBSOIL DRAINAGE - OUTLET STRUCTURES | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 6.0 SUBSOIL DRAINAGE - OUTLET STRUCTURES
section | 6.0 SUBSOIL DRAINAGE - OUTLET STRUCTURES
checkpoint | 6.01 - Materials & Construction
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 4.6
label | SPECIFICATION DETAIL SUMMARY: Materials used and construction as per drawings or in other sections of this spec.
label | ACCEPTANCE CRITERIA: Materials to be used for the outlet structures shall be as specified on the drawings or in other sections of this Specification.
label | ○ Outlet structure shall be constructed in accordance with the drawings and relevant sections of this Specs.
label | TEST SPEC AND FREQUENCY: For every section of outlet structure
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, Dockets, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T