## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 8.0 GROUND ANCHORS - BARS | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 8.0 GROUND ANCHORS - BARS
section | 8.0 GROUND ANCHORS - BARS
checkpoint | 8.01 - Anchor Bars
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.3.1.1
label | SPECIFICATION DETAIL SUMMARY: All anchors bars should be grade 500E as specified in the drawings.
label | ○ Mill certs shall be submitted to the Engineer for each batch.
label | ACCEPTANCE CRITERIA: All anchors bars should be grade 500E as specified in the drawings.
label | ○ Mill certs shall be submitted to the Engineer for each batch of bar showing the ultimate late, the yield, and percentage of elongation at yield load and the modulus of elasticity.
label | ○ Bar shall be hot dip galv with min. coating thickness of 600gm/m2
label | TEST SPEC AND FREQUENCY: For each batch of bar
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Mill certs, Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.02 - Cement Grout
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.3.2
label | SPECIFICATION DETAIL SUMMARY: Cement used for grouting shall comprise fresh Portland Cement complying with NZS3122 : 1995, water and approved additives.
label | ○ The proportions of cement, water and additives shall conform to NZS 3109 to produce a cement-rich grout having a standard-cured compressive strength of not less than 20 MPa at 7 days and 40 MPa at 28 days when tested in accordance with NZS 3112.
label | ACCEPTANCE CRITERIA: Cement for grouting must have a compressive strength of not less than 20 MPa at 7 days and 40 MPa at 28 days.
label | ○ Sand or other materials shall not be used unless approved by the Engineer.
label | TEST SPEC AND FREQUENCY: Compressive testing at 7 and 28 days for each batch of concrete poured
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Dockets, QA Checksheet(s), Lab Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.03 - Anchor Fabrication
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.4.1
label | SPECIFICATION DETAIL SUMMARY: Anchors shall be fabricated under controlled (factory) conditions in accordance with the approved method statement including the shop/fabrication drawings), using organisations and persons experienced in that type of work.
label | ACCEPTANCE CRITERIA: The fabricated anchors will be inspected by the Engineer prior to installation. Any anchor which is in any way damaged or fails to meet the specified requirements will be rejected
label | TEST SPEC AND FREQUENCY: Inspection by Engineer prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.04 - Drilling Logs
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.4.2
label | SPECIFICATION DETAIL SUMMARY: The Contractor must use suitable equipment & techniques for the site, drillholes must be 150mm in diameter, air drilling unless approved by the Engineer, and polymer drilling fluids should not be used.
label | ACCEPTANCE CRITERIA: Drillholes must be performed according to drawings or Engineer's instructions, within 2° alignment
label | The summary log shall record at least the following:
label | ○ Ground anchor number and type
label | ○ Date and time of the start and finish of the drilling
label | ○ Length, diameter and inclination of the hole
label | ○ Method of drilling hole
label | ○ Ground conditions encountered and ease of drilling
label | ○ Depth at which rock was encountered
label | ○ Any water encountered
label | ○ Location and extent of air loss
label | ○ Problems such as caving that occurred during drilling and any drilling fluid, flushing medium or casing used
label | ○ Length of casing used
label | ○ Date and time of clearing out the hole
label | ○ Length of bar installed and any as built details which vary from those shown on the Drawings
label | ○ Date and time of grouting
label | ○ Nominal and actual volume of grout placed
label | TEST SPEC AND FREQUENCY: Drilling logs provided within 1 working day of completion of drilling hole.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Drilling Log
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.05 - Installation
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.4.3
label | SPECIFICATION DETAIL SUMMARY: Before anchor installation, clean the drillhole with air and wait for approval from the Engineer.
label | ○ Install anchors according to fabricator's recommendations and Contractor's method statement, ensuring fixed length is within the specified anchorage zone. Handle equipment to prevent damage to anchor strands and corrosion protection.
label | ○ Provide centralizers if needed. Keep individual anchor records for installation dates and problems.
label | ACCEPTANCE CRITERIA: Installation of an anchor will not be permitted until the relevant drillhole log has been approved by the Engineer.
label | TEST SPEC AND FREQUENCY: Engineer to approve drillhole log prior to install
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.06 - Grouting
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.4.4
label | SPECIFICATION DETAIL SUMMARY: The grouting equipment must produce homogenous grout free of lumps and undispersed cement, with a pumping system featuring valves and calibrated pressure gauges for continuous grout circulation and pumping with an accuracy of +/- 0.1 MPa grout pressure, following the Contractor's approved method statement.
label | ACCEPTANCE CRITERIA: The grouting procedures shall be as per the Contractor’s approved method statement and shall conform to the requirements of BS 8081.
label | ○ The Contractor shall keep records of all grouting works. The information provided shall be as listed in the Contractor’s method statement but as a minimum shall not be less than specified in BS 8081.
label | TEST SPEC AND FREQUENCY: Records provided to the Engineer within 1 working day of completion of each and every any stage of grouting
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Grout Records
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.07 - Stressing (Lock off)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.5
label | SPECIFICATION DETAIL SUMMARY: After completion of backfilling behind the wall and around the ground anchor, and following the Engineer’s written approval, the anchor headworks shall be completed with the anchor plate and nut installed.
label | ACCEPTANCE CRITERIA: The anchor nut shall then be tightened and locked off to 25 kN
label | TEST SPEC AND FREQUENCY: Following Engineer’s approval
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.08 - Ground Anchor Acceptance Test – 83.84km only
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.6.1
label | SPECIFICATION DETAIL SUMMARY: One acceptance test is required during construction for the ground anchors at 83.84 km site only.
label | ○ Acceptance tests shall be carried out on anchors forming part of the permanent works as a measure of quality control.
label | ACCEPTANCE CRITERIA: The testing will be in accordance with BS 8081:2015 and ISO 22477-5:2018.
label | ○ Test anchors must be axially loaded, either by cutting the slope perpendicular to the anchor or using a stressing chair.
label | ○ If a ground anchor fails acceptance testing, the Contractor informs the Engineer and conducts additional testing.
label | TEST SPEC AND FREQUENCY: The Contractor shall give the Engineer at least 2 working days’ notice of testing to be carried out. The Engineer will be present during the testing.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval, Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.09 - Anchor Stressing & Testing
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.6.2
label | SPECIFICATION DETAIL SUMMARY: The Contractor shall keep records of all anchor stressing and testing.
label | ACCEPTANCE CRITERIA: The information provided shall be as listed in the Contractor’s method statement but as a minimum shall not be less than specified in BS 8081.
label | TEST SPEC AND FREQUENCY: The Engineer must receive stressing records and test results for a specific anchor within 5 working days of its completion.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Stress and Test Records
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 8.10 - Acceptance Load Test
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.6.3
label | SPECIFICATION DETAIL SUMMARY: The objectives of the acceptance load tests are to take any “slack” out of the installed anchor system and to demonstrate that installed anchors are able to provide at least the design working load capacity.
label | Loading Procedure as outlined in Table 5.1 of the Specifications 5.6.3.3
label | ACCEPTANCE CRITERIA: The creep rate α for acceptance test shall be checked according to Annex A of ISO 22477-5:2018.
label | α = (sb-sa)/log(tb/ta) <2 mm where: sa is the displacement of the anchor head at the time ta; sb is the displacement of the anchor head at the time tb; ta is the start of the respective time interval; and tb is the end of the respective time interval.
label | ○ The ground anchor with creep rates exceeding the above criteria will be deemed to have failed.
label | TEST SPEC AND FREQUENCY: The tests shall be carried out on all the installed anchor and at a location to be agreed by the Engineer on site. Acceptance ground anchor tests shall be undertaken prior to placement of the timber lagging.
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Acceptance Test Results, Written confirmation of Engineer’s approval,
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT