## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CH 136 - 9.0 GROUND ANCHORS - TIE-BACK | itp |  |  |  |  | Kiwirail - North Auckland Line Recovery - CH 136 - 9.0 GROUND ANCHORS - TIE-BACK
section | 9.0 GROUND ANCHORS - TIE-BACK
checkpoint | 9.01 - Anchor Bars
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.3.1.1
label | SPECIFICATION DETAIL SUMMARY: All anchors bars should be grade 500, complting to the requirements of BS 8081 and BS 5986.
label | ○ Mill certs shall be submitted to the Engineer for each batch.
label | ACCEPTANCE CRITERIA: Mill certs shall be submitted to the Engineer for each batch of bar showing the ultimate late, the yield, and percentage of elongation at yield load and the modulus of elasticity.
label | ○ Bar shall be hot dip galv with min. coating thickness of 600gm/m2
label | TEST SPEC AND FREQUENCY: For each batch of bar
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Mill certs, Dockets
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 9.02 - Cement Grout
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 5.3.2
label | SPECIFICATION DETAIL SUMMARY: Cement used for grouting shall comprise fresh Portland Cement complying with NZS3122 : 1995, water and approved additives.
label | ○ The proportions of cement, water and additives shall conform to NZS 3109 to produce a cement-rich grout having a standard-cured compressive strength of not less than 20 MPa at 7 days and 35 MPa at 28 days when tested in accordance with NZS 3112.
label | ACCEPTANCE CRITERIA: Cement for grouting must have a compressive strength of not less than 20 MPa at 7 days and 30 MPa at 28 days.
label | ○ Sand or other materials shall not be used unless approved by the Engineer.
label | ○ Water cement ratio shall not be less than 0.4
label | TEST SPEC AND FREQUENCY: Compressive testing at 7 and 28 days for each batch of concrete poured
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Dockets, Lab Test Results
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T
checkpoint | 9.03 - Deadman Anchor Blocks
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.1
label | SPECIFICATION DETAIL SUMMARY: Deadman anchor block excavation should follow the drawings' levels and dimensions, with appropriate plant used to avoid disturbance.
label | ○ Temporary support or battering of excavation sides is approved by the Engineer.
label | ○ Reinforcing steel should be placed, and the sides and base cleaned of loose or softened material.
label | ○ The completed excavation and reinforcing steel must be inspected and approved before placing concrete, and the backfill must comply with the Specification and drawings.
label | ACCEPTANCE CRITERIA: Excavation and reinforcing steel comply with the drawings. Engineer to inspect and approve before placing concrete.
label | TEST SPEC AND FREQUENCY: Pre-pour inspection prior to concrete pour
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written Confirmation of Engineer’s Approval, Phoros, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.04 - Tie-back Anchor Fabrication
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.2
label | SPECIFICATION DETAIL SUMMARY: Anchors shall be fabricated under controlled (factory) conditions in accordance with the approved method statement including the shop/fabrication drawings), using organisations and persons experienced in that type of work.
label | ACCEPTANCE CRITERIA: The fabricated anchors will be inspected by the Engineer prior to installation. Any anchor which is in any way damaged or fails to meet the specified requirements will be rejected.
label | TEST SPEC AND FREQUENCY: Inspection by Engineer prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.05 - Tie-back Anchor Installation
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.3
label | SPECIFICATION DETAIL SUMMARY: The installation of a tie-back anchor bar must follow the drawings or the Engineer's instructions, with the contractor marking the alignment for approval.
label | ○ The trench must be excavated to the required depths and minimize damage.
label | ○ The bar, wrapped in Densotape and uPVC duct, should be connected to the deadman anchor and anchor headworks.
label | ○ The contractor must maintain records of the installation date and any issues encountered.
label | ACCEPTANCE CRITERIA: Installation of a tie-back anchor bar must follow the drawings or the Engineer’s instructions. Engineer to approve aligment.
label | TEST SPEC AND FREQUENCY: Inspection by Engineer prior to installation
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.06 - Deadman ground beam and anchor bar backfill
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.4.3
label | SPECIFICATION DETAIL SUMMARY: After the deadman ground beam reaches its design strength, the excavation around it & the tie-back anchor bar trench must be backfilled with approved material, following the Engineer's approval.
label | ○ This backfilling must be carried out in a controlled manner, ensuring the deadman and tie-back anchor bar are not disturbed or damaged.
label | ACCEPTANCE CRITERIA: Approved backfill material to be used. Backfilling to be carried out to the Engineer’s approval.
label | TEST SPEC AND FREQUENCY: Engineers approval Prior to backfill
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Written confirmation of Engineer’s methodology and approval
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: HOLD
label | PS4 OWNER SIGN OFF: T&T
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9.07 - Stressing (Lock off)
label | DRAWING / SPECIFICATION REF.: T+T NAL Recovery Specifications: 6.5.1
label | SPECIFICATION DETAIL SUMMARY: After completion of backfilling behind the wall and around the ground anchor, and following the Engineer’s written approval, the anchor headworks shall be completed with the anchor plate and nut installed.
label | ACCEPTANCE CRITERIA: The anchor nut shall then be tightened and locked off to 25 kN
label | TEST SPEC AND FREQUENCY: Following Engineer’s approval
label | CONTROL TYPE I.E. CHECKSHEET / RECORDS: Photos, QA Checksheet(s)
label | HOLD / WITNESS: HOLD
label | EXTERNAL (REQUESTED BY PS4) / INTERNAL (JFC REQUIREMENT): External
label | PS3 OWNER: JFC
label | HOLD / REVIEW / WITNESS: REVIEW
label | PS4 OWNER SIGN OFF: T&T