## Table 1
[5 empty] | Inspection and Test Plan - Hume Fwy Civil Works | [7 empty] | Document # ITP - 010
[13 empty] | Revision : 1 | 3-Sep
Client: | DTP |  |  |  | Construction Process: Hume Fwy Civil Works incl. bridge expansion joint and drain clearing |  |  |  | Prepared by: |  | Reviewed by : |  | Approved by :
Project: | FY26 Hume Hwy Pave Rehab | [7 empty] | Justin Barnes |  | Name: Cameron Beattie |  | Name: | Cameron Beattie
Contract: | Tallarook 100177.10401 |  |  |  | Specifications: VicRoads Sections 660 Bridge Expansion Joints |  |  |  | Project Engineer |  | Fulton Hogan |  | Client | DTP
Date: | / /
Lot No: |  |  |  |  | Location: Hume Fwy Tallarook Ch 223,890 to 224,410
Item |  | Task/Activity Description |  |  | Inspection / Controls and Verification Detail | [5 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility
No. |  |  |  |  | Frequency | Acceptance Criteria |  | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Fulton Hogan Industries | Client | Date | Comments
1 |  | Preliminary Works
1.1 |  | Submission of Project Management Documentation |  |  | 2 weeks prior to commencement | Receival of all relevant documentation including HSMP/OHS/QMP/TMPEMP/Procedures |  | Cl 160.A4 Cl 176.A3 | ITP Signed | Completed ITP | HP | Project Engineer / Supervisor / Superintendent
1.2 |  | Site confirmation and vegetation removal |  |  | Prior to commencement | Joint site inspection to determine agreed scope of work including extent of drainage / vegetation work |  | Cl 176.I1 Cl 100.5 Cl 100.10 | ITP Signed | Completed ITP | HP | Project Engineer / Supervisor / Superintendent
1.3 |  | Placement of VMS boards |  |  | 2 weeks prior to commencement | Approval of installation location for VMS boards |  | Cl 100.11 | ITP Signed | Completed ITP | HP | Project Engineer / Supervisor / Superintendent
1.4 |  | Service location |  |  | Prior to commencement | All services marked out and located on site |  | Cl 100.13 | ITP Signed | Completed ITP | HP | Project Engineer / Supervisor / Superintendent
1.5 |  | Product approval |  |  | Prior to commencing works | Approval of products / materials |  | Sec 663 | ITP Signed | Completed ITP | HP | Project Engineer / Supervisor / Superintendent
1.6 |  | Methodology and works sequence approved |  |  | Prior to commencing works | Approval of methodology and works sequence |  | Sec 660 | ITP Signed | Completed ITP | HP | Project Engineer / Supervisor / Superintendent
2 |  | Civil Works
2.1 |  | Vegetation and verge removal |  |  | Prior to asphalting | All approved vegetation and verge stripping works completed |  | Cl 100.1 Cl 204.03 | Inspection | Completed ITP | IP | Project Engineer / Supervisor / Superintendent
2.2 |  | Drain clearing |  |  | Prior to asphalting | Drain cleared and reshaped appropriately |  | Cl 100.1 Cl 700.1 | Inspection | Completed ITP | IP | Project Engineer / Supervisor / Superintendent
2 |  | Expansion Joint Demolition & Installation
2.1 |  | Saw cutting and removal of existing nosing |  |  | Prior to new nosing installation | Sawcutting of all existing asphalt completed and all loose material removed from existing recess and a clear base and sides present to pour new nosing. Sand / grit blasting recommended |  | This ITP Manufacturers Specification | Inspection | Completed ITP | HP* | Project Engineer / Foreman |  | N/A
2.2 |  | Preparation and pouring of nosing |  |  | After sawcutting / demolition works completion | Once the recess is clear of debris, insert styrofoam gap former, mix and pour the nosing polymer as per manufactuers specification |  | This ITP Manufacturers Specification | Approval Correspondance | Completed ITP | IP | Project Engineer / Supervisor / Superintendent
2.3 |  | Preparation for joint seal |  |  | After nosing has been poured and set | Once the polymer has cured, styrofoam filler can be removed. 5mm x 5mm chamfer to be cut into edges of nosing. Undertake further grit blasting, prime the surface and install backing rod |  | This ITP Manufacturers Specification | Approval Correspondance | Completed ITP | IP | Project Engineer / Supervisor / Superintendent
2.4 |  | Pouring of silicone sealant |  |  | After backing rod has been inserted | Mix and install approved sealant as per manufactuers specification, ensuring a 12mm recess below pavement level |  | This ITP Manufacturers Specification | Approval Correspondance | Completed ITP | IP | Project Engineer / Supervisor / Superintendent
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  |  |  | Position: |  | Signature:
Legend
HP | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent |  |  |  | IP Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point |  | Work shall not proceed past the HP* until released by FH |  |  |  | TP Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point |  | An inspection which may be witnessed by the Superintendent or Client |  |  |  | SCP Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point |  | Written or verbal approval given by the Superintendent |  |  |  | SC Surfacing Course WC Wearing Course IC1 Intermediate Course 1 IC2 Intermediate Course 2 BC Base Course