## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-010 - Preliminary & Civil Works - Tallarook | itp |  |  |  |  | ITP-010 - Preliminary & Civil Works - Tallarook Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Submission of Project Management Documentation
label | FREQUENCY: 2 weeks prior to commencement
label | ACCEPTANCE CRITERIA: Receival of all relevant documentation including HSMP/OHS/QMP/TMPEMP/Procedures
label | REFERENCE DOCUMENTS: Cl 160.A4 Cl 176.A3
label | INSPECTION/TEST METHOD: ITP Signed
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Site confirmation and vegetation removal
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: Joint site inspection to determine agreed scope of work including extent of drainage / vegetation work
label | REFERENCE DOCUMENTS: Cl 176.I1, Cl 100.5, Cl 100.10
label | INSPECTION/TEST METHOD: ITP Signed
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Placement of VMS boards
label | FREQUENCY: 2 weeks prior to commencement
label | ACCEPTANCE CRITERIA: Approval of installation location for VMS boards
label | REFERENCE DOCUMENTS: Cl 100.11
label | INSPECTION/TEST METHOD: ITP Signed
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Service location
label | FREQUENCY: Prior to commencement
label | ACCEPTANCE CRITERIA: All services marked out and located on site
label | REFERENCE DOCUMENTS: Cl 100.13
label | INSPECTION/TEST METHOD: ITP Signed
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Product approval
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Approval of products / materials
label | REFERENCE DOCUMENTS: Sec 663
label | INSPECTION/TEST METHOD: ITP Signed
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Methodology and works sequence approved
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Approval of methodology and works sequence
label | REFERENCE DOCUMENTS: Sec 660
label | INSPECTION/TEST METHOD: ITP Signed
label | RECORD OF CONFORMITY: Completed ITP
label | HP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2 - Civil Works
checkpoint | 2.1 - Vegetation and verge removal
label | FREQUENCY: Prior to asphalting
label | ACCEPTANCE CRITERIA: All approved vegetation and verge stripping works completed
label | REFERENCE DOCUMENTS: Cl 100.1, Cl 204.03
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
checkpoint | 2.2 - Drain clearing
label | FREQUENCY: Prior to asphalting
label | ACCEPTANCE CRITERIA: Drain cleared and reshaped appropriately
label | REFERENCE DOCUMENTS: Cl 100.1, Cl 700.1
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
section | 2 - Expansion Joint Demolition & Installation
checkpoint | 2.1 - Saw cutting and removal of existing nosing
label | FREQUENCY: Prior to new nosing installation
label | ACCEPTANCE CRITERIA: Sawcutting of all existing asphalt completed and all loose material removed from existing recess and a clear base and sides present to pour new nosing. Sand / grit blasting recommended
label | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: Completed ITP
label | HP*
label | RESPONSIBILITY: Project Engineer / Foreman
date | Date Completed:
checkpoint | 2.2 - Preparation and pouring of nosing
label | FREQUENCY: After sawcutting / demolition works completion
label | ACCEPTANCE CRITERIA: Once the recess is clear of debris, insert styrofoam gap former, mix and pour the nosing polymer as per manufactuers specification
label | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
label | INSPECTION/TEST METHOD: Approval Correspondance
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
checkpoint | 2.3 - Preparation for joint seal
label | FREQUENCY: After nosing has been poured and set
label | ACCEPTANCE CRITERIA: Once the polymer has cured, styrofoam filler can be removed. 5mm x 5mm chamfer to be cut into edges of nosing. Undertake further grit blasting, prime the surface and install backing rod
label | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
label | INSPECTION/TEST METHOD: Approval Correspondance
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
checkpoint | 2.4 - Pouring of silicone sealant
label | FREQUENCY: After backing rod has been inserted
label | ACCEPTANCE CRITERIA: Mix and install approved sealant as per manufactuers specification, ensuring a 12mm recess below pavement level
label | REFERENCE DOCUMENTS: This ITP Manufacturers Specification
label | INSPECTION/TEST METHOD: Approval Correspondance
label | RECORD OF CONFORMITY: Completed ITP
label | IP
label | RESPONSIBILITY: Project Engineer / Supervisor / Superintendent
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: