## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
387b04e8-51e3-4302-8abc-1c71f1ab1815 | checklist | FH-ZU2-QU-ITP048 - ALER 3 General Fitout & Finishes - Rev 1 | itp | ITP048 - ALER 3 General Fitout & Finishes
71765bcc-e035-418c-a522-5c7240d442bd | section | 1.0 - Preliminary Activities
82148329-5883-42a8-8325-d0dbd4a07fb0 | checkpoint | 1.1 - Check for correct documentation
1569920e-2755-574b-8a06-60bf071dc436 | note | Frequency - Prior to commencing works
affb0c67-1f44-5292-ab98-4b7a44e8c3bc | note | Acceptance Criteria - Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
71107fc7-6663-55e5-b68a-12157c532489 | note | ○ Current revisions of these documents to be obtained via Aconex or ACC.
0e51160d-a86c-525b-a903-8d59e3472d2e | note | Reference Documents - Current Revisions in Aconex or ACC
988e5233-0430-535f-be0d-6b707a317ffe | note | Inspection/Test Method - Verify
987ec886-fe66-56af-99e4-7c3f0440f920 | note | Record of conformity - This ITP Signed
9222eb23-03bb-526f-a110-bbca88644113 | note | HP*
c65ab3c7-8c17-5283-9f03-7863c9a3797e | note | Responsibility - Project / Site Engineer
46b8d3ca-c2b2-5117-9878-4e69550be08c | date | Date Completed:
00bd31c9-51b6-4065-bb1c-23248f858bcb | checkpoint | 1.2 - Implementation of all measures and controls
2f378e9f-6220-5f4f-af53-aa9da0e06e57 | note | Frequency - Prior to commencing works
08691e97-681a-53fa-a3e9-6a4ed1efe100 | note | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
52184e54-dc99-518b-8ee2-08ef578a956b | note | Reference Documents - PSP, EMP, TMP, SWMS, WMS
e5e30699-29ff-5390-838d-b21ef494a819 | note | Inspection/Test Method - Visual Inspection
57af1f02-d0f2-5a82-b4d4-f77173ae357c | note | Record of conformity - This ITP Signed
a43a0dad-828c-5f00-bf86-645cf682a645 | note | HP*
ab5f3394-03e4-5ca2-9985-c69c5dda08d6 | note | Responsibility - Project / Site Engineer
c32c003c-fee6-597d-9299-b2a2b31ec56f | date | Date Completed:
61c81f21-0b85-4692-bf90-050f16a16ef8 | checkpoint | 1.3 - Check all materials & shop drawings have been approved for use
0a7ad73c-35f4-5d85-a02a-2ade80021ebb | note | Frequency - Prior to commencing works
6ee02961-c947-5c42-a3eb-a235bdc9fcaf | note | Acceptance Criteria - Ensure all materials & shop drawings have been reviewed & approved by BECA.
ca44d3f9-6ce7-50e0-a84a-0efe38ef87d6 | note | Reference Documents - Materials Schedule Drawing Package 030
3a62eb20-2d63-50f3-a38d-960457106a3b | note | Inspection/Test Method - Verify
f1c5b363-89d6-5e54-bd96-3c6eaa0a3ceb | note | Record of conformity - Aconex Register
229df714-be81-51cc-aa62-2f7382698309 | note | HP*
b77553e5-2f23-5c2e-938d-5a9692739add | note | Responsibility - Project / Site Engineer
73f9a687-a0fa-5d40-a5d0-99d7e83f7658 | date | Date Completed:
11475bc7-6fc5-42b4-bf59-2bc829b48a8d | checkpoint | 1.4 - Material inspections (off-site)
31395cfb-c027-5b7a-8897-a1df22613fb8 | note | Frequency - Prior to commencing works
456f57d5-aeb7-55af-9172-c3ec988d652e | note | Acceptance Criteria - WITNESS POINT
3c5f7c5e-fd95-57b8-b5ac-1d8f86606c0b | note | ○ Give notice for inspection of fabricated window assemblies at the factory ready for delivery.
92fc7cf0-d690-5652-a308-4f4ee449e244 | note | Reference Documents - ZULU- BECA-001- SPC-00005, 0451
adca769b-ff5e-5e03-b511-43a10b028532 | note | Inspection/Test Method - Visual inspection
2543a1ac-3332-5fe4-ab66-1be8e07f0177 | note | Record of conformity - This ITP Signed, Inspection Report
88bc23fd-18bb-56c7-81ac-ac2ebc4a8719 | note | WP
f91a965d-b6cd-5da8-a348-fd9c98c5e9d6 | note | Responsibility - Project / Site Engineer / Principals Representative
e9f1c215-9994-5de2-97d4-f98b2674dc74 | date | Date Completed:
43569aff-6d15-4771-9687-5e8b774e26d4 | checkpoint | 1.5 - Material inspections (on-site)
3fada14a-0599-5a0f-9c27-71813fb813cc | note | Frequency - Prior to commencing works
e607b5a3-3c18-536f-b8e4-a8dbc7ec20b7 | note | Acceptance Criteria - Complete a material inspection for deliveries of the following items:
b4c49d92-8e7c-53da-ad8d-a15f75d3494c | note | ○ Roofing
674db405-6806-5c07-b8d7-0e3986785c40 | note | ○ Light Steel Framing
4d811c4a-5777-51bd-a2e2-e1d5bdf9b955 | note | ○ Glazing
cd18de37-f729-544e-bf48-5a9f7e079499 | note | ○ Insulation/sarking
4f155bad-adf8-5a0b-989e-155d6e5e3641 | note | Reference Documents - FH Quality Procedures
a70ef51e-dff4-5b7d-a4f8-105d58daef3c | note | Inspection/Test Method - Visual inspection
6291d2d6-75d8-587c-ad09-689fbab7a4f6 | note | Record of conformity - This ITP Signed
b4055b36-af17-500d-b153-5a5f5b24f24b | note | HP*
fa529de5-2aa8-5890-be6a-91d9b2dbfdbe | note | Responsibility - Project / Site Engineer
91feedfd-b5fe-5b36-a53e-9e68131a330c | date | Date Completed:
9143c8d9-8ee2-4557-bcd9-d997b88ea9d8 | checkpoint | 1.6 - Survey Set out
f5e87f8b-3baa-55b0-8790-4255cd32c7a5 | note | Frequency - Each Lot
d7263785-4e98-520c-8d65-f92c2c5feb87 | note | Acceptance Criteria - Confirm survey set out has been completed on site prior to commencement of works
04ab567b-c6ad-5eaf-b20c-36df9422d4b1 | note | Reference Documents - Survey Process
80e80219-027b-51af-9384-72030f58b845 | note | Inspection/Test Method - Visual Inspection
871b29e4-d475-5e5c-b832-04dd8a817ef6 | note | Record of conformity - This ITP Signed
8344e273-9b4a-5d5f-9fda-52bff5d0c789 | note | HP*
78c87179-9954-5d7a-a21a-087bd8b6a9b2 | note | Responsibility - Project / Site Engineer
909a765f-6660-517a-8dc6-bd1c08115003 | date | Date Completed:
8731080e-0b92-47d4-ae7a-72bb32cd6cd5 | section | 2.0 - Construction
e77382a2-a4bf-45cb-97e4-f0023616ae40 | checkpoint | 2.1 - Roofing
3784af9f-5892-5cd1-9455-d459ebe377c4 | note | Frequency - Each Lot
f22ce040-f9e4-5b5f-ab6a-3fa03f5c0636 | note | Acceptance Criteria - WITNESS POINT
fc346737-5241-58d3-91a1-2e8ca5e9829e | note | ○ Check for installation of the following against manufacturers specification, project drawings and AS/NZS standards:
b5b0d7d2-e697-5922-a517-3e3ca882b25b | note | — Roofing battens
40687f3a-c136-5417-91ea-7d23f3d30ad6 | note | — Insulation Blanket
21fc8278-e3fb-5be1-8668-e64478509a3c | note | — Sarking/vapour barrier
129c91e7-0a61-520b-b366-c6db966064f9 | note | — Roofing Sheets
91505c7c-91ce-5a68-b55b-3e3fb78fb359 | note | — Gutter Hail/Leaf Guards
3b259b48-5f9b-5ea0-be94-f7d46b1b904c | note | — Eaves Soffits
1539d4f9-a1ff-5517-8a48-a2f39f046f31 | note | ○ Notice shall be given for inspection of roofing supports prior to covering up or concealing
60261554-21ee-595f-8764-a583906b8732 | note | Reference Documents - Drawing set 030, AS 1562.1, ZULU- BECA-001- SPC-00005, 0423
c0c00af0-98cf-5af3-9e1e-94c4232641bc | note | Inspection/Test Method - Visual Inspection
96e20172-ee0c-5572-b637-a0a04b142c27 | note | Record of conformity - This ITP Signed, BE ITC, Compliance Certificate
c7ab52b9-a4c0-53e8-988a-7ac7209a86a6 | note | WP
e692a7bf-292b-5a9d-92b4-c1ea03f5c0c5 | note | Responsibility - Project / Site Engineer / Principals Representative
fff9f376-f00b-5a4c-a88e-4edae4307def | date | Date Completed:
34e813d4-8b56-48fe-8d8c-7245c3d4af0f | checkpoint | 2.2 - Glazing
9e92b8a8-be91-5a49-ba54-9fe6494e2f05 | note | Frequency - Each Lot
64a4b9f7-45eb-5f4d-a377-aa668ef8e24a | note | Acceptance Criteria - WITNESS POINT
1bc9ed2e-a278-5335-8a57-4e34c382c9a0 | note | ○ Installation of all windows as per the project drawings and manufacturer specifications.
fe39e5d1-7527-5e4c-9bc2-1b402e801208 | note | ○ Check windows are plumb, correctly sealed and securely fixed.
112858cf-968f-5622-b1ce-40e6c9d7863d | note | ○ Give notice for inspection of the following:
0788560b-600f-541e-a156-454f001778fe | note | — Openings prepared to receive Windows in precast walls
fffa979b-da36-50f8-b4e2-6a48f14dc470 | note | — Commencement of Window installation
81ccbf36-1e0a-5186-b219-d6a36235a850 | note | ○ Certification required confirming that window assemblies conform to AS 2047 (2014)
6cf1bde9-0a2f-5d00-bc63-2ab5ada7f616 | note | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0451, AS 2047
0b6f6314-46bf-582b-b2fc-3f7c9d74cf22 | note | Inspection/Test Method - Visual Inspection
027aece3-7ea8-5182-b5e4-00be70b55401 | note | Record of conformity - This ITP Signed, BE ITC, Compliance Certificate
eca327c5-6555-5094-abf4-cf004b4124a5 | note | WP
25c551c9-0a25-5bf2-b68a-9d16f1da537c | note | Responsibility - Project / Site Engineer / Principals Representative
d966bf25-6a52-5a0d-8e8e-ff16e70e584e | date | Date Completed:
39d4c039-3163-466b-bdad-2098d01f1612 | checkpoint | 2.3 - External & Internal Door & Jambs
18cf1767-660d-5e13-a79c-b1fcaa2c0a17 | note | Frequency - Each Lot
721b0717-b3a9-509c-978a-76d816409d28 | note | Acceptance Criteria - WITNESS POINT
bf24d47f-c3a5-59b8-9b22-f0e0a3c0470b | note | ○ Installation of the following
970cdf2b-6462-556b-b717-014af8accd20 | note | — Door frames/jambs
84134c1d-01ba-52d1-aabb-d086ccd5bb25 | note | — Hang doors
3a32ecfe-f375-5384-8e90-7b430a86eaac | note | — Locks, latches & handles
1160613c-63cf-57cc-985a-10f0c2561980 | note | — Fire Doors – as per certifiers requirements
4e5c8e89-6599-5efc-8b6a-0b154dbe733f | note | ○ Check for
7c0c9c66-48a6-56b9-a55e-26186d6a04db | note | — Plumbness
ad291b33-4e87-561c-a03d-10e9cff9fbd7 | note | — Securely affixed
d4d4b501-7792-5e8e-8e75-feb07e58e2e1 | note | — Proper function
d2327fa9-8f0e-521e-8180-b9edad387aa5 | note | — As per drawing sizing & locations
ec0e4646-ab53-5bdf-8379-73c1bfeea38c | note | — Adequate clearance bottom of doors
7ce75aca-f216-57e9-a943-23d2527e7e23 | note | — Sealing installed as required
cd31b31b-070e-5864-8272-c55b0c3f9aa6 | note | ○ Give notice for inspection of door frames in place prior to any joinery/trim being installed.
c266d930-97ba-5916-8fb4-b70ba17c3530 | note | Reference Documents - Drawing Set 030, ZULU- BECA-001- SPC-00005, 0455
e55252f3-d8fd-5cad-b0f2-df82027f27ac | note | Inspection/Test Method - Visual Inspection
fc7b07ae-434e-5800-ade2-68347b4d43f1 | note | Record of conformity - This ITP Signed, BE ITC
8b01f211-8867-524f-aefa-497410184164 | note | WP
3f3ac091-ab9d-5654-9f74-4e97200c7ff8 | note | Responsibility - Project / Site Engineer, Principal’s Representative
013c5497-ac8f-534a-a4ca-56a3321c20ee | date | Date Completed:
2ca43b19-10cf-48a3-9338-20495e33e8c0 | checkpoint | 2.4 - Wall & Partition Framing
5dd59736-20de-51a0-bff1-a0721bfbab49 | note | Frequency - Each Lot
030c7fad-306d-59de-b3de-4860f0f64dee | note | Acceptance Criteria - WITNESS POINT
b401a721-f530-5e46-9ab3-c141662e13a5 | note | ○ Installation of Light Steel Framing to the project drawings and as per manufacturers specification.
fa873e97-f3ad-5127-b9cd-f91033bbe781 | note | — Max Stud Spacing of 600 mm
2599023f-6bbf-55a1-9fe0-9dad2605e120 | note | — Damp Proof Course as required
ec43df72-a124-561d-8113-5b043b9c840a | note | ○ Give notice for inspection of the following
9c570ad4-8b38-54b2-bc1c-aef2a879732d | note | — Set out prior to construction
024ae0b8-c538-50d0-b435-b6e176ee5d3a | note | — Wall & Partition framing prior to plastering/lining
c1e1a46d-cfad-5608-b863-b8f2dd93bba7 | note | — Framed & lines partitions ready to receive framed and glazed components
bf9b863c-5cb2-5399-b08f-0d43d807e73f | note | — Completion of installation Certification required confirming that the erected frame conforms to the documented project requirements.
3015fcc7-bd74-5297-bedd-f4c7f0f7da0a | note | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0342
f4049c9d-c8ae-54e9-b4d2-a4269759aa85 | note | Inspection/Test Method - Visual Inspection
000385d8-12e5-5d4f-b8a4-9eb21bb96f10 | note | Record of conformity - This ITP Signed, BE ITC, Compliance Certificate
89659934-fd18-5fcb-8c67-79d9d35ef8a2 | note | WP
949b0c29-dbfe-585c-a65a-0ef54c9c21fc | note | Responsibility - Project / Site Engineer, Principal’s Representative
c088c7bd-e03e-5974-b3fd-4c0b5050e6e2 | date | Date Completed:
2332eea7-73f3-40b0-9f6b-65345f2320ab | checkpoint | 2.5 - Fireproofing – Fyrchek Panels / Ceilings
8ba034e0-8f90-56b4-acd0-046722b867fa | note | Frequency - Each Lot
bfe80276-41a5-591c-b557-ed327d60a175 | note | Acceptance Criteria - WITNESS POINT
d162ab32-5a59-5c20-86a9-34e3098815d5 | note | ○ Ensure the following during installation:
6867a8f7-6391-55a8-a508-4eac45068f8a | note | — Butt joints flat with no visible gaps
7c5fe17b-c156-554b-964e-92385444bed5 | note | — Junction with floors and ceilings straight and true, and allow for a 10mm fire caulking gap
e50d767f-954c-5e01-9b56-775cd5ac03ba | note | ○ Expansion joints, taped joints and setting per spec and manufacturers requirements
f5b3597a-5999-5fca-a659-a147c16733a6 | note | ○ Give notice for inspections of the following:
87195833-9a36-56dc-a770-fb1fd6b28d75 | note | — Control/construction joints completed and ready for fire- stopping
1fc8bccc-30ce-56ff-921e-f6a2ae3075ba | note | ○ Finished Fire Stopping prior to concealment
79cd0acf-fd1f-5c16-ae28-54617f5497e4 | note | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0511, 0182, Gyprock – The Red Book
c1a3b7b7-b806-5f58-b6a3-4c59f0ea0e64 | note | Inspection/Test Method - Visual Inspection
4760cf3d-5ed5-5c09-907c-b8f91c1b52bc | note | Record of conformity - This ITP Signed, BE ITP, Fireproofing Certificate
b12a4213-678f-5a90-9936-91fd940393ac | note | HP*
8b8dedbb-9d0f-5815-8ff3-296d9881be26 | note | Responsibility - Project / Site Engineer, Principal’s Representative
35d57e4c-f365-5752-8268-cf8e90da5592 | date | Date Completed:
46da049b-e7de-47a9-a3b5-436c6d288baf | checkpoint | 2.6 - Suspended Ceiling
fb7a6e06-5d80-5679-9a60-e62cc4e2066e | note | Frequency - Each Lot
d1bf00df-45bd-5481-96a7-1292069c924f | note | Acceptance Criteria - WITNESS POINT
bde953e0-bc1b-5856-9203-e9f37021f41d | note | ○ Installation of the suspended wall system as per manufacturers specifications and to the project drawings.
4221a44f-6cf8-5361-bfd3-d2836ae3edc1 | note | ○ Ensure ceiling height is correct.
db8e80a3-68ae-5738-a4d7-50905de8adb0 | note | ○ Give notice so that inspections can be made of the following:
eb036aa8-2417-553a-8668-4bd12c6319ba | note | — Suspension system before installation of lining
99c4ec30-c68a-536f-8fa0-3ca1c554410b | note | — Ceiling assembly before installing of fittings and site painting
022dfc29-276a-5246-a8d4-301b4f15dbaa | note | — Completed Ceiling
5ae3d02f-8b8b-5de2-a654-ca7f2e0e63f5 | note | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0532
40323f05-4a39-58d7-b071-81562fdbe213 | note | Inspection/Test Method - Visual Inspection
51e49f46-99f8-5400-88e8-3256701e592d | note | Record of conformity - This ITP Signed, BE ITC
fb6bb127-e6db-5b4f-b6dc-8780944c54e1 | note | WP
4c965696-a7e0-5ce2-ac3c-8e5cbdff017b | note | Responsibility - Project / Site Engineer, Principal’s Representative
d5f8bd3e-fe89-5b8d-a2ce-0f56132d4fba | date | Date Completed:
fa88e38c-0cb5-40dd-8192-dd11a90e0aab | checkpoint | 2.7 - Insulation
8a64bbe0-2986-52d5-b92a-02fc96b3de89 | note | Frequency - Each Lot
5a63f0ee-69b4-5837-86d5-99d907d4622f | note | Acceptance Criteria - Install all wall insulation prior to plastering/wall lining.
1d68cd92-3e62-5459-9a08-1212e02d5783 | note | ○ Ensure adequately placed and secured.
861ad847-538f-58fe-bb26-349d2561b618 | note | Reference Documents - Drawing set 030
1d84f2e8-d3e8-5324-b488-573123ccb7d6 | note | Inspection/Test Method - Visual Inspection
66663c20-0c40-563d-9420-54e912ec3519 | note | Record of conformity - This ITP Signed
ad2fe35f-530b-5310-a75b-c4043434053c | note | IP
29862900-7af1-5c63-a848-8f67d30f01ba | note | Responsibility - Project / Site Engineer
86e017f4-dd4b-5459-abb4-8b87ae8ef570 | date | Date Completed:
d1c436a4-ed38-41ad-a76a-5a6fa1dc90d8 | checkpoint | 2.7 - Plastering & lining
f4f4fb07-14cf-52ec-8c55-fd3951c3129b | note | Frequency - Each Lot
b7949853-7f94-50e4-9700-59616442215d | note | Acceptance Criteria - WITNESS POINT
d6975bbf-2d50-5243-be0c-ace31fffed6b | note | ○ Installation of the following as per manufacturers specification:
eab65a65-b1e3-513c-9bea-ac7fe4cbd20d | note | — Wall Plastering to steel frames
41350e4e-cf0f-5c69-9a10-6c793e53d1bf | note | — Ceiling lining to suspended ceiling
ce25e632-d85a-5408-bc0c-ba98509cdb6f | note | ○ Expansion joints, taped joints and setting per spec and manufacturers requirements
473f1e59-7715-59be-a109-83c8b9a040ba | note | ○ Give notice for inspection of finished surface prior to applying sealer or finish coatings or decorative paper
1288633c-a514-5328-9d28-f88b3dde4057 | note | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0511
88d8b61c-00de-5194-95c5-65b32b4201e1 | note | Inspection/Test Method - Visual Inspection
f4226d54-9efa-58d9-8813-757c68250b97 | note | Record of conformity - This ITP Signed, BE ITC
77b1dffc-b5b7-5e6a-887c-741f26f07ca2 | note | WP
dae4ffd6-4a4a-5c3d-bbb8-215ed5fa2b09 | note | Responsibility - Project / Site Engineer Principal’s Representative
ff3f8bbd-ae72-56c7-8b3f-529297bc1e77 | date | Date Completed:
12b1bb25-f6e5-40e5-a8a0-e1d7093cff99 | checkpoint | 2.8 - Fireproofing – Penetrations
8ad26e3c-5acf-5c92-918a-2b5573710f35 | note | Frequency - Each Lot
24d5c6a9-791a-5b5f-8e87-66e1522a45b6 | note | Acceptance Criteria - Ensure the following for all penetrations in fire rated rooms:
ed4d4d3e-1d9c-5b84-a919-e4eac3a44533 | note | — Penetrations are sealed and approved
b4ab348f-df1d-57a2-9628-b8a7a7a24aad | note | — Fire collars are installed as per manufacturer specs
679749c7-55f5-5616-94b3-a23943797fab | note | — Verify door jambs are filled in or packed
06de94fe-38ee-5895-b508-e06ff2df61fd | note | — 500mm run for junction seals
3035db50-2707-56db-8790-983733d84a6c | note | — 500x500mm area for penetration seals
ff87c433-6896-54a5-824e-39c59ba96cd5 | note | ○ Give notice for inspections of the following:
94649d54-299e-5aef-a55c-bf064e03ccfb | note | — Service penetrations completed and ready for fire-stopping
c04bb1df-536d-5541-88c6-95ce512d0932 | note | — Finished Fire Stopping prior to concealment
76498162-b4e3-5b4b-b430-abab02115681 | note | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0182, Gyprock – The Red Book
a5a35bb1-7186-5688-a0a5-d1aa4b1270be | note | Inspection/Test Method - Visual Inspection
a0427760-b4f3-5593-8597-e96585772b5b | note | Record of conformity - This ITP Signed, BE ITP, Fireproofing Certificate
1eee4887-bfbe-5fb4-9e37-66a6374cf688 | note | WP
25174823-996f-545f-8a6c-e5f210bf4547 | note | Responsibility - Project / Site Engineer, Principal’s Representative
fc36bb30-91e0-511a-9238-aa11788a00ea | date | Date Completed:
acfacc70-7712-4209-820e-f8b5c23e6ef1 | checkpoint | 2.9 - Joinery/Fixing
76f0315a-f5ef-5c8f-8665-c79cf8e2648c | note | Frequency - Each Lot
1ea12d32-277f-5dc1-b044-89b280892cc7 | note | Acceptance Criteria - Installation of the following in accordance with project drawings and as per manufacturers specifications:
ee5d3633-aa74-59fa-bc04-0600e5ff1a04 | note | — Skirting
d86bb272-239d-584b-a17a-8b7d617bb0ae | note | — Architraves
ebc22509-81f3-57ef-8f5b-ad6cf5120f3a | note | — Cabinets (if applicable)
ad0bf5ae-324c-50e6-92f9-5e6f08e6fa7f | note | — Door Handles
c470dad7-0c53-567e-ac37-1255d653f429 | note | — Grabrails
ac9324e5-1f20-59f8-9c9f-d5ebdc933f3a | note | — Toilet fixtures such as soap dispensers, toilet roll holder, paper towel dispenser etc
f7fc5b10-e2bd-5a84-ada4-567c699f23eb | note | — Door close speeds set
11bd4ed5-3408-5fc5-abea-aeea687df34e | note | — Kick plates
9f7dcb54-d87a-5375-882d-40f58bff5857 | note | Reference Documents - Drawing set 030
e437e0f8-5b2b-5cf4-ba79-a95477b6dc13 | note | Inspection/Test Method - Visual Inspection
c064cb27-4ad7-5920-8f39-fefe89b8c0b0 | note | Record of conformity - This ITP Signed, BE ITC
e5c20a80-d8f5-5a4b-83a6-97c9aebfd394 | note | IP
af725d5e-c43d-5e8a-be21-24c1b45544ef | note | Responsibility - Project / Site Engineer
4071eaf7-d842-5bc7-905e-4d668232589e | date | Date Completed:
8f6e8e9b-bb1c-4705-809b-629a98743cda | section | 3.0 - Finishes
9c727057-4a3b-422d-9598-0f0662707cc6 | checkpoint | 3.1 - Painting
ff57b7a2-d770-51bd-a1d9-e919f85acc73 | note | Frequency - Each Lot
f18e087e-b4b7-53bb-bfd8-0113f6a8eaed | note | Acceptance Criteria - WITNESS POINT
1256dd3e-686a-512e-abdd-b259bc7cf236 | note | ○ Painting off required components as per specified colour & paint.
1af8fb98-48b3-5cce-9271-a508993cca8f | note | ○ New unpainted interior surfaces: To AS/NZS 2311 (2017) Table 5.1.
12dc8a22-16da-55ef-b349-9a42127afe4b | note | ○ New unpainted exterior surfaces: To AS/NZS 2311 (2017) Table 5.2
d287fad4-1405-5c40-a92d-2f42853e8c23 | note | ○ Give notice for inspection of: Opaque finishing stages:
deb37eb1-cf43-5bf8-83ec-7be0c271ddcd | note | — Completion of surface preparation.
464878ba-c49c-5ff5-b3f1-90bcfbda49ca | note | — After application of final coat. Clear finishing stages:
8b6db6ab-287f-5c46-9413-9767dfdb3883 | note | — Before surface preparation of timber.
40db2cfb-8d37-544a-92d5-639350f9dc0e | note | — Completion of surface preparation.
783eb65c-e018-595f-8b0f-7954bea2bec6 | note | — After application of final coat.
802fabd9-b5cd-557d-9f24-1601fc9715d3 | note | Reference Documents - Drawing set 030, ZULU- BECA-001- SPC-00005, 0671p
f5265081-2fbe-5ff2-8394-accf12da1d76 | note | Inspection/Test Method - Visual Inspection
dac316f4-de06-556d-a5f9-caabdcc06c54 | note | Record of conformity - This ITP Signed, BE ITC
6ceab4b7-3485-5a47-9aca-20c85e7e9e7b | note | WP
e96c24af-987a-5bd5-90a6-cd074c0643d9 | note | Responsibility - Project / Site Engineer, Principal’s Representative
025ffbe0-938a-5df4-914f-ba06f455c989 | date | Date Completed:
| checkpoint | 3.2 - Waterproofing
| note | Frequency - Each Lot
| note | Acceptance Criteria - WITNESS POINT
| note | ○ Installation of approved Waterproof Membrane in strict accordance with manufacturer’s instructions and to the extents covered in Aconex BecaCPL-GCOR-002069.
| note | ○ Give notice for inspection of:
| note | — Substrates prepared and ready prior to waterproofing
| note | — Secondary Layers prepared and ready for subsequent layers
| note | — Membranes after installation and before concealment"
| note | Reference Documents - ZULU BECA-001-SPC-00005621
| note | Inspection/Test Method - Visual Inspection
| note | Record of conformity - This ITP Signed, BE ITC
| note | WP
| note | Responsibility - Project / Site Engineer, Principal’s Representative
| date | Date Completed:
d53ac908-b940-432a-8c25-be91fd82c24a | checkpoint | 3.3 - Flooring
8341d306-ea94-5a23-ba03-b423a07f4df1 | note | Frequency - Each Lot
903bfe94-a435-53db-aa58-786149c19d54 | note | Acceptance Criteria - WITNESS POINT
edb9d75d-079e-53fb-b0f0-ced2cc1b9155 | note | ○ Ensure all flooring surface is level and falls to drains have the required grades prior to installation of flooring.
aa4df830-8542-5648-8585-7c1a1547e5d0 | note | ○ Installation of the following strictly according to manufacturer’s specifications and project drawings:
6f6a0541-785f-5e81-8d7e-f4fd8a48a465 | note | — Vinyl Flooring
3a7a9c4f-febe-58a2-a852-5e09a975a0de | note | — Resin Based Flooring Give inspection for the following: Resin based Flooring
32d8f9be-3f6d-5e57-88ed-e3a3e3e6be95 | note | — Completion of substrate preparation
eda86625-9e57-5059-8d71-798855201ae9 | note | — Substrate joints, thresholds and perimeter walls
f27647df-7d95-5188-ae3d-3913d0a89494 | note | — Completed priming of base.
c05ee0d7-aa3e-549a-bb7d-57cfc2cdd9fe | note | — Completion of each coat in the flooring system
17f2a431-d740-57a0-9c2b-696d40a4a2e6 | note | — Completed application Resilient Flooring
fe27741a-01c9-5f36-a009-51d4cf3058b5 | note | — Substrate immediately before fixing resilient finishes or underlay
63d1ce23-2dd0-5b4a-b7c7-47a8c3807d7d | note | — Trial set outs before execution
69ceeab9-25c8-5615-a642-7494c27860e0 | note | — Completed underlay, if any
8f1b7e31-0898-5ca9-aa40-e6248868f882 | note | — Finished surface before applying sealers or polishes, if any
b355c41a-867c-5f40-aac0-95cd6cdeae1b | note | — Completed installation
e6b1f353-3681-5f15-9d14-750d1b34b3e9 | note | Reference Documents - Drawing set 030, Materials Schedule, ZULU- BECA-001- SPC-00005, 0657, 0651
bf733fe2-5d3c-545e-8e3c-13c80d83ccbd | note | Inspection/Test Method - Visual Inspection
153e7d96-2831-5ca1-b18d-0a5c49038282 | note | Record of conformity - This ITP Signed, BE ITC
dfde5c55-f809-5bb2-9ca0-6a27ed1fb467 | note | WP
eac95cb2-adef-56af-96e7-a958f2562bb7 | note | Responsibility - Project / Site Engineer / Principal’s Representative
cbe3ea68-e642-5671-ac9f-cc595a011817 | date | Date Completed:
9f863566-56bf-407f-aa61-81c02cef68dc | checkpoint | 3.4 - Furniture
2e6fd97c-c2d9-57e2-bd95-c04c01766f5a | note | Frequency - Each Lot
603e00ef-70d4-507f-9ab9-2c7126445eae | note | Acceptance Criteria - Delivery and installation of approved furniture.
c2bd93ba-300a-5ddb-a9b1-547b8a8c52df | note | ○ Installed on site as per manufacturers specifications.
54220b00-f621-55b8-b409-c62df598a32e | note | Reference Documents - Drawing Set 030, Aconex DCWC Mgt-GCOR- 010265
c805e58a-b6e8-5f42-8daf-905ec8e6a178 | note | Inspection/Test Method - Visual Inspection
9c9c1fd8-b969-50c0-977b-b17220be318a | note | Record of conformity - This ITP Signed
425fedee-f0f8-5a31-832d-7802fd1930a7 | note | IP
86efff61-d79c-54d6-81fd-d4dffc8af56b | note | Responsibility - Project / Site Engineer
ce89112c-e2d1-5e47-ad92-ea08f0f42bfb | date | Date Completed:
746caf49-7e44-41ef-9964-c1364b207916 | checkpoint | 3.5 - Mirror
7d4f69f3-6ea7-5e7b-8cf3-92e914eea197 | note | Frequency - Each Lot
16b7d95b-99c6-5f7f-a718-08cc484b45ff | note | Acceptance Criteria - Installation of bathroom mirror as per drawings and manufacturer specification.
c8f7e3d3-5c1e-5a89-a8ea-64b5e93e03d9 | note | ○ Correct adhesive used and allowed to cure for minimum period whilst mirror is supported.
6a9c70e9-f4c4-5383-962a-b007f677c50f | note | Reference Documents - Drawing Set 030
bf1af911-5421-5e17-8683-143ed6f2a447 | note | Inspection/Test Method - Visual Inspection
1e9fe04f-88b0-5113-a3f9-deb01c5aaa4b | note | Record of conformity - This ITP Signed
50ab70be-6da4-5705-aa68-f3ca30e8ea72 | note | IP
cc8c337b-826a-528b-b612-fb01b96c6838 | note | Responsibility - Project / Site Engineer
7e9d58a3-0660-5279-bb67-bbadcf000ee2 | date | Date Completed:
3a3e68b2-81d2-4f14-a90f-ebf21b0ccaea | checkpoint | 3.6 - Eye Wash Station
57683cb1-6962-500a-beca-e0190f748687 | note | Frequency - Each Lot
fb84a581-ea5c-591c-b6a9-ea6a4149c51f | note | Acceptance Criteria - Installation of eye wash station as per drawings and manufacturer specification.
690e2236-da3e-5a8b-bd2e-4585c3fd2291 | note | Reference Documents - Drawing Set 030
716f1db8-7969-5185-a916-2fdd0dd1555f | note | Inspection/Test Method - Visual Inspection
2fa434cf-6497-5012-85ad-98b388b4c462 | note | Record of conformity - This ITP Signed
2de2f90c-c4af-5dc5-9ef5-cacce91868da | note | IP
80ad295e-8d25-52cd-9124-451bcda1b524 | note | Responsibility - Project / Site Engineer
da94c9e5-eee1-5f92-b06c-eb903ea95d13 | date | Date Completed:
b953c6f8-9008-4e34-a9b7-b356f7dfb3ce | checkpoint | 3.7 - Installation of Small Kitchenette
ce6327fb-ae34-5802-b817-ea5d690a01a0 | note | Frequency - Each Lot
f1e14dc3-9f97-52db-bf6f-37c3ced7523c | note | Acceptance Criteria - Installation of kitchenette as per drawings and manufacturer specification.
7baf584a-e473-533a-a4ce-b153a7bee292 | note | Reference Documents - Drawing Set 030
c5baf04f-1b9b-5d23-a458-76b41195798a | note | Inspection/Test Method - Visual Inspection
98cb1448-97ad-5041-aebd-5ac387aaaf6b | note | Record of conformity - This ITP Signed
88b70d1d-0856-5a87-a6a9-5a20ef9ffad4 | note | IP
a69f6e7f-fb7b-5224-bf54-f87021ce227c | note | Responsibility - Project / Site Engineer
be66b174-4e54-5e9b-b87d-b4b63c3cf58e | date | Date Completed:
52988a2a-61e3-4a91-854d-af9f80af16e1 | checkpoint | Final Inspection
dc788842-12ad-5863-b0b7-f62ae79cdb1e | note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality \System Procedures and verifies lot compliance with specifications.
64a572f6-a790-52d7-a971-05031dbc11d8 | textbox | Print Name:
209881a4-96eb-588b-b59f-07d4ec6944b9 | textbox | Position:
681870ea-d672-5751-9de7-d2bf7fc59cf2 | date | Work Completed On:
c2d66707-357b-516e-b580-15db4d39f0d5 | date | Date: