## ChecklistsITCs
Delete rows that aren't applicable to the project, then create the project breakdown and send to CONQA
type | name | values | prefix | postfix
checklist | Site Establishment and Safety Checklist | Pass, Fail
checkpoint | Delivery and goods lift location
checkpoint | Delivery requirements i.e. booking process
checkpoint | On site storage / office location
checkpoint | Site specific restrictions i.e. noise / starting times
checklist | Ductwork Checklist | Pass, Fail
checkpoint | Rectangular duct installed as per latest drawing | Yes, No
checkpoint | Duct flanges firmly bolted and sealed where required | Yes, No
checkpoint | Cleats installed as required | Yes, No
checkpoint | Correct hanger spacing / supports installed | Yes, No
checkpoint | DW insulated where required and damage free | Yes, No
checkpoint | Ductwork restrained for wind/seismic where required | Yes, No, N/A
checkpoint | Any required ductwork leakage testing | Pass, Fail
checkpoint | Spiral installed as per latest drawing | Yes, No
checkpoint | Spiral joins sealed correctly | Yes, No
checkpoint | Correct hanger spacing / supports installed for spiral | Yes, No
checkpoint | Spiral insulated where required and damage free | Yes, No, N/A
checkpoint | Additional taping/sealing to medium/high pressure spiral | Yes, No, N/A
checkpoint | Pops & flex installed as per latest drawing | Yes, No
checkpoint | Correct hanger spacing / supports installed for flex | Yes, No
checkpoint | Free from support off other services | Yes, No
checkpoint | Flexible duct connections completed correctly | Yes, No
checkpoint | Blade dampers installed as documented and left in the open position | Yes, No
checkpoint | BD pop access panel coordinated and marked | Yes, No, N/A
checkpoint | Cushion boxes installed as per latest drawing | Yes, No
checkpoint | Balancing dampers installed as documented and left in the open position | Yes, No, N/A
checkpoint | Location of register coordinted with other services and marked on plan or floor | Yes, No
checkpoint | Volume Control Dampers installed as per latest drawing | Yes, No
checkpoint | Motorised dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Smoke dampers installed as per latest drawing / actuator fit off | Yes, No, N/A
checkpoint | Fire dampers installed as per latest drawing / access panel in DW where required | Yes, No, N/A
checkpoint | Damper access panels coordinated and marked | Yes, No
checkpoint | Photos of ductwork correctly sealed through smoke wall & smoke damper | Yes, No, N/A
checklist | Indoor Equipment | Pass, Fail
checkpoint | Indoor Unit (IDU) correctly supported as per project engineering requirements | Yes, No
checkpoint | Correct IDU installed as per latest drawing | Yes, No
checkpoint | Flexible connections installed and sealed | Yes, No
checkpoint | Access to filter bank / filters installed | Yes, No
checkpoint | Access to all relevant controls and isolators | Yes, No
checkpoint | IDU access panel coordinated and marked | Yes, No
checkpoint | Ventilation fan correctly supported as per project engineering requirements | Yes, No
checkpoint | Correct fan installed as per latest drawing | Yes, No
checkpoint | Fan connections secured and sealed | Yes, No
checkpoint | Access to fan and isolator | Yes, No
checkpoint | Ventilation fan access panel coordinated and marked | Yes, No
checkpoint | Correct VAV installed as per latest drawing | Yes, No, N/A
checkpoint | Access to VAV and controls | Yes, No, N/A
checkpoint | VAV access panel coordinated and marked | Yes, No, N/A
checklist | Grille Fit-Off Checklist | Pass, Fail, N/A
checkpoint | Grilles installed in correct location as per latest duct layout / RCP | Yes, No
checkpoint | Correct grille type installed | Yes, No
checkpoint | Grille installed flush and square | Yes, No
checkpoint | Are all grilles installed correctly? Air leaks, vibration or failure | Yes, No
checkpoint | Grille color as per schedule | Yes, No
checkpoint | Grille left clean of fingerprints and caps installed where required | Yes, No
checkpoint | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below) | Yes, No
checklist | All Subbie Rough-in Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | All Subbie Fit off & Testing Progression Checklist | Complete, Incomplete
checkpoint | All work in zone completed and appear compliant | Yes, No
label | Pass once all work complete
checklist | As Builts Checklist | Complete, Incomplete
button | Update As-Built's of any known changes | Yes, No
checklist | Pipework Checklist | Pass, Fail, N/A
checkpoint | Pipework installed as per latest drawings | Yes, No
checkpoint | Pipework installed level and free of damage | Yes, No
checkpoint | All joins welded / crimped as per manufacturer's instructions | Yes, No
checkpoint | Air bleeds installed in pipework where required | Yes, No
checkpoint | Riser or area branch valve access panel coordinated and marked | Yes, No, N/A
checkpoint | Correct hanger spacing / supports installed for pipe runs | Yes, No
checkpoint | No other services suspended from pipework | Yes, No
checkpoint | Correct coil valves installed as per schedule | Yes, No
checkpoint | Test points, drains and bleeders installed where required | Yes, No
checkpoint | Coil valves accessible and not blocking any service points | Yes, No
checkpoint | Coil valveset access panel coordinated and marked | Yes, No
checkpoint | Correct coil valves installed as per schedule | Yes, No
checkpoint | Test points, drains and bleeders installed where required | Yes, No
checkpoint | Coil valves accessible and not blocking any service points | Yes, No
checkpoint | Coil valveset access panel coordinated and marked | Yes, No
checkpoint | HHW Pressure Test – ITR attached | Pass, Fail, N/A
checkpoint | HHW Flushed - plan, photos of flow readings and water quality attached | Pass, Fail, N/A
checkpoint | Drain trapped where required | Yes, No
checkpoint | Correct hanger spacing / fall | Yes, No
checkpoint | Drain tested | Pass, Fail
checkpoint | Drain pump installed level and tested | Yes, No
checkpoint | Drain terminates at a tundish | Yes, No
checkpoint | Drains, pump and tundish access for maintenance. | Yes, No
checklist | Pipework Testing | Pass, Fail, N/A
checkpoint | Pipe tested and recorded as per Pipe Testing ITP
checkpoint | Initial pipe pressure test (attach photo)
checkpoint | 24hr pipe pressure test (attach photo)
checkpoint | Piping cleaned and flushed
Checklist | Drains | Pass, Fail, N/A
checkpoint | Drain trapped where required
checkpoint | Drain pump installed on a gradient/ level
checkpoint | Drain terminates at a tundish
checkpoint | Drain pipe insulated where required
checkpoint | Drains, pump and tundish access for maintenance
checkpoint | Drain pipe is labelled clearly
checklist | VAV Checklist | Pass, Fail, N/A
checkpoint | Unit installed as per latest drawing
checkpoint | Inspect the unit casing is not damaged. Record and report for any issues
checkpoint | Unit is labelled clearly
checkpoint | Unit correctly supported as per documented
checkpoint | Confirm test points, sensors and pressure points have been provided and installed as documented
checkpoint | Confirm electrical connection to unit
checkpoint | Confirm ductwork connections to the unit are correct
checkpoint | Unit complete with acoustic wrapping as per documented
checkpoint | Adequate maintenance clearance maintained
checkpoint | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail

## TO BUILD - LEVEL 1
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 7
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
PIPEWORK:
Pipework Checklist
Pipework Testing
VAV UNITS:
VAV Checklist
Ductwork Checklist
SITE QA | All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Indoor Equipment

## TO BUILD - LEVEL 9
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 10
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 11
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 12
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 13
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 14
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 32
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
PIPEWORK:
Pipework Checklist
Pipework Testing
VAV UNITS:
VAV Checklist
Ductwork Checklist
SITE QA | All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Indoor Equipment

## TO BUILD - LEVEL 33
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
PIPEWORK:
Pipework Checklist
Pipework Testing
VAV UNITS:
VAV Checklist
Ductwork Checklist
SITE QA | All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Indoor Equipment

## TO BUILD - LEVEL 35
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 36
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 37
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 38
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA
As Builts Checklist

## TO BUILD - LEVEL 39
Project Breakdown | Checklists
PROJECT NAME: CASSELLDEN - BB TENANCY AND AMENITIES UPGRADE
OHS | Site Establishment and Safety Checklist
DUCTWORK:
Ductwork Checklist
Grille Fit-Off Checklist
SITE QA | All Subbie Rough-in Progression Checklist
All Subbie Fit off & Testing Progression Checklist
As Builts Checklist
Indoor Equipment