## Sheet1
1.1 | Check for correct documentation | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | 1.1 - Check for correct documentation | FREQUENCY: Prior to commencing any activity | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | REFERENCE DOCUMENTS: Drawings and drawing registers | INSPECTION/TEST METHOD: Visual inspection | RECORD OF CONFORMITY: This ITP signed off | HP* | RESPONSIBILITY: Project Engineer / Site Foreman | Date Completed: | 1.1 - Check for correct documentation
1.2 | Implementation of all measures and controls | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS CHAR(AMP) ITP | QMP, TMP, JSEA, SWMS, ITP | Visual Inspection | This ITP signed off | HP* | Project Engineer / Site Foreman | 1.2 - Implementation of all measures and controls | FREQUENCY: Prior to commencing any activity | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS CHAR(AMP) ITP | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This ITP signed off | HP* | RESPONSIBILITY: Project Engineer / Site Foreman | Date Completed: | FREQUENCY: Prior to commencing any activity
1.3 | Precast Materials Inspection | Each Delivery | Precast materials have been inspected and fit for purpose and free of defects | 701.04b | Visual Inspection | This ITP signed Receival and Inspection Checklist | IP | Project Engineer | 1.3 - Precast Materials Inspection | FREQUENCY: Each Delivery | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects | REFERENCE DOCUMENTS: 701.04b | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist | IP | RESPONSIBILITY: Project Engineer | Date Completed: | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
1.4 | Precast Pipe Compliance | Prior to Commencing | Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058 Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2. | VicRoads Spec. Cl.619 Cl. 701.04(a) Cl. 701.04(b)(i) Cl. 705.04(d) Cl. 705.11 AS4058 AS4680 | Document review CHAR(AMP) Site inspection | Receival CHAR(AMP) Inspection Checklist Manufacturer cetificate or accreditation | IP | Project Engineer | 1.4 - Precast Pipe Compliance | FREQUENCY: Prior to Commencing | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058 Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619 Cl. 701.04(a) Cl. 701.04(b)(i) Cl. 705.04(d) Cl. 705.11 AS4058 AS4680 | INSPECTION/TEST METHOD: Document review CHAR(AMP) Site inspection | RECORD OF CONFORMITY: Receival CHAR(AMP) Inspection Checklist Manufacturer cetificate or accreditation | IP | RESPONSIBILITY: Project Engineer | Date Completed: | REFERENCE DOCUMENTS: Drawings and drawing registers
1.5 | Bedding material classification | Prior to start | Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 19mm sieve. 5%-40% passing 0.075mm. PI = 20 max. | 701.04e Table 701.041 Table 701.042 Table 701.231 | Verify | Test Reports from supplier | TP | Project Engineer | 1.5 - Bedding material classification | FREQUENCY: Prior to start | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 19mm sieve. 5%-40% passing 0.075mm. PI = 20 max. | REFERENCE DOCUMENTS: 701.04e Table 701.041 Table 701.042 Table 701.231 | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Test Reports from supplier | TP | RESPONSIBILITY: Project Engineer | Date Completed: | INSPECTION/TEST METHOD: Visual inspection
1.6 | Backfill material Classification | Prior to start | Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 37.5mm sieve. 5%-40% passing 0.075mm sieve. PI = 20 max. | 701.04e Table 701.041 Table 701.042 Table 701.231 | Verify | Test Reports from supplier | TP | Project Engineer | 1.6 - Backfill material Classification | FREQUENCY: Prior to start | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 37.5mm sieve. 5%-40% passing 0.075mm sieve. PI = 20 max. | REFERENCE DOCUMENTS: 701.04e Table 701.041 Table 701.042 Table 701.231 | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Test Reports from supplier | TP | RESPONSIBILITY: Project Engineer | Date Completed: | RECORD OF CONFORMITY: This ITP signed off
1.7 | Mortar material classification | Prior to start | Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa | 610.33 | Verify | Test Reports from supplier | TP | Project Engineer | 1.7 - Mortar material classification | FREQUENCY: Prior to start | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa | REFERENCE DOCUMENTS: 610.33 | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Test Reports from supplier | TP | RESPONSIBILITY: Project Engineer | Date Completed: | HP*
2.1 | Excavation Permit | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | ITP Signed | HP* | Project Engineer | 2.1 - Excavation Permit | FREQUENCY: Each lot | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | REFERENCE DOCUMENTS: Excavation permit | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: ITP Signed | HP* | RESPONSIBILITY: Project Engineer | Date Completed: | RESPONSIBILITY: Project Engineer / Site Foreman
2.2 | Set out drainage | Prior to excavation | The position of all drainage lines are to be confirmed with the superintendent | Drawings 701.10 | Visual Inspection | ITP Signed | HP | Engineer / Forman CHAR(AMP) Superintendent | 2.2 - Set out drainage | FREQUENCY: Prior to excavation | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent | REFERENCE DOCUMENTS: Drawings 701.10 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | HP | RESPONSIBILITY: Engineer / Forman CHAR(AMP) Superintendent | Date Completed: | Date Completed:
2.3 | Excavation (pipes) | Each Trench | Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical Depth of trench: • > 100mm below underside of pipe (for pipe width CHAR(LESS) 1500 mm) • > 200mm below underside of pipe (for pipe width > 1500 mm) | 701.15 Table 701.151 | Visual Inspection | ITP Signed | IP | Site Foreman | 2.3 - Excavation (pipes) | FREQUENCY: Each Trench | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical Depth of trench: • > 100mm below underside of pipe (for pipe width CHAR(LESS) 1500 mm) • > 200mm below underside of pipe (for pipe width > 1500 mm) | REFERENCE DOCUMENTS: 701.15 Table 701.151 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Site Foreman | Date Completed: | 1.2 - Implementation of all measures and controls
2.4 | Compact base of trench | Each Trench | Compacted to refusal using mechanical plant. | 701.1 | Visual Inspection | ITP Signed | IP | Project Engineer | 2.4 - Compact base of trench | FREQUENCY: Each Trench | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant. | REFERENCE DOCUMENTS: 701.1 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Project Engineer | Date Completed: | FREQUENCY: Prior to commencing any activity
2.5 | Place bedding material CHAR(AMP) compact | Each Trench | Bedding material shall be compactied to no less than the below thickness: - 100mm under pipes. - 80mm (earth foundation) - 150mm (rock foundation) | 701.19 | Visual Inspection | ITP Signed | IP | Project Engineer | 2.5 - Place bedding material CHAR(AMP) compact | FREQUENCY: Each Trench | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness: - 100mm under pipes. - 80mm (earth foundation) - 150mm (rock foundation) | REFERENCE DOCUMENTS: 701.19 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Project Engineer | Date Completed: | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS CHAR(AMP) ITP
2.6 | Place pipes | Each Line/Pit | Pipes CHAR(AMP) pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied | Drawings 701.17 | Visual Inspection | ITP Signed | IP | Project Engineer / Site Foreman | 2.6 - Place pipes | FREQUENCY: Each Line/Pit | ACCEPTANCE CRITERIA: Pipes CHAR(AMP) pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied | REFERENCE DOCUMENTS: Drawings 701.17 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Project Engineer / Site Foreman | Date Completed: | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
2.7 | Jointing pipe sections | Each Line | Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled | 701.18 | Visual Inspection | ITP Signed | IP | Project Engineer / Site Foreman | 2.7 - Jointing pipe sections | FREQUENCY: Each Line | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled | REFERENCE DOCUMENTS: 701.18 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Project Engineer / Site Foreman | Date Completed: | INSPECTION/TEST METHOD: Visual Inspection
2.8 | Place CHAR(AMP) compact backfill material over pipes | each lot | Backfill under paved area: fill trench with selected back fill material to subgrade level Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level Loose layer thickness CHAR(LESS)= 150mm. 1 lot = 150mm layer | 701.14 701.15 | Visual Inspection | ITP Signed | IP | Site Engineer / Site Foreman | 2.8 - Place CHAR(AMP) compact backfill material over pipes | FREQUENCY: each lot | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level Loose layer thickness CHAR(LESS)= 150mm. 1 lot = 150mm layer | REFERENCE DOCUMENTS: 701.14 701.15 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Site Engineer / Site Foreman | Date Completed: | RECORD OF CONFORMITY: This ITP signed off
2.9 | Repairs to damaged pipes | Each damaged pipe | No repairs shall be undertaken without the superintendents approval of the repair materials and procedures All repair procedures undertaken in accordance with Cl 701.25 | 701.31 | Verify | ITP Signed | HP | Engineer / Forman CHAR(AMP) Superintendent | 2.9 - Repairs to damaged pipes | FREQUENCY: Each damaged pipe | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures All repair procedures undertaken in accordance with Cl 701.25 | REFERENCE DOCUMENTS: 701.31 | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: ITP Signed | HP | RESPONSIBILITY: Engineer / Forman CHAR(AMP) Superintendent | Date Completed: | HP*
3.1 | Compaction and moisture content of backfill CHAR(AMP) bedding material | as required/requested | Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal. | 701.2 | Verify | Test Reports | TP | Project Engineer | 3.1 - Compaction and moisture content of backfill CHAR(AMP) bedding material | FREQUENCY: as required/requested | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal. | REFERENCE DOCUMENTS: 701.2 | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Test Reports | TP | RESPONSIBILITY: Project Engineer | Date Completed: | RESPONSIBILITY: Project Engineer / Site Foreman
Date Completed:
1.3 - Precast Materials Inspection
FREQUENCY: Each Delivery
ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
REFERENCE DOCUMENTS: 701.04b
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
IP
RESPONSIBILITY: Project Engineer
Date Completed:
1.4 - Precast Pipe Compliance
FREQUENCY: Prior to Commencing
ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058 Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.619 Cl. 701.04(a) Cl. 701.04(b)(i) Cl. 705.04(d) Cl. 705.11 AS4058 AS4680
INSPECTION/TEST METHOD: Document review CHAR(AMP) Site inspection
RECORD OF CONFORMITY: Receival CHAR(AMP) Inspection Checklist Manufacturer cetificate or accreditation
IP
RESPONSIBILITY: Project Engineer
Date Completed:
1.5 - Bedding material classification
FREQUENCY: Prior to start
ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 19mm sieve. 5%-40% passing 0.075mm. PI = 20 max.
REFERENCE DOCUMENTS: 701.04e Table 701.041 Table 701.042 Table 701.231
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Test Reports from supplier
TP
RESPONSIBILITY: Project Engineer
Date Completed:
1.6 - Backfill material Classification
FREQUENCY: Prior to start
ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below: 100% passing 37.5mm sieve. 5%-40% passing 0.075mm sieve. PI = 20 max.
REFERENCE DOCUMENTS: 701.04e Table 701.041 Table 701.042 Table 701.231
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Test Reports from supplier
TP
RESPONSIBILITY: Project Engineer
Date Completed:
1.7 - Mortar material classification
FREQUENCY: Prior to start
ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
REFERENCE DOCUMENTS: 610.33
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Test Reports from supplier
TP
RESPONSIBILITY: Project Engineer
Date Completed:
2.1 - Excavation Permit
FREQUENCY: Each lot
ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
REFERENCE DOCUMENTS: Excavation permit
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: ITP Signed
HP*
RESPONSIBILITY: Project Engineer
Date Completed:
2.2 - Set out drainage
FREQUENCY: Prior to excavation
ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
REFERENCE DOCUMENTS: Drawings 701.10
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
HP
RESPONSIBILITY: Engineer / Forman CHAR(AMP) Superintendent
Date Completed:
2.3 - Excavation (pipes)
FREQUENCY: Each Trench
ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts. Trench walls to be vertical where practical Depth of trench: • > 100mm below underside of pipe (for pipe width CHAR(LESS) 1500 mm) • > 200mm below underside of pipe (for pipe width > 1500 mm)
REFERENCE DOCUMENTS: 701.15 Table 701.151
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Site Foreman
Date Completed:
2.4 - Compact base of trench
FREQUENCY: Each Trench
ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
REFERENCE DOCUMENTS: 701.1
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Project Engineer
Date Completed:
2.5 - Place bedding material CHAR(AMP) compact
FREQUENCY: Each Trench
ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness: - 100mm under pipes. - 80mm (earth foundation) - 150mm (rock foundation)
REFERENCE DOCUMENTS: 701.19
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Project Engineer
Date Completed:
2.6 - Place pipes
FREQUENCY: Each Line/Pit
ACCEPTANCE CRITERIA: Pipes CHAR(AMP) pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
REFERENCE DOCUMENTS: Drawings 701.17
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Project Engineer / Site Foreman
Date Completed:
2.7 - Jointing pipe sections
FREQUENCY: Each Line
ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
REFERENCE DOCUMENTS: 701.18
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Project Engineer / Site Foreman
Date Completed:
2.8 - Place CHAR(AMP) compact backfill material over pipes
FREQUENCY: each lot
ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level Loose layer thickness CHAR(LESS)= 150mm. 1 lot = 150mm layer
REFERENCE DOCUMENTS: 701.14 701.15
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Site Engineer / Site Foreman
Date Completed:
2.9 - Repairs to damaged pipes
FREQUENCY: Each damaged pipe
ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures All repair procedures undertaken in accordance with Cl 701.25
REFERENCE DOCUMENTS: 701.31
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: ITP Signed
HP
RESPONSIBILITY: Engineer / Forman CHAR(AMP) Superintendent
Date Completed:
3.1 - Compaction and moisture content of backfill CHAR(AMP) bedding material
FREQUENCY: as required/requested
ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort. Bedding material shall be compacted using a compaction plated to refusal.
REFERENCE DOCUMENTS: 701.2
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Test Reports
TP
RESPONSIBILITY: Project Engineer
Date Completed: