## Thin Asphalt
|  | Insert Contractors Logo |  |  | Contractor = Contractors nominated representative Principals Rep = Principals Representative Quality Manager = Contactors Quality Manager
CONTRACTOR DOWNER |  |  | LOCATION | Identify Site
THIN ASPHALT CONSTRUCTION INSPECTION AND TEST PLAN |  |  | Prepared by Contract Manager | Signature Nik Basarge | H = Hold Point = Principal inspection/review and approval of work before next activity can take place
|  |  | Reviewed by Design Manager/Asset Manager | Signature_______________________________________ | W = Witness Point = Principal invited to inspect, next Activity can take place should Principal not attend
Complete DAILY with all relevant QA records for that day attached |  |  | Approved by Quality Manager | Signature _________________________________________ | DR = Document or Record review, prior works activity or post activity to verify compliance
No. | Inspection & Test Activity | Applicable Standard & Acceptance Criteria | Frequency | Criteria Notes | Inspect / Approve / Initial Sign Off |  | Records & Remarks
[5 empty] | Contractor | Principals Rep | Update as required/confirm document
1.0 Pre-Commencement Activities (Design suitability)
1.1 | Treatment Design confirmed |  | Pre site works | Treatment Design approved by Principal | H |  | Principal approval signature on Design document
1.2 | Renewal Quality Plan |  | Pre site works | RQP approved by Principal | H |  | Principal approval signature on RQP
1.3 | Asphalt JMF confirmed | NZTA M10, M27 & P11 Mix design report submitted to NZTA | Pre site works | Design meets specification requirements and is approved by Principal |  | H | Contractor's asphalt designer has signed JMF report
1.4 | Underground and surface utilities identified and accounted for in design |  | Pre site works | Existing utility owners contacted and acknowledgement of proposed works. Service lid condition and levels confirmed suitable for proposed works. |  | W | Included in Asphalt Design Report
1.5 | Traffic Management | TMP checked and approved Plans approved Current EED (if applicable) | Before traffic management set up | Hold point - No traffic management is to be set up until TMP has been checked and approved | H |  | Includer approved TMP
1.6 | Notification of intention to start work | Letter drop to local residents. Greater consultation where required | Before work commences | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | H |  | letter drops
1.7 | Pavement Marking Records | Measure existing markings to aid reinstatement | Measure existing markings to aid reinstatement | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | H |  | Site Measure or Video Viewer
| HP – Asphalt design verified for site commencement |  |  | Contractor checklist copied to Principal |  | W | Pre-commencement checklist signed and filed
2.0 Material - Source Properties Compliance
2.1 | Binder content | NZTA M10, M27 and P11 IANZ accredited test cert | 1 per 200t at asphalt plant | Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 |  | W | Test report reviewed for compliance , filed and copy sent to Principal
2.2 | Particle Size Distribution | NZTA M10, M27 and P11 IANZ accredited test cert | 1 per 200t at asphalt plant | Refer to Table 5.3 |  | W | Test report reviewed for compliance , filed and copy sent to Principal
2.3 | Max. Specific Gravity (MSG) of mix | IANZ accredited test cert | 1 per 600t at asphalt plant | Report |  | W | Test report reviewed for compliance , filed and copy sent to Principal
2.4 | Air Voids at lab design compaction | NZTA M10, M27 and P11 IANZ accredited test cert | 1 per 600t at asphalt plant | Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 |  | W | Test report reviewed for compliance , filed and copy sent to Principal
| HP – Material compliance confirmed (binder, & production properties) |  |  | Material compliance checklist copied to Principal |  | W | Asphalt material compliance checklist signed & filed
3.0 Asphalt construction
3.1 | Pre-AC Construction Site Checklist (week prior) |  | Prior to AC Construction on each site | No change from design report |  |  | Record any issues noted
3.2 | Go/No Go Checklist (within 24 hours) |  | Prior to AC Construction on each site | Weather, readiness of materials and plant, air temperature, pavement temperature, surface compliance post milling, saturation, chipseal tack coat et al | H | W | Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
3.3 | Milling Insitu pavement | String to determine specified depth achieved |  | Specified AC depth achievable, area covered, lane and shoulder width | DR | W | Site records
3.4 | Over Milling | Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill. | Prior to pre-level | On site measurements & photos | DR |  | Site records
3.5 | Pre-Level | Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents | Prior to surfacing | On site measurements & photos | DR |  | Site records
3.6 | Paving Method | Paving plan to be completed prior to establish on site. | Prior to surfacing | Paving Plan should be showing total paving runs with paving run width. | DR |  | Site records
3.7 | Tack / Chipseal | NZTA M10, M27, P11 | Each application pre paving | Design report requirements met. Provide the specific tack coat chipseal and residual binder | DR | W | Site records
3.8 | Asphalt temperature | NZTA M10, M27, P11 | Every load on entry to site and again during compaction | Reference QMP for set temperatures | DR | W | Site records
3.9 | Thickness Monitoring | Confirm Pavement height will allow thickness required to be achieved. | Every 10 - 15 metres | Dipping on paver runs | DR | W | Site records
3.1 | Construction trial where specified | NZTA M10, M27, P11 |  | Include a minimum trial area, width of the paver and width of the roller. Include joints, offsets and overlap areas. |  | W | Trial records reviewed & filed
3.11 | Compaction TAC | NZTA M10, M27, P11 | Minimum Requirements For TAC 1 Test per 300m² with 1 Core per 600m² on Mat , 1 Test per 100m Length with 1 core per 100m length on Joint. | As per NZTA M10 Specification | DR |  | Site / Lab records
3.12 | Compaction SAC | NZTA M10, M27, P12 | As per NZTA M10 Specification | As per NZTA M10 Specification | DR |  | Site / Lab records
3.13 | Post compaction testing | Shape - NZTA M10 and M27 section 9.8 and P11. Levels - NZTA M10 and M27 section 10.2 and P11 | Post AC Construction on each site | Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 < +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. |  | W | Site records
4.0 Post-construction
4.1 | Construction Test Results - Cores | NZTA M10, M27 section 9.7 and P11 | Average of 4 measurements per core | Average Thickness > Specified Depth (Nominal) | DR
4.2 | Construction Test Results - Insitu density and air voids | NZTA M10 and M27 section 9.9 and P11 IANZ accredited test cert. |  | Insitu density and air voids as specified | DR
4.3 | QA Handover | NZTA M10, M27 or P11 as appropriate and contract drawings | For each site on the project | Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. |  | W | Evidence provided demonstrating full compliance with specified design
4.4 | RAMM update | RAMM updates completed |  | Review of RAMM update and confirmation |  | W | Site records of RAMM update to be reviewed and confirmed
Quality Record Close Out:
|  | Digital Signature |  | Quality Manager Name |  | Date