## Sheet1
1.1 | Treatment Design confirmed |  | Pre site works | Treatment Design approved by Principal | H |  | Principal approval signature on Design document | 1.1 - Treatment Design confirmed | Applicable Standard CHAR(AMP) Acceptance Criteria - | Frequency - Pre site works | Criteria Notes - Treatment Design approved by Principal | Contractor - H | Principals Rep - | Records CHAR(AMP) Remarks - Principal approval signature on Design document | 1.1 - Treatment Design confirmed
1.2 | Renewal Quality Plan |  | Pre site works | RQP approved by Principal | H |  | Principal approval signature on RQP | 1.2 - Renewal Quality Plan | Applicable Standard CHAR(AMP) Acceptance Criteria - | Frequency - Pre site works | Criteria Notes - RQP approved by Principal | Contractor - H | Principals Rep - | Records CHAR(AMP) Remarks - Principal approval signature on RQP | Applicable Standard CHAR(AMP) Acceptance Criteria -
1.3 | Asphalt JMF confirmed | NZTA M10, M27 CHAR(AMP) P11 Mix design report submitted to NZTA | Pre site works | Design meets specification requirements and is approved by Principal |  | H | Contractor's asphalt designer has signed JMF report | 1.3 - Asphalt JMF confirmed | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 CHAR(AMP) P11 Mix design report submitted to NZTA | Frequency - Pre site works | Criteria Notes - Design meets specification requirements and is approved by Principal | Contractor - | Principals Rep - H | Records CHAR(AMP) Remarks - Contractor's asphalt designer has signed JMF report | Frequency - Pre site works
1.4 | Underground and surface utilities identified and accounted for in design |  | Pre site works | Existing utility owners contacted and acknowledgement of proposed works. Service lid condition and levels confirmed suitable for proposed works. |  | W | Included in Asphalt Design Report | 1.4 - Underground and surface utilities identified and accounted for in design | Applicable Standard CHAR(AMP) Acceptance Criteria - | Frequency - Pre site works | Criteria Notes - Existing utility owners contacted and acknowledgement of proposed works. Service lid condition and levels confirmed suitable for proposed works. | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Included in Asphalt Design Report | Criteria Notes - Treatment Design approved by Principal
1.5 | Traffic Management | TMP checked and approved Plans approved Current EED (if applicable) | Before traffic management set up | Hold point - No traffic management is to be set up until TMP has been checked and approved | H |  | Includer approved TMP | 1.5 - Traffic Management | Applicable Standard CHAR(AMP) Acceptance Criteria - TMP checked and approved Plans approved Current EED (if applicable) | Frequency - Before traffic management set up | Criteria Notes - Hold point - No traffic management is to be set up until TMP has been checked and approved | Contractor - H | Principals Rep - | Records CHAR(AMP) Remarks - Includer approved TMP | Contractor - H
1.6 | Notification of intention to start work | Letter drop to local residents. Greater consultation where required | Before work commences | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | H |  | letter drops | 1.6 - Notification of intention to start work | Applicable Standard CHAR(AMP) Acceptance Criteria - Letter drop to local residents. Greater consultation where required | Frequency - Before work commences | Criteria Notes - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | Contractor - H | Principals Rep - | Records CHAR(AMP) Remarks - letter drops | Principals Rep -
1.7 | Pavement Marking Records | Measure existing markings to aid reinstatement | Measure existing markings to aid reinstatement | Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | H |  | Site Measure or Video Viewer | 1.7 - Pavement Marking Records | Applicable Standard CHAR(AMP) Acceptance Criteria - Measure existing markings to aid reinstatement | Frequency - Measure existing markings to aid reinstatement | Criteria Notes - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site. | Contractor - H | Principals Rep - | Records CHAR(AMP) Remarks - Site Measure or Video Viewer | Records CHAR(AMP) Remarks - Principal approval signature on Design document
| HP – Asphalt design verified for site commencement |  |  | Contractor checklist copied to Principal |  | W | Pre-commencement checklist signed and filed | - HP – Asphalt design verified for site commencement | Applicable Standard CHAR(AMP) Acceptance Criteria - | Frequency - | Criteria Notes - Contractor checklist copied to Principal | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Pre-commencement checklist signed and filed | 1.2 - Renewal Quality Plan
2.1 | Binder content | NZTA M10, M27 and P11 IANZ accredited test cert | 1 per 200t at asphalt plant | Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 |  | W | Test report reviewed for compliance , filed and copy sent to Principal | 2.1 - Binder content | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert | Frequency - 1 per 200t at asphalt plant | Criteria Notes - Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3 | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal | Applicable Standard CHAR(AMP) Acceptance Criteria -
2.2 | Particle Size Distribution | NZTA M10, M27 and P11 IANZ accredited test cert | 1 per 200t at asphalt plant | Refer to Table 5.3 |  | W | Test report reviewed for compliance , filed and copy sent to Principal | 2.2 - Particle Size Distribution | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert | Frequency - 1 per 200t at asphalt plant | Criteria Notes - Refer to Table 5.3 | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal | Frequency - Pre site works
2.3 | Max. Specific Gravity (MSG) of mix | IANZ accredited test cert | 1 per 600t at asphalt plant | Report |  | W | Test report reviewed for compliance , filed and copy sent to Principal | 2.3 - Max. Specific Gravity (MSG) of mix | Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert | Frequency - 1 per 600t at asphalt plant | Criteria Notes - Report | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal | Criteria Notes - RQP approved by Principal
2.4 | Air Voids at lab design compaction | NZTA M10, M27 and P11 IANZ accredited test cert | 1 per 600t at asphalt plant | Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 |  | W | Test report reviewed for compliance , filed and copy sent to Principal | 2.4 - Air Voids at lab design compaction | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert | Frequency - 1 per 600t at asphalt plant | Criteria Notes - Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6 | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal | Contractor - H
| HP – Material compliance confirmed (binder, CHAR(AMP) production properties) |  |  | Material compliance checklist copied to Principal |  | W | Asphalt material compliance checklist signed CHAR(AMP) filed | - HP – Material compliance confirmed (binder, CHAR(AMP) production properties) | Applicable Standard CHAR(AMP) Acceptance Criteria - | Frequency - | Criteria Notes - Material compliance checklist copied to Principal | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Asphalt material compliance checklist signed CHAR(AMP) filed | Principals Rep -
3.1 | Pre-AC Construction Site Checklist (week prior) |  | Prior to AC Construction on each site | No change from design report |  |  | Record any issues noted | 3.1 - Pre-AC Construction Site Checklist (week prior) | Applicable Standard CHAR(AMP) Acceptance Criteria - | Frequency - Prior to AC Construction on each site | Criteria Notes - No change from design report | Contractor - | Principals Rep - | Records CHAR(AMP) Remarks - Record any issues noted | Records CHAR(AMP) Remarks - Principal approval signature on RQP
3.2 | Go/No Go Checklist (within 24 hours) |  | Prior to AC Construction on each site | Weather, readiness of materials and plant, air temperature, pavement temperature, surface compliance post milling, saturation, chipseal tack coat et al | H | W | Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager) | 3.2 - Go/No Go Checklist (within 24 hours) | Applicable Standard CHAR(AMP) Acceptance Criteria - | Frequency - Prior to AC Construction on each site | Criteria Notes - Weather, readiness of materials and plant, air temperature, pavement temperature, surface compliance post milling, saturation, chipseal tack coat et al | Contractor - H | Principals Rep - W | Records CHAR(AMP) Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager) | 1.3 - Asphalt JMF confirmed
3.3 | Milling Insitu pavement | String to determine specified depth achieved |  | Specified AC depth achievable, area covered, lane and shoulder width | DR | W | Site records | 3.3 - Milling Insitu pavement | Applicable Standard CHAR(AMP) Acceptance Criteria - String to determine specified depth achieved | Frequency - | Criteria Notes - Specified AC depth achievable, area covered, lane and shoulder width | Contractor - DR | Principals Rep - W | Records CHAR(AMP) Remarks - Site records | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 CHAR(AMP) P11 Mix design report submitted to NZTA
3.4 | Over Milling | Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill. | Prior to pre-level | On site measurements CHAR(AMP) photos | DR |  | Site records | 3.4 - Over Milling | Applicable Standard CHAR(AMP) Acceptance Criteria - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill. | Frequency - Prior to pre-level | Criteria Notes - On site measurements CHAR(AMP) photos | Contractor - DR | Principals Rep - | Records CHAR(AMP) Remarks - Site records | Frequency - Pre site works
3.5 | Pre-Level | Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents | Prior to surfacing | On site measurements CHAR(AMP) photos | DR |  | Site records | 3.5 - Pre-Level | Applicable Standard CHAR(AMP) Acceptance Criteria - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents | Frequency - Prior to surfacing | Criteria Notes - On site measurements CHAR(AMP) photos | Contractor - DR | Principals Rep - | Records CHAR(AMP) Remarks - Site records | Criteria Notes - Design meets specification requirements and is approved by Principal
3.6 | Paving Method | Paving plan to be completed prior to establish on site. | Prior to surfacing | Paving Plan should be showing total paving runs with paving run width. | DR |  | Site records | 3.6 - Paving Method | Applicable Standard CHAR(AMP) Acceptance Criteria - Paving plan to be completed prior to establish on site. | Frequency - Prior to surfacing | Criteria Notes - Paving Plan should be showing total paving runs with paving run width. | Contractor - DR | Principals Rep - | Records CHAR(AMP) Remarks - Site records | Contractor -
3.7 | Tack / Chipseal | NZTA M10, M27, P11 | Each application pre paving | Design report requirements met. Provide the specific tack coat chipseal and residual binder | DR | W | Site records | 3.7 - Tack / Chipseal | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11 | Frequency - Each application pre paving | Criteria Notes - Design report requirements met. Provide the specific tack coat chipseal and residual binder | Contractor - DR | Principals Rep - W | Records CHAR(AMP) Remarks - Site records | Principals Rep - H
3.8 | Asphalt temperature | NZTA M10, M27, P11 | Every load on entry to site and again during compaction | Reference QMP for set temperatures | DR | W | Site records | 3.8 - Asphalt temperature | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11 | Frequency - Every load on entry to site and again during compaction | Criteria Notes - Reference QMP for set temperatures | Contractor - DR | Principals Rep - W | Records CHAR(AMP) Remarks - Site records | Records CHAR(AMP) Remarks - Contractor's asphalt designer has signed JMF report
3.9 | Thickness Monitoring | Confirm Pavement height will allow thickness required to be achieved. | Every 10 - 15 metres | Dipping on paver runs | DR | W | Site records | 3.9 - Thickness Monitoring | Applicable Standard CHAR(AMP) Acceptance Criteria - Confirm Pavement height will allow thickness required to be achieved. | Frequency - Every 10 - 15 metres | Criteria Notes - Dipping on paver runs | Contractor - DR | Principals Rep - W | Records CHAR(AMP) Remarks - Site records | 1.4 - Underground and surface utilities identified and accounted for in design
3.1 | Construction trial where specified | NZTA M10, M27, P11 |  | Include a minimum trial area, width of the paver and width of the roller. Include joints, offsets and overlap areas. |  | W | Trial records reviewed CHAR(AMP) filed | 3.1 - Construction trial where specified | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11 | Frequency - | Criteria Notes - Include a minimum trial area, width of the paver and width of the roller. Include joints, offsets and overlap areas. | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Trial records reviewed CHAR(AMP) filed | Applicable Standard CHAR(AMP) Acceptance Criteria -
3.11 | Compaction TAC | NZTA M10, M27, P11 | Minimum Requirements For TAC 1 Test per 300m² with 1 Core per 600m² on Mat , 1 Test per 100m Length with 1 core per 100m length on Joint. | As per NZTA M10 Specification | DR |  | Site / Lab records | 3.11 - Compaction TAC | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11 | Frequency - Minimum Requirements For TAC 1 Test per 300m² with 1 Core per 600m² on Mat , 1 Test per 100m Length with 1 core per 100m length on Joint. | Criteria Notes - As per NZTA M10 Specification | Contractor - DR | Principals Rep - | Records CHAR(AMP) Remarks - Site / Lab records | Frequency - Pre site works
3.12 | Compaction SAC | NZTA M10, M27, P12 | As per NZTA M10 Specification | As per NZTA M10 Specification | DR |  | Site / Lab records | 3.12 - Compaction SAC | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P12 | Frequency - As per NZTA M10 Specification | Criteria Notes - As per NZTA M10 Specification | Contractor - DR | Principals Rep - | Records CHAR(AMP) Remarks - Site / Lab records | Criteria Notes - Existing utility owners contacted and acknowledgement of proposed works. Service lid condition and levels confirmed suitable for proposed works.
3.13 | Post compaction testing | Shape - NZTA M10 and M27 section 9.8 and P11. Levels - NZTA M10 and M27 section 10.2 and P11 | Post AC Construction on each site | Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. |  | W | Site records | 3.13 - Post compaction testing | Applicable Standard CHAR(AMP) Acceptance Criteria - Shape - NZTA M10 and M27 section 9.8 and P11. Levels - NZTA M10 and M27 section 10.2 and P11 | Frequency - Post AC Construction on each site | Criteria Notes - Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC. | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Site records | Contractor -
4.1 | Construction Test Results - Cores | NZTA M10, M27 section 9.7 and P11 | Average of 4 measurements per core | Average Thickness > Specified Depth (Nominal) | DR |  |  | 4.1 - Construction Test Results - Cores | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 section 9.7 and P11 | Frequency - Average of 4 measurements per core | Criteria Notes - Average Thickness > Specified Depth (Nominal) | Contractor - DR | Principals Rep - | Records CHAR(AMP) Remarks - | Principals Rep - W
4.2 | Construction Test Results - Insitu density and air voids | NZTA M10 and M27 section 9.9 and P11 IANZ accredited test cert. |  | Insitu density and air voids as specified | DR |  |  | 4.2 - Construction Test Results - Insitu density and air voids | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10 and M27 section 9.9 and P11 IANZ accredited test cert. | Frequency - | Criteria Notes - Insitu density and air voids as specified | Contractor - DR | Principals Rep - | Records CHAR(AMP) Remarks - | Records CHAR(AMP) Remarks - Included in Asphalt Design Report
4.3 | QA Handover | NZTA M10, M27 or P11 as appropriate and contract drawings | For each site on the project | Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. |  | W | Evidence provided demonstrating full compliance with specified design | 4.3 - QA Handover | Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 or P11 as appropriate and contract drawings | Frequency - For each site on the project | Criteria Notes - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer. | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Evidence provided demonstrating full compliance with specified design | 1.5 - Traffic Management
4.4 | RAMM update | RAMM updates completed |  | Review of RAMM update and confirmation |  | W | Site records of RAMM update to be reviewed and confirmed | 4.4 - RAMM update | Applicable Standard CHAR(AMP) Acceptance Criteria - RAMM updates completed | Frequency - | Criteria Notes - Review of RAMM update and confirmation | Contractor - | Principals Rep - W | Records CHAR(AMP) Remarks - Site records of RAMM update to be reviewed and confirmed | Applicable Standard CHAR(AMP) Acceptance Criteria - TMP checked and approved Plans approved Current EED (if applicable)
Frequency - Before traffic management set up
Criteria Notes - Hold point - No traffic management is to be set up until TMP has been checked and approved
Contractor - H
Principals Rep -
Records CHAR(AMP) Remarks - Includer approved TMP
1.6 - Notification of intention to start work
Applicable Standard CHAR(AMP) Acceptance Criteria - Letter drop to local residents. Greater consultation where required
Frequency - Before work commences
Criteria Notes - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
Contractor - H
Principals Rep -
Records CHAR(AMP) Remarks - letter drops
1.7 - Pavement Marking Records
Applicable Standard CHAR(AMP) Acceptance Criteria - Measure existing markings to aid reinstatement
Frequency - Measure existing markings to aid reinstatement
Criteria Notes - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
Contractor - H
Principals Rep -
Records CHAR(AMP) Remarks - Site Measure or Video Viewer
- HP – Asphalt design verified for site commencement
Applicable Standard CHAR(AMP) Acceptance Criteria -
Frequency -
Criteria Notes - Contractor checklist copied to Principal
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Pre-commencement checklist signed and filed
2.1 - Binder content
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert
Frequency - 1 per 200t at asphalt plant
Criteria Notes - Individual Test Result: ± 0.5 Mean of Three Test Results: ± 0.3
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal
2.2 - Particle Size Distribution
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert
Frequency - 1 per 200t at asphalt plant
Criteria Notes - Refer to Table 5.3
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal
2.3 - Max. Specific Gravity (MSG) of mix
Applicable Standard CHAR(AMP) Acceptance Criteria - IANZ accredited test cert
Frequency - 1 per 600t at asphalt plant
Criteria Notes - Report
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal
2.4 - Air Voids at lab design compaction
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert
Frequency - 1 per 600t at asphalt plant
Criteria Notes - Individual Test Results: +2.0, -1.0 Mean of Three Test Results: +1.2, -0.6
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Test report reviewed for compliance , filed and copy sent to Principal
- HP – Material compliance confirmed (binder, CHAR(AMP) production properties)
Applicable Standard CHAR(AMP) Acceptance Criteria -
Frequency -
Criteria Notes - Material compliance checklist copied to Principal
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Asphalt material compliance checklist signed CHAR(AMP) filed
3.1 - Pre-AC Construction Site Checklist (week prior)
Applicable Standard CHAR(AMP) Acceptance Criteria -
Frequency - Prior to AC Construction on each site
Criteria Notes - No change from design report
Contractor -
Principals Rep -
Records CHAR(AMP) Remarks - Record any issues noted
3.2 - Go/No Go Checklist (within 24 hours)
Applicable Standard CHAR(AMP) Acceptance Criteria -
Frequency - Prior to AC Construction on each site
Criteria Notes - Weather, readiness of materials and plant, air temperature, pavement temperature, surface compliance post milling, saturation, chipseal tack coat et al
Contractor - H
Principals Rep - W
Records CHAR(AMP) Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
3.3 - Milling Insitu pavement
Applicable Standard CHAR(AMP) Acceptance Criteria - String to determine specified depth achieved
Frequency -
Criteria Notes - Specified AC depth achievable, area covered, lane and shoulder width
Contractor - DR
Principals Rep - W
Records CHAR(AMP) Remarks - Site records
3.4 - Over Milling
Applicable Standard CHAR(AMP) Acceptance Criteria - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
Frequency - Prior to pre-level
Criteria Notes - On site measurements CHAR(AMP) photos
Contractor - DR
Principals Rep -
Records CHAR(AMP) Remarks - Site records
3.5 - Pre-Level
Applicable Standard CHAR(AMP) Acceptance Criteria - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
Frequency - Prior to surfacing
Criteria Notes - On site measurements CHAR(AMP) photos
Contractor - DR
Principals Rep -
Records CHAR(AMP) Remarks - Site records
3.6 - Paving Method
Applicable Standard CHAR(AMP) Acceptance Criteria - Paving plan to be completed prior to establish on site.
Frequency - Prior to surfacing
Criteria Notes - Paving Plan should be showing total paving runs with paving run width.
Contractor - DR
Principals Rep -
Records CHAR(AMP) Remarks - Site records
3.7 - Tack / Chipseal
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11
Frequency - Each application pre paving
Criteria Notes - Design report requirements met. Provide the specific tack coat chipseal and residual binder
Contractor - DR
Principals Rep - W
Records CHAR(AMP) Remarks - Site records
3.8 - Asphalt temperature
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11
Frequency - Every load on entry to site and again during compaction
Criteria Notes - Reference QMP for set temperatures
Contractor - DR
Principals Rep - W
Records CHAR(AMP) Remarks - Site records
3.9 - Thickness Monitoring
Applicable Standard CHAR(AMP) Acceptance Criteria - Confirm Pavement height will allow thickness required to be achieved.
Frequency - Every 10 - 15 metres
Criteria Notes - Dipping on paver runs
Contractor - DR
Principals Rep - W
Records CHAR(AMP) Remarks - Site records
3.1 - Construction trial where specified
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11
Frequency -
Criteria Notes - Include a minimum trial area, width of the paver and width of the roller. Include joints, offsets and overlap areas.
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Trial records reviewed CHAR(AMP) filed
3.11 - Compaction TAC
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P11
Frequency - Minimum Requirements For TAC 1 Test per 300m² with 1 Core per 600m² on Mat , 1 Test per 100m Length with 1 core per 100m length on Joint.
Criteria Notes - As per NZTA M10 Specification
Contractor - DR
Principals Rep -
Records CHAR(AMP) Remarks - Site / Lab records
3.12 - Compaction SAC
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27, P12
Frequency - As per NZTA M10 Specification
Criteria Notes - As per NZTA M10 Specification
Contractor - DR
Principals Rep -
Records CHAR(AMP) Remarks - Site / Lab records
3.13 - Post compaction testing
Applicable Standard CHAR(AMP) Acceptance Criteria - Shape - NZTA M10 and M27 section 9.8 and P11. Levels - NZTA M10 and M27 section 10.2 and P11
Frequency - Post AC Construction on each site
Criteria Notes - Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape. Not more than 5mm under a 3m Straight Edge. Level - -0 CHAR(LESS) +5mm from Specified Level Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Site records
4.1 - Construction Test Results - Cores
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 section 9.7 and P11
Frequency - Average of 4 measurements per core
Criteria Notes - Average Thickness > Specified Depth (Nominal)
Contractor - DR
Principals Rep -
Records CHAR(AMP) Remarks -
4.2 - Construction Test Results - Insitu density and air voids
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10 and M27 section 9.9 and P11 IANZ accredited test cert.
Frequency -
Criteria Notes - Insitu density and air voids as specified
Contractor - DR
Principals Rep -
Records CHAR(AMP) Remarks -
4.3 - QA Handover
Applicable Standard CHAR(AMP) Acceptance Criteria - NZTA M10, M27 or P11 as appropriate and contract drawings
Frequency - For each site on the project
Criteria Notes - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA Spray sheets for membrane area received by Contract Engineer from Sealing Team. Surfacing layer extents recorded and verified by Contract Engineer.
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Evidence provided demonstrating full compliance with specified design
4.4 - RAMM update
Applicable Standard CHAR(AMP) Acceptance Criteria - RAMM updates completed
Frequency -
Criteria Notes - Review of RAMM update and confirmation
Contractor -
Principals Rep - W
Records CHAR(AMP) Remarks - Site records of RAMM update to be reviewed and confirmed