## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Thin Asphalt Construction | itp
section | 1.0 Pre-Commencement Activities (Design suitability)
checkpoint | 1.1 - Treatment Design confirmed
label | Frequency - Pre site works
label | Criteria Notes - Treatment Design approved by Principal
label | Contractor - H
label | Records & Remarks - Principal approval signature on Design document
holdpoint | HOLD POINT
checkpoint | 1.2 - Renewal Quality Plan
label | Frequency - Pre site works
label | Criteria Notes - RQP approved by Principal
label | Contractor - H
label | Records & Remarks - Principal approval signature on RQP
holdpoint | HOLD POINT
checkpoint | 1.3 - Asphalt JMF confirmed
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27 & P11 Mix design report submitted to NZTA
label | Frequency - Pre site works
label | Criteria Notes - Design meets specification requirements and is approved by Principal
label | Principals Rep - H
label | Records & Remarks - Contractor's asphalt designer has signed JMF report
holdpoint | HOLD POINT
checkpoint | 1.4 - Underground and surface utilities identified and accounted for in design
label | Frequency - Pre site works
label | Criteria Notes - Existing utility owners contacted and acknowledgement of proposed works.
label | ○ Service lid condition and levels confirmed suitable for proposed works.
label | Principals Rep - W
label | Records & Remarks - Included in Asphalt Design Report
checkpoint | 1.5 - Traffic Management
label | Applicable Standard & Acceptance Criteria - TMP checked and approved
label | ○ Plans approved
label | ○ Current EED (if applicable)
label | Frequency - Before traffic management set up
label | Criteria Notes - Hold point - No traffic management is to be set up until TMP has been checked and approved
label | Contractor - H
label | Records & Remarks - Includer approved TMP
holdpoint | HOLD POINT
checkpoint | 1.6 - Notification of intention to start work
label | Applicable Standard & Acceptance Criteria - Letter drop to local residents. Greater consultation where required
label | Frequency - Before work commences
label | Criteria Notes - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | Contractor - H
label | Records & Remarks - letter drops
holdpoint | HOLD POINT
checkpoint | 1.7 - Pavement Marking Records
label | Applicable Standard & Acceptance Criteria - Measure existing markings to aid reinstatement
label | Frequency - Measure existing markings to aid reinstatement
label | Criteria Notes - Hold point - No physical work is to be commenced on site until notification has been sent no later than 24 hours of establishing on site.
label | Contractor - H
label | Records & Remarks - Site Measure or Video Viewer
holdpoint | HOLD POINT
checkpoint | HP – Asphalt design verified for site commencement
label | Criteria Notes - Contractor checklist copied to Principal
label | Principals Rep - W
label | Records & Remarks - Pre-commencement checklist signed and filed
section | 2.0 Material - Source Properties Compliance
checkpoint | 2.1 - Binder content
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert
label | Frequency - 1 per 200t at asphalt plant
label | Criteria Notes - Individual Test Result: ± 0.5
label | ○ Mean of Three Test Results: ± 0.3
label | Principals Rep - W
label | Records & Remarks - Test report reviewed for compliance , filed and copy sent to Principal
checkpoint | 2.2 - Particle Size Distribution
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert
label | Frequency - 1 per 200t at asphalt plant
label | Criteria Notes - Refer to Table 5.3
label | Principals Rep - W
label | Records & Remarks - Test report reviewed for compliance , filed and copy sent to Principal
checkpoint | 2.3 - Max. Specific Gravity (MSG) of mix
label | Applicable Standard & Acceptance Criteria - IANZ accredited test cert
label | Frequency - 1 per 600t at asphalt plant
label | Criteria Notes - Report
label | Principals Rep - W
label | Records & Remarks - Test report reviewed for compliance , filed and copy sent to Principal
checkpoint | 2.4 - Air Voids at lab design compaction
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27 and P11 IANZ accredited test cert
label | Frequency - 1 per 600t at asphalt plant
label | Criteria Notes - Individual Test Results: +2.0, -1.0
label | ○ Mean of Three Test Results: +1.2, -0.6
label | Principals Rep - W
label | Records & Remarks - Test report reviewed for compliance , filed and copy sent to Principal
checkpoint | HP – Material compliance confirmed (binder, & production properties)
label | Criteria Notes - Material compliance checklist copied to Principal
label | Principals Rep - W
label | Records & Remarks - Asphalt material compliance checklist signed & filed
section | 3.0 Asphalt construction
checkpoint | 3.1 - Pre-AC Construction Site Checklist (week prior)
label | Frequency - Prior to AC Construction on each site
label | Criteria Notes - No change from design report
label | Records & Remarks - Record any issues noted
checkpoint | 3.2 - Go/No Go Checklist (within 24 hours)
label | Frequency - Prior to AC Construction on each site
label | Criteria Notes - Weather, readiness of materials and plant, air temperature, pavement temperature, surface compliance post milling, saturation, chipseal tack coat et al
label | Contractor - H
label | Principals Rep - W
label | Records & Remarks - Pre-commencement checklist (ie pre-start reqs, by foreman/crew manager)
holdpoint | HOLD POINT
checkpoint | 3.3 - Milling Insitu pavement
label | Applicable Standard & Acceptance Criteria - String to determine specified depth achieved
label | Criteria Notes - Specified AC depth achievable, area covered, lane and shoulder width
label | Contractor - DR
label | Principals Rep - W
label | Records & Remarks - Site records
checkpoint | 3.4 - Over Milling
label | Applicable Standard & Acceptance Criteria - Renewals Manager and NZTA invited to inspect milled surface and agree need and extent of over-milling and infill.
label | Frequency - Prior to pre-level
label | Criteria Notes - On site measurements & photos
label | Contractor - DR
label | Records & Remarks - Site records
checkpoint | 3.5 - Pre-Level
label | Applicable Standard & Acceptance Criteria - Renewals Manager and NZTA invited to inspect milled surface and agree pre-level extents
label | Frequency - Prior to surfacing
label | Criteria Notes - On site measurements & photos
label | Contractor - DR
label | Records & Remarks - Site records
checkpoint | 3.6 - Paving Method
label | Applicable Standard & Acceptance Criteria - Paving plan to be completed prior to establish on site.
label | Frequency - Prior to surfacing
label | Criteria Notes - Paving Plan should be showing total paving runs with paving run width.
label | Contractor - DR
label | Records & Remarks - Site records
checkpoint | 3.7 - Tack / Chipseal
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27, P11
label | Frequency - Each application pre paving
label | Criteria Notes - Design report requirements met. Provide the specific tack coat chipseal and residual binder
label | Contractor - DR
label | Principals Rep - W
label | Records & Remarks - Site records
checkpoint | 3.8 - Asphalt temperature
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27, P11
label | Frequency - Every load on entry to site and again during compaction
label | Criteria Notes - Reference QMP for set temperatures
label | Contractor - DR
label | Principals Rep - W
label | Records & Remarks - Site records
checkpoint | 3.9 - Thickness Monitoring
label | Applicable Standard & Acceptance Criteria - Confirm Pavement height will allow thickness required to be achieved.
label | Frequency - Every 10 - 15 metres
label | Criteria Notes - Dipping on paver runs
label | Contractor - DR
label | Principals Rep - W
label | Records & Remarks - Site records
checkpoint | 3.10 - Construction trial where specified
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27, P11
label | Criteria Notes - Include a minimum trial area, width of the paver and width of the roller. Include joints, offsets and overlap areas.
label | Principals Rep - W
label | Records & Remarks - Trial records reviewed & filed
checkpoint | 3.11 - Compaction TAC
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27, P11
label | Frequency - Minimum Requirements For TAC
label | ○ 1 Test per 300m² with 1 Core per 600m² on Mat , 1 Test per 100m Length with 1 core per 100m length on Joint.
label | Criteria Notes - As per NZTA M10 Specification
label | Contractor - DR
label | Records & Remarks - Site / Lab records
checkpoint | 3.12 - Compaction SAC
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27, P12
label | Frequency - As per NZTA M10 Specification
label | Criteria Notes - As per NZTA M10 Specification
label | Contractor - DR
label | Records & Remarks - Site / Lab records
checkpoint | 3.13 - Post compaction testing
label | Applicable Standard & Acceptance Criteria - Shape - NZTA M10 and M27 section 9.8 and P11.
label | ○ Levels - NZTA M10 and M27 section 10.2 and P11
label | Frequency - Post AC Construction on each site
label | Criteria Notes - Roughness - Where the length of the site or the geometry is such that a road roughness-measuring vehicle cannot be used then the straight edge can be used for checking the surface shape.
label | ○ Not more than 5mm under a 3m Straight Edge.
label | ○ Level - -0 < +5mm from Specified Level
label | ○ Where there is Kerb and Channel shall be flush with or no more than 5mm above the LOC.
label | Principals Rep - W
label | Records & Remarks - Site records
section | 4.0 Post-construction
checkpoint | 4.1 - Construction Test Results - Cores
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27 section 9.7 and P11
label | Frequency - Average of 4 measurements per core
label | Criteria Notes - Average Thickness > Specified Depth (Nominal)
label | Contractor - DR
checkpoint | 4.2 - Construction Test Results - Insitu density and air voids
label | Applicable Standard & Acceptance Criteria - NZTA M10 and M27 section 9.9 and P11 IANZ accredited test cert.
label | Criteria Notes - Insitu density and air voids as specified
label | Contractor - DR
checkpoint | 4.3 - QA Handover
label | Applicable Standard & Acceptance Criteria - NZTA M10, M27 or P11 as appropriate and contract drawings
label | Frequency - For each site on the project
label | Criteria Notes - Over milled and Deep lift extents recorded and verified by Contract Engineer / QA
label | ○ Spray sheets for membrane area received by Contract Engineer from Sealing Team.
label | ○ Surfacing layer extents recorded and verified by Contract Engineer.
label | Principals Rep - W
label | Records & Remarks - Evidence provided demonstrating full compliance with specified design
checkpoint | 4.4 - RAMM update
label | Applicable Standard & Acceptance Criteria - RAMM updates completed
label | Criteria Notes - Review of RAMM update and confirmation
label | Principals Rep - W
label | Records & Remarks - Site records of RAMM update to be reviewed and confirmed
checkpoint | Quality Record Close Out:
textbox | Quality Manager Name:
date | Date:
signoff | Add Signature