## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-021
[11 empty] | Revision : 0 | Date :
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Fencing Installation |  | Name: | Jake Cardillo | Name: | Damon Bromwich |  | Name: Shaun Kent
Contract No: |  |  |  | Specifications: Yarra Trams Infrastructure - Tram Stop Platform Design Standard
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | •Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | •All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check materials |  | Prior to commencing any activity | •Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish. •Welding shall be in accordance with AS1554 •Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000 | STD_T6000 CE-021-ST-0012 cl 4.3.1.4 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Confirm sleeve position |  | Prior to commencing any activity | •Confirm sleeves are set out to locations specified on design drawings | Construction Drawings | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.5 | Bonds |  | Prior to commencing any activity | •Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location | STD_T6000 | Verify | This ITP signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Sleeve installation |  | Prior to Asphalt | •Location of post sleeve's must align with the provided design drawings & 2.4m spacing. •Core two 100mm dimater, 300mm deep holes per panel at 2400mm centres. •Insert post sleeve and secure using non-shrink structural grout. | STD_T6002 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Post Installation |  | Each Lot | •Post shall be installed to designated height and level •The top of fence base plate shall be level with surrounding pavement | STD_T6002 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Grout Installation |  | Each Lot | •Surface shall be cleaned before application of structural fill grout | STD_T6002 | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Continuous Handrails |  | Each Lot | •5mm cap plate on handrail returns •All sections to be welded as per AS 1554 •All sharp edges and welds to be ground back to smooth finish •Domed buttons to be welded on top of handrail 150mm from the post centreline | STD_T6001 & T6002 | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
3 | Completion
2.1 | Fencing Panel |  | Each Lot | •Align fencing panel such that the posts sit securely in the installed post sleeves. •Ensure fence panel is free of damage and is positioned in accordance with the design line and level. | IFC Drawings | Verify | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.