## ITP-026
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-030
[11 empty] | Revision : 0 | Date : 27/02/2020
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Kirby & Casting Welding |  | Name: | Mustafa Kamel | Name: | Sam, Rocky |  | Name: | Shaun Kent
Contract No: |  |  |  | Specifications: Yarra Trams Infrastructure - Tram Track Construction Standard (CE-021-ST-0044), Yarra Trams Technical Specification, Design Drawings
|  |  |  | Structure / Component: Tram Tracks |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Works | •Ensure that all employees and contractors are using the most current and complete set of drawings | Design Drawings and Register | Visual Inspection | This ITP Signed Off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Welders Qualifications |  | Prior to Commencing Works | Welders shall be trained and qualified for the brand and each type of weld used, e.g. standard gap, long preheat, short preheat, junction etc. Certification shall be provided to and approved by the Superintendent prior to commencement of welding. | CE-021-ST-0044 Appendix C | Verify | This ITP Signed Off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Cutting Rail Ends |  | Each Weld | Rail ends shall be saw or friction cut. The cut ends of each rail shall permit butting of the rail heads to within 1 mm across the full head of the rail. The prepared surfaces shall be visually inspected for cracks and reground if any are detected. | CE-021-ST-0044 cl 4.9.4.6 & Appendix C | Inspect | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Butting and Aligning Rail Ends |  | Each Weld | Rail ends to be welded shall be butted together as closely as possible, preferably with no gap between rail heads. Care shall be taken to ensure that the rails are not pulled together excessively, forcing the feet of the two rails together and producing a peaked or high joint. Rail ends shall be butted and aligned, and assembled with base plate and spacer blocks, if applicable, prior to commencement of pre-heating. | CE-021-ST-0044 cl 4.9.6 & Appendix C | Inspect | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Preheating |  | Each Weld | A correctly adjusted, suitable oxy-LPG pre-heating torch shall be used. The preheating torch shall not be applied closer than 30 mm to the rails being pre-heated. Both sides of each rail end shall be evenly pre-heated from the rail ends to 150 mm beyond the rail ends. Pre-heating shall be confined to the top surface of the foot of each rail and to half the height of the web. Preheating shall be such that during welding, the foot and web of the rail shall be at a temperature of between 270°C and 350°C | CE-021-ST-0044 Appendix C | Inspect | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Welding |  | Each Weld | Rails and components shall be clamped in position prior to welding. Welding of the joint shall be carried out as a continuous operation. A disruption to the procedure may require additional preheating. All weld ends shall be welded using an overlapping back welding technique over the weld for a minimum length of 20 mm to ensure that all craters are fully filled to the full cross section of the weld. | CE-021-ST-0044 cl 4.9.9 & Appendix C | Verify | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Cooling Weld |  | Each Weld | The welded rails shall not be permitted to cool rapidly. Heat blankets shall be used to cover the welded portions of rails (i.e. web and foot on each side of the rail ends. The blankets shall extend a minimum distance of 300 mm beyond the extremities of the welds, i.e. minimum length 900 mm. The heat blanket shall remain in place for a minimum period of 15 minutes after completion of welding. | CE-021-ST-0044 cl 4.9.9 & Appendix C | Verify | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.6 | Grinding Weld |  | Each Weld | Grinding of the rail head, as applicable, shall be performed only after the rail head has cooled to below 50°C. A rail profile grinder shall be used to grind the rail head weld. A spindle (straight) or disc grinder shall be used to grind the rail check and groove. A 1 m straight edge shall be used while grinding the rail head (wheel running surfaces) to ensure a good straight surface and profile. | CE-021-ST-0044 cl 4.9.6 & Appendix C | Verify | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.7 | Flushness of joints |  | Each Weld | Misalignment of rail heads on the running and gauge surfaces, due to different amounts of rail wear, shall be rectified by grinding. The slope of transition shall not be greater than 1:25. Misalignments of the groove and check not exceeding 3 mm shall be rectified by grinding. The slope in transition shall not be greater than 1:10. Any grinding required to make joints flush shall extend to 500 mm each side of the joint | CE-021-ST-0044 cl 4.9.6 & Appendix C | Verify | This ITP Signed Off | IP | Fulton Hogan Engineer | N/A |  | N/A
3 | Testing
3.1 | Weld Review |  | Each Weld | • All welds shall be inspected by the Superintendent & Fulton Hogan Engineer • Unsatisfactory welds shall be cut out and replaced | Works Procedure | Inspection | This ITP Signed Off | TP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo An Chico: Write "N/A" to disable the cell.
Note on B17: BROMWICH, Damon: TBC - I don't think there is a qualification for this
Note on E27: BROMWICH, Damon: Updated. No US testing