## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-032
[11 empty] | Revision : 0 | Date :
Client: |  | Yarra Trams |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Orca Island Installation |  | Name: Jake Cardillo |  | Name: Aaron Hatch |  |  | Name: Shaun Kent
Contract No: |  |  |  | Specifications: Orca Island Installation Guide (Permanent)
|  |  |  | Structure / Component: Orca Island |  | Signed : |  | Signed : A.H |  |  | Signed :
|  |  |  | Location: |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to Commencing Activity | •Ensure that employees and sub-contractors are using the most current and complete set of drawings | Contract Drawings and Registers | Visual Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Commencing Activity | •All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP | EMP, TMP, SWMS, WP | Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check materials |  | Each Delivery | •Inspect delivered materials for any chips, cracks or other visible damage. | Receivable Inspection Checklist | Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Setting out |  | Each Lot | •Line and level shall be set out according to design plans •Alignment of new seperation kerb and islands shall be marked out using string line | Work Procedure | Inspection | This ITP Signed off | WP | Fulton Hogan Engineer, Client |  |  | N/A
2 | Construction Works
2.1 | Base preperation |  | Each Lot | •Concrete/asphalt base shall be inspected to be free of foreign loose materials and water pooling. •If required glue foam tape to the road where channel will be placed to ensure containment of adhesive. | Orca Installation Guide | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Preperation of Orca Polyurethane (Adhesive Agent) |  | Each Lot | •Mix Orca Polurethane as follows: - 2 parts of Part B Polyol Black - 1 part of Part A MDI Using a paint stirer in a drill, stir for a minimum of 4 minutes. •Once Part A & B have been mixed, add 1:1 Part C Rubber Compound in the mixed A+B compound and stir again for 2 minutes. Ensure even mix throughout the adhesive. | Orca Installation Guide | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Placement of Orca Polyurethane |  | Each Lot | •Pour the Orca Polyurethane compound onto the road, spreading to a thickness of approximately 2mm. | Orca Installation Guide | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.4 | Placement and Securement of Orca Island |  | Each Lot | •Lay the island on the polyurethane material. •Drill holes through island fixing hole into road surface, then screw island down securely with 12mm x 150mm coach screws and mudguard washer. Ensure screws are all the way down to secure island. •Plastic plugs to be put in bolt holes. | Orca Installation Guide | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.