## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-012 - Signage Installation | itp |  |  |  |  | ITP-012 - Signage Installation
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings
label | – all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Signage Conformance
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Ensure sign size and image correspond with IFC drawings and meets specification requirements
label | REFERENCE DOCUMENTS: Drawings AS 1742
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Service Identification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
label | REFERENCE DOCUMENTS: DBYD, Markings on ground, service chart
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Signage Install
label | FREQUENCY: Each Sign
label | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
label | ○ Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
label | ○ Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
label | REFERENCE DOCUMENTS: AS 1472, TS 1313 Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: