## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-018 - Energy Absorbing Bollards | itp |  |  |  |  | ITP-018 - Energy Absorbing Bollards
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: All employees and subcontractors shall have the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Design Drawings and Register
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including; EMP, TMP, PSP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Service proving
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: Service locating shall be conducted in form of DBYD and service location
label | REFERENCE DOCUMENTS: DBYD Service Locator, Service Chart
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Excavation permit
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: Ensure excavation permit has been obtained for the specified tasks
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Materials
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: All materials shall comply as per technical specification, Ensure materials are not damaged
label | REFERENCE DOCUMENTS: ASE TS
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.6 Setting out
label | FREQUENCY: Prior to Commenciing any Activity
label | ACCEPTANCE CRITERIA: Ensure location of bollards conforms to design drawings, Mark hole centre position at location
label | REFERENCE DOCUMENTS: ASE TS cl1.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Excavation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Care shall be taken in excavation, Hole shall be minimum 600mm dia and 1000mm in depth
label | REFERENCE DOCUMENTS: ASE TS 2.2
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure base is supported by solid ground, and block is level
label | REFERENCE DOCUMENTS: ASE TS 3.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Installation of reo cage
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: EAB cage shall be placed level
label | REFERENCE DOCUMENTS: ASE TS 4.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Pre pour checklist
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure minimum clearances are provided, no foreign materials are present, and EAB cartridge is level
label | REFERENCE DOCUMENTS: Fulton Hogan Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Concrete placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: 32MPa concrete shall be placed to cover reinforcement cage and fill hole
label | ○ Concrete shall be compacted by use of vibrator
label | ○ If surface pavers are to be used, allow 25mm gap from finished surface
label | ○ Ensure reo cage is level post compaction
label | REFERENCE DOCUMENTS: ASE TS 4.2
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.6 Installation of Bollard
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure bollard is installed, and bolts are tightened adequately if required, Concrete, pavers or bitumen shall be finished to specified requirements
label | REFERENCE DOCUMENTS: ASE TS 5.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: