## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-021 - Fencing Installation | itp |  |  |  |  | ITP-021 - Fencing Installation
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check materials
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Confirm manufacturing process with supplier, fencing material shall be laser cut with clean finish.
label | ○ Welding shall be in accordance with AS1554
label | ○ Ensure all components and fastenings are procured to the materials, sizes and grades specified in STD_T6000
label | REFERENCE DOCUMENTS: STD_T6000 CE-021-ST-0012 cl 4.3.1.4
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Confirm sleeve position
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Confirm sleeves are set out to locations specified on design drawings
label | REFERENCE DOCUMENTS: Construction Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.5 Bonds
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure fencing is isolated and earthed to achieve electrical isolation. Lug shall be fitted to baseplate at specified fencing location
label | REFERENCE DOCUMENTS: STD_T6000
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Sleeve installation
label | FREQUENCY: Prior to Asphalt
label | ACCEPTANCE CRITERIA: Location of post sleeve's must align with the provided design drawings & 2.4m spacing.
label | ○ Core two 100mm dimater, 300mm deep holes per panel at 2400mm centres.
label | ○ Insert post sleeve and secure using non-shrink structural grout.
label | REFERENCE DOCUMENTS: STD_T6002
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Post Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Post shall be installed to designated height and level, The top of fence base plate shall be level with surrounding pavement
label | REFERENCE DOCUMENTS: STD_T6002
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Grout Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Surface shall be cleaned before application of structural fill grout
label | REFERENCE DOCUMENTS: STD_T6002
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Continuous Handrails
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: 5mm cap plate on handrail returns
label | ○ All sections to be welded as per AS 1554
label | ○ All sharp edges and welds to be ground back to smooth finish
label | ○ Domed buttons to be welded on top of handrail 150mm from the post centreline
label | REFERENCE DOCUMENTS: STD_T6001 & T6002
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Completion
checkpoint | 3.1 Fencing Panel
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Align fencing panel such that the posts sit securely in the installed post sleeves.
label | ○ Ensure fence panel is free of damage and is positioned in accordance with the design line and level.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: