## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-029 - RhinoTac TGSI Installation | itp |  |  |  |  | ITP-029 - RhinoTac TGSI Installation
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check Materials
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection List
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level of reinstated bluestone kerbing shall be set out according to design levels. Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable).
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer, Client
textbox | Date Completed:
section | Construction of Access Ramp Bluestone Footpath
checkpoint | 2.1 Base preparation
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: RhinoTac Accessible Tactile should be cut and dry laid in accordance with the site specific application and applicable standards before fixing
label | REFERENCE DOCUMENTS: CTA_15_RhinoTac_Install
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Placement of TGSI tiles
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure the placement of the tiles are in accordance with IFC drawings and are compliant to AS1428.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Setting of TGSI tiles
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Apply adhesive mateial to the back of the RhinoTac Accessible Tactile, around the periphery and through the middle, be sure to apply enough adhesive to bind the tile to the substrate.
label | REFERENCE DOCUMENTS: CTA_15_RhinoTac_Install
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Fixing of TGSI tiles
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Carefully place the RhinoTac Accessible Tactile and apply pressure to transfer the adhesive. Drill down approximately 30mm into the subtrate using a hammer drill to fasten 6mm diameter screw
label | REFERENCE DOCUMENTS: CTA_15_RhinoTac_Install
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.5 Removing excessive adhesive
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Excess adhesive must be removed immeediately from the surface before curing, using a clean damp cloth (water only).
label | REFERENCE DOCUMENTS: CTA_15_RhinoTac_Install
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Completion
checkpoint | 3.1 Completion
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ensure pavement area is free of debris and waste.
label | REFERENCE DOCUMENTS: Visual Inspection
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: