## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-032 - Orca Island Installation | itp |  |  |  |  | ITP-032 - Orca Island Installation
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Check materials
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Inspect delivered materials for any chips, cracks or other visible damage.
label | REFERENCE DOCUMENTS: Receivable Inspection Checklist
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans. Alignment of new seperation kerb and islands shall be marked out using string line.
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer, Client
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Base preperation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete/asphalt base shall be inspected to be free of foreign loose materials and water pooling. If required glue foam tape to the road where channel will be placed to ensure containment of adhesive.
label | REFERENCE DOCUMENTS: Orca Installation Guide
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Preperation of Orca Polyurethane (Adhesive Agent)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Mix Orca Polurethane as follows:
label | – 2 parts of Part B Polyol Black
label | – 1 part of Part A MDI
label | ○ Using a paint stirer in a drill, stir for a minimum of 4 minutes.
label | ○ Once Part A & B have been mixed, add 1:1 Part C Rubber Compound in the mixed A+B compound and stir again for 2 minutes. Ensure even mix throughout the adhesive.
label | REFERENCE DOCUMENTS: Orca Installation Guide
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Placement of Orca Polyurethane
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pour the Orca Polyurethane compound onto the road, spreading to a thickness of approximately 2mm.
label | REFERENCE DOCUMENTS: Orca Installation Guide
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.4 Placement and Securement of Orca Island
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Lay the island on the polyurethane material.
label | ○ Drill holes through island fixing hole into road surface, then screw island down securely with 12mm x 150mm coach screws and mudguard washer. Ensure screws are all the way down to secure island.
label | ○ Plastic plugs to be put in bolt holes.
label | REFERENCE DOCUMENTS: Orca Installation Guide
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
textbox | Date: