## Table 1
[8 empty] | Inspection and Test Plan - Control and Supervision of the Works | [13 empty] | Doc ID: FH-ZU2- QU-ITP037 Rev: 0
Client: APAM (MELBOURNE AIRPORT) | [9 empty] | Contract No: CP14038 | [8 empty] | Prepared By: Jihad Barbar
Project: Taxiway Zulu 2.0 | [15 empty] | Reviewed By: Jamal Khodr | [6 empty] | Date: 21/05/24
Construction Process: Miscellaneous Concrete Structures | [15 empty] | Approved By: Jamal Khodr | [6 empty] | Date: 21/05/24
Specifications: Specifications as per Drawings
Structure / Component: Concrete Structures
Lot No: |  | Lot Details: | [8 empty] | Lot size/Quantity: | [6 empty] | Date:
Item No. |  | Task/Activity Description |  |  |  | Inspection/Test | [10 empty] | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility FH Engineer Superintendent Surveyor Foreman |  | Checked by:
[6 empty] | Frequency | Acceptance Criteria |  | Reference Documents |  | Inspection/ Test Method |  |  |  | Record of conformity |  |  |  |  | Fulton Hogan | Beca |  |  | Other | Date
1 |  | Preliminaries
1.1 |  | The current revision drawings are being used including subcontractors copy. |  |  |  | Prior to Start | Current revision drawing is being used (including the subcontractors copy). Current revision to be obtained via Aconex or ACC |  | Drawings and drawing registers |  | Verify |  |  |  | Up to date drawing sets and this ITP signed |  | HP* | FH Engineer
1.2 |  | Implementation of all measures and controls |  |  |  | Prior to Start | All necessary measures and controls being implemented, that is CEMP, TMP, SWMS, & WP |  | CEMP, TMP, SWMS, & WP |  | Verify |  |  |  | Site and office Inspection |  | HP* | FH Engineer
1.3 |  | Excavation Permit |  |  |  | Prior to Start | Excavation Permit issued by APAM obtained prior to any excavation on site. |  | Approved permits |  | Verify |  |  |  | Proof of & permit ITP sign |  | HP* | FH Engineer
2 |  | Supply of Materials
2.1 |  | Reinforcement |  |  |  | Pre- commence ment | Test Certificates demonstrating compliance of the reinforcement with the requirements of AS 3600 |  | Drawings and Specification |  | Verify |  |  |  | Aconex Corresponden ce |  | HP | FH Engineer and Beca
2.2 |  | Concrete Mix |  |  |  | Each Lot | Mix design to be submitted to contract administrator for review and acceptance. |  | Drawings ZULU-BECA- 014-DWG- 00201 ZULU-BECA- 030-DWG- 20001 |  | Verify |  |  |  | Mix Design |  | HP | FH Engineer and Beca
3 |  | Construction\Erection of Formwork
3.1 |  | Setout |  |  |  | Each Lot | Setout completed and conformance with Beca IFC Drawings. |  | Drawings |  | Verify |  |  |  | Survey Report |  | SCP | FH Engineer Surveyor
3.2 |  | Excavate |  |  |  | Each Lot | Excavation depth shall be as per specified or as shown on Drawings to accommodate structures. |  | Specifications as per Drawings |  | Verify |  |  |  | This ITP signed |  | IP | FH Engineer
3.3 |  | Confirm Ground |  |  |  | Each lot | Completion of excavation and inspection of subgrade materials. No soft spots, unsuitable material |  | Specifications as per Drawings |  | Verify |  |  |  | DCP Test Results (if required) |  | HP* | FH Engineer
3.4 |  | Formwork |  |  |  | Each Lot | Formwork / Reverse Shall conform to shapes, lines, levels and dimensions of the concrete shown or indicated on the Drawings. |  | Specifications as per Drawings |  | Verify |  |  |  | This ITP Signed |  | IP | FH Engineer Surveyor
3.5 |  | Penetrations/Cast in items |  |  |  | Each Lot | Penetrations/cast in items are present in the formwork. |  | Drawings |  | Verify |  |  |  | This ITP Signed |  | IP | FH Engineer Surveyor
4 |  | Reinforcement
4.1 |  | Reinforcement installation |  |  |  | Prior to concrete pour | Pre-Pour Checklist Completed:  Position and spacing check and recorded.  Cover checked and recorded.  Reinforcing supports checked and recorded.  Laps at required length.  Penetrations/cast in items |  | Specifications and drawings |  | Verify |  |  |  | Pre-pour inspection List CLA37A |  | IP HP* | FH Engineer
5 |  | Pre-pour Planning and Inspections and Placement (1st Pour)
5.1 |  | Pre-pour Inspection |  |  |  | Prior to concrete pour | Superintendent or Engineer to conduct pre-pour inspection prior to concrete pour |  | Specifications and Drawings |  | Verify |  |  |  | Pre-pour inspection List CLA37A |  | HP* WP | FH Engineer
5.2 |  | Pour in-situ |  |  |  | Each Lot | Concrete shall be placed within 90mins from batching. All concrete supplied for concrete structures shall be subject to project control testing in accordance with AS 1379. |  | Specifications and drawings |  | Verify |  |  |  | This ITP signed |  | IP | FH Engineer
5.3 |  | Concrete Testing |  |  |  | Each Lot | 1 – 7 Day cylinder and 2 – 28 day cylinders to be taken. |  | Specifications and drawings |  | Verify |  |  |  | Concrete Testers Sheet/Results |  | TP | FH Engineer
5.5 |  | Finishing & Curing |  |  |  | Each Lot | Concrete to be vibrated to ensure compaction and air voids removed. Screed finish required on exposed surfaces. Concrete shall be moist cured or coated by an approved curing compound for a period not less than seven days unless approved by the Superintendent. |  | Specifications and drawings |  | Verify |  |  |  | This Signed ITP |  | IP | FH Engineer
6 |  | Post Pour Details and Inspections
6.1 |  | Removal of Formwork |  |  |  | Each Lot | Forms shall remain and be maintained firmly in place until the concrete has attained the necessary strength to support its own weight. |  |  |  | Verify |  |  |  | This ITP signed |  | IP | FH Engineer
Final Inspection On behalf of Fulton Hogan it is hereby certified that the Works represented by the items of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. Print Name: Position: Signature: Date: / /
Legend:
| HP |  | Hold Point |  | Work shall not proceed past the HP until released by the Superintendent | [6 empty] | IP |  | Inspection point |  |  |  | Formal Inspection to be done and recorded
| HP* |  | Fulton Hogan Hold Point |  | Work shall not proceed past the HP* until released by Fulton Hogan | [6 empty] | TP |  | Test Point |  |  |  | Product compliance test to be undertaken and recorded/reported
[8 empty] | Inspection and Test Plan - Control and Supervision of the Works | [13 empty] | Doc ID: FH-ZU2- QU-ITP037 Rev: 0
Client: APAM (MELBOURNE AIRPORT) | [9 empty] | Contract No: CP14038 | [8 empty] | Prepared By: Jihad Barbar
Project: Taxiway Zulu 2.0 | [15 empty] | Reviewed By: Jamal Khodr | [6 empty] | Date: 21/05/24
Construction Process: Miscellaneous Concrete Structures | [15 empty] | Approved By: Jamal Khodr | [6 empty] | Date: 21/05/24
Specifications: Specifications as per Drawings
Structure / Component: Concrete Structures
WP |  |  | Witness Point | An inspection which must be witnessed by the Superintendent | [7 empty] | SCP | Survey conformance point |  |  |  |  | A qualified surveyor to check product/section/structure and report
AP |  |  | Approval Point | Written or verbal approval given by the Superintendent
Notes