## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix
3d56704f-44b9-436a-88a7-882ed39acce2 | checklist | Byford U-Beam Stage-1 Casting Checklist |  | Byford U-Beam Stage-1 Casting
33e1642c-1803-410e-97a2-b0e11c708144 | section | Pre-Pour Checklist
11f851a0-a6a3-4d59-b1ac-39894113681e | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
37d5a902-7e78-4fdb-b75b-cdc671e56b24 | checkpoint | Shop Drawings approved for Works
a930a70b-5901-46d1-b904-479b76705e9a | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
f8e73dfc-886b-4d67-98c6-6e39a8cdc024 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
188bfaff-0a90-410a-846f-bd10a3074607 | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
75201410-af47-44a4-b17d-5cb4a070bb6c | checkpoint | Detailed inspection of Mould and cage
3a775a10-4da8-4ba4-a7a4-aa230ed7361b | checkpoint | Cover maintained and within tolerance
bb06cc61-73f9-4e6f-82e0-380334f05a80 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
16ec099a-5519-4d90-901c-3a895c01098e | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
34fba665-51e3-4a97-a208-7eaeb6436470 | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
16e1d1c1-a5d6-4667-a3c7-3626199f2b4d | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
5e51f49c-3c78-41d0-9dbe-4f35f1a90573 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
9b25c136-be44-436e-98b7-8c46b7bbfe60 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
aa360362-ce7c-422e-b5db-dd524bc99ac6 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
a59146c4-8389-4b27-a430-a0e10fe58a88 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (attach results)
10da2b4c-11ff-4e52-814b-be536cae3523 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
fcaf9f0f-4d97-40d8-b07b-25b126cdb638 | checkpoint | Stressing Records subject to Client Review
81d23dd9-4d09-4b90-917d-b0e6aeaa8bd4 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
13db744c-ff6c-4b3f-ac20-52a8366c53fd | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
453a6ea5-c6d8-49cb-929a-ef6d373f0b9a | checkpoint | All Cooling tubes installed as per drawings
0b16c686-7a3c-4c96-aef4-31f463d33762 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
71f1e260-f02b-484d-914e-30ad5ce59a4d | checkpoint | QA Engineer Check Completed by
ce66b55a-740e-4420-9af6-d758ef4df8ff | checkpoint | Client Inspector (if present)
005240e5-2a13-44b7-9332-b5241bba55e2 | section | Supervisor Release
7e5161d9-daf5-403d-8d04-b069ceda843f | checkpoint | Supervisor Release to Engineering Team
744d6e1f-ccd1-4388-bf84-da980ecaaaf1 | section | Casting Checklist
48dc3901-28eb-4839-bded-57c964432a68 | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
b8665d9b-69e4-4e89-b094-3af6606f451f | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
d5721a31-a1f5-4f79-8517-2ec58e037a02 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
22b9b714-b3c6-4a93-8934-39f2c4d89573 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
7f111803-14d0-4f3b-b9bb-13fa74ade85f | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
77330ade-9880-481f-b4a7-3bb835951f6b | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
ffca7c7b-8c5d-443f-ad1a-39b3fe87a6e0 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
a078c6ca-68ec-4220-a886-2219a1ed2c61 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
95c2cca6-ae7b-41c3-8f6e-a9438f19ab32 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
b9af6e4d-5823-46b0-b4d2-038e73110740 | checkpoint | Concrete Placed within allowable time from Batching Plant
2485c0ac-aa35-4f8e-b3e5-7c0bcc285238 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
de48d957-f511-41cb-951f-da6f1e690e36 | checkpoint | Required Finish Applied as per Drawings
56482f97-77fc-4514-913d-6286912611c4 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
8d61de29-0e51-4f68-9803-9b4477e33200 | checkpoint | Concrete Covered Overnight
ce91d371-b61e-4db0-b18d-031c7e474cd0 | checkpoint | Cylinders Stored next to Bed
811b1bb2-cb15-4ef2-853a-8043aeeb13af | section | Stripping Checklist
070206a7-8604-4197-a528-ee8aa39693bb | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
8e9b49f6-da6b-41ed-b538-d6eda4f92470 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
da054075-a340-46c1-b2e1-fe01a2dfdba7 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
0f98b8f4-cd35-4995-b2b9-77412833dde3 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
842c54d2-6b32-47fa-8915-3f894e5e2c80 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
dd6bf488-ea55-43f4-a12e-d69e9ca1ca14 | checkpoint | Lifted and Handled as per Drawings
4c1e18b8-2d8a-4de6-8a57-1c9fea30835f | checkpoint | Product Clearly Labelled
3689c579-22d8-45e4-b424-0bad08b0e895 | checkpoint | Storage as per Approved Temporary Works Drawings
25423762-ab12-4c53-891f-7fc34f4c11c0 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature does not exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
86ba6e95-d86e-466b-86af-fa4392c911bf | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
b6cbb7fb-36f0-47b9-b746-3738f176afce | checkpoint | Specified Finish Achieved
420b3eac-c7c4-4d34-9cf6-a5eec17951b4 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
4cfeb342-b250-4eed-a3cb-8df53719d479 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire
a066e65d-dae5-4d36-8ccf-f9666e0cbe48 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
19ba0b17-ff44-4ffa-ad81-e1aaac531416 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
d4586d36-39e1-4576-863c-e9de04638363 | section | Any Defect Identified
2594e669-41ad-40f8-988a-701f89055f7d | checkpoint | Punchlist Completed
cf7067bf-2a1e-4765-83a1-b795e2873f66 | checkpoint | Repairs Required (if applicable)
e45dfa64-6ce6-4064-8ef3-b37b5bd7ed1d | checkpoint | Repairs Completed as per approved WMS (if applicable)
837dd6b1-aaed-45c4-942a-c172bd9e77c2 | checkpoint | Crack Map Completed
5c9fb481-d8fe-44c0-a6d9-7d8bf8fa961f | checkpoint | Any NCR Required (if applicable)
7666c60d-dc6d-42f3-af68-9ed67b247b0b | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
cece918d-81a5-4548-9d1b-8e0623e69334 | section | As-Built Drawings
16dc0419-0937-4c4c-b0e1-4c10a3ffba78 | checkpoint | As-Built Drawings Completed, Stamped and Attached
44046711-60ca-4533-985b-aebef3a15d1a | section | Concrete Strength Test Report
e344b336-bc86-41d2-a759-656c6937784c | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
bdca8ed9-02cb-461a-892d-19d7e29eed76 | section | Transportation Requirements
938e1344-07c1-46f7-a4a5-e2aa7754ae0e | checkpoint | Certificate of Conformance
ff11f27d-8802-4bda-86a2-94e676b3f163 | checkpoint | Inspection Release Certificate
53cd7c3b-f148-4f24-8332-43f04076ecc0 | checkpoint | Delivery Notes
3225e364-6de3-40f2-b3d0-c6992c03ca7a | checkpoint | Delivery Docket
f901d6a0-e746-4121-8251-5959aded4c21 | section | Final Acceptance
01b97dc6-c460-4807-a4bb-9fbbad221373 | checkpoint | Completed by
7c13ea6a-47c9-4f2e-a94b-ab38b1c5c6df | checkpoint | Reviewed by
fbb49e91-a678-4a2c-8652-1a080c30c495 | signoff | INTERNAL HOLD POINT
681538f2-bc4a-4dfb-b8d9-08994595cf93 | checkpoint | Client Representative (if applicable)
0c2966b2-bb35-4e3b-9215-d2a4ff017def | checklist | Byford U-Beam Stage-2 Casting Checklist |  | Byford U-Beam Stage-2 Casting Checklist
69e02ca0-aa40-4440-987b-fbfac32d8588 | section | Pre-Pour Checklist
e9d804bb-507a-4999-9de1-19b0cb8a7bcc | checkpoint-no-value | Details
1233fbbe-8a90-5695-bf6b-28144e51953d | textbox | Cast Number
d6de33d6-1d6a-59cc-aab5-58e1f9ee90b2 | textbox | Beam Number and Orientation
acb384d1-e98c-5a02-9f7c-1128a2c5f72b | textbox | End Diaphragm
97bfed52-24af-496f-b878-0367a5bf9c60 | checkpoint | Shop Drawings approved for Works
4b3f8c75-2893-4a84-b5cf-1e8bea62f84a | checkpoint | Mould and Sacrificial formwork Dimensions are within Shop Drawings Tolerance
4c1b674a-8bd8-50e8-959b-bec5d6dadc3e | note | Length
822d1104-8a27-5ed9-980e-888b7bf6caaf | note | Width
830ee2ae-8950-5298-a691-e9600cf10537 | note | Height
bab4373d-5276-50ed-954e-45ea96aec8c3 | note | Straightness
b82d264a-3d32-5473-8664-32a90bab9013 | note | Cross-section
c3207d6f-31da-496f-a961-37de7ae5ee94 | checkpoint | Condeck Surface Checked
a0273126-e254-5157-8d98-f128fa5c6b52 | note | Cleaned
9bb4e700-f5d2-5e02-883e-e5072418e64b | note | Sealed
3ec0752e-0691-5a4f-86ac-8445eadef662 | note | Oiled
0e62dce7-e433-4ba4-8abd-00ab27e3a1a3 | checkpoint | Reinforcement in Accordance with Drawings
800fadac-1be9-5858-94f4-5d4746740084 | note | Reinforcement size
0f320d4a-3d88-5e76-9d42-76621d58e218 | note | Lap Length
f61d890c-4ba6-5c8f-bcd8-10b22c2f1c07 | note | Splicing
62881279-32c4-593b-b849-3eefda69eb96 | note | Bar Chairs
b31c7adc-8ff0-5948-b00d-593cf326b1e2 | textbox | Stitch pour Reinforcement lapping bars spacing maintained and template plate installed
12cb8723-6db8-5a57-b575-655471779936 | textbox | Blockout recess around lifting Hoops
80c2d060-3c27-4cae-a855-4e2c95630e80 | checkpoint | Detailed inspection of Mould and cage
94d72df5-e41c-41e9-a973-8fec3bf00e61 | checkpoint | Condeck (Top Slab) - Verify all brackets fixed at slab thickening
bec954e6-8601-4196-9e81-051772112915 | checkpoint | Cover maintained and within tolerance
98bbf309-ebbb-46ff-88db-e49d08f0d40f | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
9f215da9-19e9-5047-a80a-c229bb1325f1 | textbox | Ferrules M16x96 (Handrails)
8d90112a-ec60-5a67-a2f3-d316d5261991 | textbox | Ferrules M10x45 (Expansion Joint Cover)
d1b00e18-ceba-57fe-9b5e-6d4e7db97304 | textbox | Ferrules M10x45 (Ladder)
49d2450b-c55f-5f52-8737-b23eef564e73 | textbox | Ferrules (Other type, specify)
5d0578fd-8107-4832-8967-a90957ac2d4b | checkpoint | All Stainless Items are installed in accordance with Drawings
1e328254-d184-5f54-943a-e1976e1eb331 | textbox | Other type, specify
0ef49df0-35d8-4116-bdd5-7a16d4ea940d | checkpoint | Earthing and Bonding is installed in accordance with Drawings
87db205a-a14e-5be0-b795-5d53984ab585 | textbox | Earthing Terminals (FDB-16)
09abc58f-8a0f-5f60-96e2-32bee1276a84 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
a020b351-e865-5d5e-a4b5-b441cabfd625 | textbox | <20 mOhm across cage Length
4ef34acd-9e10-5711-9e70-4735a0a2bbd0 | textbox | Checklist Completed (North & South) (attach results)
1414f7c5-5e61-4aa7-a427-013b3f054cf0 | checkpoint | All Temperature Loggers are installed as per Approved WMS
7f2ff394-48d1-5d12-a9a5-88aa58174bf6 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
571ae87d-30f9-4a7f-9c57-c354eb6c4e33 | checkpoint | All Cooling tubes installed as per drawings
22055223-9286-4296-9beb-00bb5f4df5fa | checkpoint | QA Engineer Check Completed by
a31f14b7-a59d-45d4-923a-048498b5e296 | checkpoint | Client Inspector (if present)
118485a3-1c5d-4657-a89a-fe6114039488 | section | Supervisor Release
aa567090-54f6-484f-83c2-f0a5b2df1094 | checkpoint | Supervisor Release to Engineering Team
d16096b4-b137-41e1-b7c7-ce383af86553 | section | Casting Checklist
1c30cd3a-8fed-4c79-8dc6-ffec1e76e6af | checkpoint | Casting Information
1a647942-8258-57e6-b6ff-621161085e77 | textbox | Cast Date
bf85045e-7291-4e41-adfc-4f3930c1b224 | checkpoint | Concrete Delivery Dockets
d392af45-5195-5119-892d-80cfe0b6a20e | textbox | Concrete Delivery Dockets (list all)
ebcc38eb-b9fb-4703-92f0-a8406a18856e | checkpoint | Total Concrete Volume
60fa028a-b7ea-54d1-954a-1213bd11e8e1 | textbox | Volume (m3)
8446c524-f6d7-45a3-86c0-70114a1ef359 | checkpoint | Mix Design Verified
f8a395fa-8391-5639-a09e-c5241875a63d | textbox | Specify mix used
95766753-ca7b-4c77-8947-eb86b913dd28 | checkpoint | Ambient Temperature within Limits
a4f51cbb-ff6a-5071-bca5-5481459038f1 | note | max 38°C
a1109acb-badd-4ae9-bc6c-65a6b27c8094 | checkpoint | Concrete Temperature
897bf355-b709-54f5-9399-3a7efa254455 | note | max 32°C
7b69d6a1-c9f1-46bf-9407-ee9e74008ba1 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
e41fe62b-76cf-448a-97b9-634915c22099 | checkpoint | Trucks Tested for strength
1db14c07-5972-5f2c-9497-617ae1c2a547 | textbox | Test Report Reference Number (list all)
c51f7d46-2953-4497-8ad0-6dfbd622d0ea | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
bcfedf44-15f7-4abe-88f3-cd6592d879e9 | checkpoint | Concrete Placed within allowable time from Batching Plant
4e281710-dc4d-4f7e-b96e-a08250923013 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
d565c155-02a7-47a7-8a39-eee94646fe3d | checkpoint | Required Finish Applied as per Drawings
f46b299d-0b62-452b-b947-0fa3149803f7 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
12b6b7ab-4b40-4a9e-950e-edd052f41a07 | checkpoint | Concrete Covered Overnight
76acac69-7ec7-4237-821a-c6580bbb0c40 | checkpoint | Cylinders Stored next to Bed
228bfdc9-4a5b-4fa6-8f82-66b53d9dfae3 | section | Stripping Checklist
8a7b2b52-f8f6-4b98-9b5b-d554f32bc7e1 | checkpoint | Date Stripped
901c78d2-ef96-5ae6-a1f7-9a653c24de1a | textbox | Enter Date
43fe64c4-70f6-4cf3-a1e8-1171a28ed0c5 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
f0b85fdc-6c4d-511a-a42b-626445232756 | note | Conversion KN to MPa = Reading / 7.851
786038d6-bea8-5d36-850d-c5b0f8eeb594 | note | Stripping strength 20MPa
ab2f98ba-453f-546d-8399-ab6d61235c1c | textbox | Stripping Strength (Stage-2 Casting)
a992bb3c-427c-464b-b122-9de737b09c32 | checkpoint | Lifting Strength Achieved
ddd53939-10f1-5062-be90-0c69a5b2b2d6 | note | Lifting strength required for stage 2 casting - 20MPa
990eb32e-733a-5942-8ad7-1dc6175f29d7 | textbox | Specify strength at time of lifting
f20fadb9-136e-4118-8037-44c59e33cc9c | checkpoint | Curing Strength (Stage-2 Casting)
775b182d-e021-55ec-9a45-7abb946c1815 | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
c4a6b006-d64b-56cc-af22-7a32fa98085e | note | Tarped until the curing strength achieved
21c35c3b-fb0d-400c-9376-fa4aec637f58 | checkpoint | Lifted and Handled as per Drawings
844a9458-28bb-4117-ac76-c94bdd62e421 | checkpoint | Product Clearly Labelled
b7b6fa6f-368d-4d79-96a2-0a191a18267b | checkpoint | Storage as per Approved Temporary Works Drawings
e29db614-d051-4ba7-ad2c-c4a9eb29d205 | checkpoint | Secondary Curing as per Approved Methodology
8a3fc87f-1a7b-44bd-8fae-92eda854319f | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
df44e42b-2e80-5f94-ac7f-80765b72e6f9 | note | Length
e4265a90-0641-5ae7-9983-17040cae58b3 | note | Width
7bb4ba7f-c14e-56fd-9171-dbeee66caa97 | note | Height
ff36979f-97bd-5709-a920-421e847495e8 | note | Straightness
f932effb-f869-5bc3-b54d-3dc7703f8e53 | note | Cross-section
b4b7fb99-35a5-4a3d-8f53-5d3ef4511dc0 | checkpoint | Specified Finish Achieved
c174c223-617c-4bff-b666-a72c12630471 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
a4c9f700-bb5d-5e3a-a5ae-51c28d8141b9 | textbox | Ferrules
3cde73a1-6070-5769-9afb-cb3e15618119 | textbox | Stainless Items
f6ffd1c4-9b9b-50c3-aac9-88cfb320a9fb | textbox | Lifters
8d91365d-45e2-5a6d-abc6-191ce31f5767 | textbox | Blockouts
b46c54eb-4f86-491b-8423-cb229ef6a560 | checkpoint | Post-Pour Works Completed (As Required)
7a542891-b623-52f8-ae88-77c1c09fb89f | textbox | Ferrules are Cleaned and Capped
80630288-7f59-5868-b4d3-3428afa34d9b | textbox | Roughened Surfaces are Greencut
915898d3-a5d9-5e68-9706-7a0fa68a24a2 | textbox | All Miscellaneous Items are Completed
7b44f1b2-c84f-4214-9883-c4421fb2c6b1 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
a3b8ed66-4aa0-40b2-a457-adcbaa10327d | section | Any Defect Identified
bdb4e0a3-e94c-4b15-b0f4-c32cd4de221d | checkpoint | Punchlist Completed
46f3bc41-7e30-4f9c-8bfd-8b3ad038d744 | checkpoint | Repairs Required (if applicable)
b3a4e113-562a-43f4-a6ce-1c7457a82149 | checkpoint | Repairs Completed as per approved WMS (if applicable)
891c918e-ae08-4fef-b297-3d7fb30f53a5 | checkpoint | Crack Map Completed
a600c08b-615b-42a4-a70e-31e69ba18b36 | checkpoint | Any NCR Required (if applicable)
63a845a7-9d37-46d2-817e-1a11a8a26dcd | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
e5452a26-a331-4ae9-9b7c-0f5b0e669687 | section | As-Built Drawings
18732704-20e1-4a1f-94be-a0a857027fe1 | checkpoint | As-Built Drawings Completed, Stamped and Attached
05afab1a-9537-4574-98d2-6a569cdd15cb | section | Concrete Strength Test Report
94fd4638-352c-43e4-a110-1248f6e13832 | checkpoint | Concrete Strength Test Report Received
72ed3bf3-f25d-562e-9513-1b400cbb5e33 | textbox | Concrete Test Report
009f2cbd-af76-54bf-99ce-3bcdafdfefd1 | textbox | 7 Day Strength (List all)
bde663bb-3906-572f-9122-80785c06ca94 | textbox | 28 Day Strength (List all)
bc7afb81-1cf5-4423-8b6a-8350107d682b | checklist | Preliminary Activities and Materials Approval Checklist |  | Preliminary Activities and Materials Approval
59c569d9-af0e-4098-9e2e-aa3ceef9353c | section | Preliminary Activities (Approved by Client)
71bbe339-b59b-4ee7-a177-b2afa4ff2b0d | checkpoint | Compliance to AS/NZ ISO 9001:2015
eee1cfaf-2b77-45a9-b1b4-b4c0c7c5fe10 | checkpoint | Permacast Project Quality Management Plan
53a4b40e-9c46-46b1-83e6-d9eac22f5120 | checkpoint | Inspection & Test Plan
1c57fd7e-486b-4f4c-a676-fc824b4104ac | checkpoint | MDR Index
5a3a34be-2061-4aa3-8723-9ce4d4051223 | checkpoint | Work Method Statement (WMS) - Prestress
24a58c3e-6de9-4510-8816-a570243eba2d | checkpoint | Work Method Statement (WMS) - Curing
64e897fb-d60a-4c61-a1e9-c2c192555eab | checkpoint | Concrete Repair Methodology
f94b045e-a0c4-4ce1-b160-3623c67cf5dd | checkpoint | Shop Drawings
a637bcfd-4260-4f22-bea5-93579c4569ef | checkpoint | Test Panel Prepared and Inspected by Client
8a7347c6-4425-4fe9-9bea-1c78d4e07f53 | checkpoint | All Technical Query Forms (TQs) Reviewed and Approved for Works
9c4dc1e5-2d12-41ad-bb06-fadedac91a77 | section | Concrete
2c541f82-813c-4188-aa46-8cc603292ec5 | checkpoint | S65 Concrete Mix Design Approved by Client
dc1e2d50-69a4-4cd5-9cdd-a4dc15079d78 | section | Steel Reinforcement
d64b2f66-aecf-4ddd-8c6f-d72e0119158d | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
5a9f8842-daa6-4d67-9ad6-fe8e19a0b438 | checkpoint | Cut Bar Length Tolerance +0mm -10mm, Bends in Plane, Correct Cog Lengths etc.
97ea2900-6005-4ffe-9fe1-b49465d336cb | section | Prestressing Tendons
37de0717-d100-4b80-a78e-7d6ef7885dca | checkpoint | Inspection of Delivery to Confirm Compliance with Order and Drawings
3cd57bdd-d815-411a-b9d8-329298cc72c7 | checkpoint | Ensure that all Coil Numbers are recorded
46dcb04c-7e24-45e2-bd87-8af1badaf5ba | checkpoint | Stressing Calculations Submitted and Approved by Client for Works
bae6b534-bc31-4ba7-a24d-236a94e11453 | checkpoint | Stressing Jack Calibration Certificates
2252962e-3b82-4954-8e0d-3cf647ca2f7b | section | Lifting Anchors
82a69b65-680f-4b5a-ac4c-d4248e506cc5 | checkpoint | Lifting Design Approved by Client
a264a881-bceb-4b35-aee7-342fbaa61330 | checkpoint | Lifting Devices Approved by Client
9f3f95c9-66d9-4332-8233-4cdaed838485 | checkpoint | Inspection of Delivery for Completeness and Quality
1474312c-6aad-454c-9129-272df66ec1d1 | section | Cast-in Items and Ferrules
35e450c8-afc8-47c0-9abc-151844699cb0 | checkpoint | All Cast in Materials Approved
28d50a56-12e8-40db-9e78-e0df7dcefc41 | checkpoint | Inspection of Delivery for Completeness and Quality
a0e9b0e9-f145-4563-a445-c31d14db3046 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v1) |  | Byford U-Beam Stage-1 Casting
1b283145-9444-42cc-86d4-7c38d61cc7b4 | section | Pre-Pour Checklist
34eb53e8-3762-4da2-9dd0-3cfa8ec76271 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
bca35014-dcf4-4ce1-886f-9d682980d4ae | checkpoint | Shop Drawings approved for Works
f656237f-1e93-43e5-9e64-2de978e3f465 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
5ced35c8-a6de-4316-abd5-d16386a3e515 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
3e79e8c0-bff8-4b13-8f03-d5c49d5e601a | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
73325ba1-df01-4195-8db7-dec36c028e92 | checkpoint | Detailed inspection of Mould and cage
e24f6dfe-d5f1-4186-a525-d4cc656ec91d | checkpoint | Cover maintained and within tolerance
4b276b4f-1b04-48ea-a1e5-e45b22cb7ec0 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
d23968b0-8e43-4210-9ea6-d82f890a0c64 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
6c534ea7-ba65-4442-9940-e5496cfdc34c | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
c6c80186-6f4c-43bd-a6e2-92fff1b65498 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
2355acbc-c061-408d-82bc-4d247667621e | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
ee341819-7665-47fe-84cd-a72f1909bf47 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
5df617b8-e1a4-49ad-930a-ca610f481d3a | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
9ed13afc-e62d-4446-a0df-e1db36c11028 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
5a11a7b0-b7fb-4a0b-bb64-373b982ee9f4 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangementr verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Mutli-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
7ffe0f24-b8fc-43d2-95d6-f722ca9116af | checkpoint | Stressing Records subject to Client Review
b7ccfb81-71b0-4489-9cfd-af807ee2f336 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
eb17fd1e-1b18-4d7b-8f08-374f2506d759 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
3a71a13d-2bfc-46e7-8017-689c85344f72 | checkpoint | All Cooling tubes installed as per drawings
1184bb1f-03d2-48bb-8018-e60e6ae3950a | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
356b7072-d85d-4f73-bc58-70887926aef6 | checkpoint | QA Engineer Check Completed by
99faac90-15b3-4a19-8154-43fc8d5f517c | checkpoint | Client Inspector (if present)
977002ac-7d4f-4018-a294-e4cbbd1d4c9a | section | Supervisor Release
236a0495-482c-4a98-af3f-093da395c35d | checkpoint | Supervisor Release to Engineering Team
4e39cc15-9c4b-44ba-8069-91cf45e7ba88 | section | Casting Checklist
67d33390-ecca-45d7-bbe8-6344b689379a | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
34fd634d-6622-452b-88ae-fb87ba2b8237 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
1f43ee4a-b478-466e-8f59-9f6a1f3d5304 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
85d5022a-792e-4580-a2e5-ad65c7f9cece | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
8d6500f8-b29a-4b7f-8a9a-d61032d3755e | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
2956e49e-9a58-44a3-b385-281b5415b99b | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
d501ec00-d49c-44e3-92a9-317483922c8e | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
f695eb0e-7e3d-424d-b7ac-c4d2f7f3e0d5 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
bc324c2b-adee-40f4-a3f3-f272d89cdaaf | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
49af8714-c82c-4dfc-8d0f-68fecd29eedd | checkpoint | Concrete Placed within allowable time from Batching Plant
18ecfb61-a3e3-4207-8d6a-504cba7461fb | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
d3e17bc2-f332-4502-9c35-b47caf67f7cd | checkpoint | Required Finish Applied as per Drawings
9ce32ce4-392e-4bac-959c-f073a316740e | checkpoint | Retarders applied on Green Cut areas as shown in drawings
980ee978-0055-460c-b4c7-b940ff9f30f8 | checkpoint | Concrete Covered Overnight
f743b25b-f405-495c-adcf-128df4ab20a2 | checkpoint | Cylinders Stored next to Bed
66813685-59a4-4baf-8596-e5fcf17bf705 | section | Stripping Checklist
b8398943-2e34-4fbd-8eea-bd998103b54e | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
6a3eaa61-562b-4d35-bacf-9665ecccb02d | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
0fd2af72-69ff-48fe-8245-88ca4ea0db5f | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
6ec9907e-8da6-4e60-a6bb-6ec61e8ca37f | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
b753d217-63d9-454d-8664-97dfb498da50 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
c7b9632c-6155-4006-adc0-c8163164fd01 | checkpoint | Lifted and Handled as per Drawings
4aea4ed2-5ade-410a-92b3-0616f7a6604a | checkpoint | Product Clearly Labelled
d8586f61-b348-4593-a35e-555ee686ad06 | checkpoint | Storage as per Approved Temporary Works Drawings
5c7010b5-547d-4556-b1c0-098ff804b995 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature does not exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
df2720c6-8e8a-4924-a259-81d259c04a8e | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
393ea6ab-422f-43a6-8de4-7c1189902535 | checkpoint | Specified Finish Achieved
8d59663c-7207-4d9a-af63-5ed89411693e | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
f94eeef2-a80f-41bf-8b7c-f1937ef36927 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
d0b5905b-24c8-48ca-b1e0-5377125d2553 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
5edf2845-e52e-4445-a0cb-8a38f812b75c | checkpoint | Temperature Logging Completed and Conforming. Attach Results
f4eba698-951b-4f37-a98a-2dc7dd18239e | section | Any Defect Identified
ea0ce409-f14d-4bcb-9a49-32d0662beb78 | checkpoint | Punchlist Completed
9df015d7-0e9e-465e-96b0-e0929aad9042 | checkpoint | Repairs Required (if applicable)
17aac10e-0d1f-4904-896f-83ec1131927e | checkpoint | Repairs Completed as per approved WMS (if applicable)
1b25b13f-243e-4d8b-9564-def2e17b7660 | checkpoint | Crack Map Completed
f9779003-f90c-4ae1-8582-a87b598a6fa2 | checkpoint | Any NCR Required (if applicable)
04d2f7c3-f652-425f-bc1d-03ff5e4a26d4 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
1aa4adb4-6f84-4f7c-9ca7-b36439c98b5d | section | As-Built Drawings
88e1a23f-8b57-491f-8ed6-232c4178359c | checkpoint | As-Built Drawings Completed, Stamped and Attached
07a649aa-2895-47b7-ac63-598dd16f4f74 | section | Concrete Strength Test Report
0e893350-206d-4ccd-ac1a-c3fcef34e35f | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
8004d94e-4b54-4019-908a-39031e3de29b | section | Transportation Requirements
bba6ea79-9f52-43ea-ba05-2a4aacfdff66 | checkpoint | Certificate of Conformance
6fe71b55-0f51-4644-be2c-68cdb6ec80d7 | checkpoint | Inspection Release Certificate
95bace19-dd45-4f35-b988-b6023204932a | checkpoint | Delivery Notes
31542ef5-2aeb-400a-8f37-8c433765d29d | checkpoint | Delivery Docket
47f1f9ac-57c0-443d-befb-792347c7993e | section | Final Acceptance
6f2879df-abb9-4e59-9758-1a103be4314b | checkpoint | Completed by
8d0976ca-90ec-4d0d-bc3f-714af951b19d | checkpoint | Reviewed by
6d5271be-9ef0-41ee-ba42-66c1ea67cc7c | signoff | INTERNAL HOLD POINT
a838f616-38a3-475d-8884-d74867d7001f | checkpoint | Client Representative (if applicable)
4e5d198a-4f2a-4507-89fa-fbb4b4eb2c20 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v2) |  | Byford U-Beam Stage-1 Casting
023f7196-a4b1-47ef-91ad-e81a88283f88 | section | Pre-Pour Checklist
307a56f5-10e6-4577-9110-38cdb7f2937f | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
dda59448-a973-4a76-9011-fd0c0ca4cc5d | checkpoint | Shop Drawings approved for Works
10e7ba12-aba2-431a-86d8-afac863ddc85 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
5cc4ffce-b49c-4ff4-8dd6-db8fb5afa671 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
69f81d7b-406e-4998-bd05-cad41bb01a4c | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
2fc72fe5-2e1c-4de0-859f-e1d7ff7d0fc8 | checkpoint | Detailed inspection of Mould and cage
01a17418-32a8-43dd-a20f-66a2eedbd7dc | checkpoint | Cover maintained and within tolerance
029fae10-b775-4cf3-9884-12f68614fb17 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
12b84248-dd90-4809-b187-ca54cb1d98b9 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
debbedcb-ef98-4632-b445-1849743f35ba | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
85aa444f-a967-4c31-8b7d-b58ae8d4ca03 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
757c8ae4-9316-4faa-843b-38ede2e0b15a | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
0c5b8ee9-1b91-4966-8a17-9bfc6a304561 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
db0ad82c-1436-4522-89b7-d331cf3638f6 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
014ef517-a7e8-44be-956f-c9151ceb3bc3 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
f3d5490f-86ee-47de-957d-83d1aba19f07 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangementr verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Mutli-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
84d4ee06-9fdd-48b0-a492-d7e1ff2a50fa | checkpoint | Stressing Records subject to Client Review
a6a02d9a-3356-4f26-8aea-df6aefeef974 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
6b47284c-4f2b-4ac5-bf04-def772e35af9 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
cca31838-53d0-4e06-9388-5ab156be4282 | checkpoint | All Cooling tubes installed as per drawings
e04f6d54-5bcf-4b01-8f53-60e9bdede152 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
e9733a5d-9dc5-463e-8d16-77203d623100 | checkpoint | QA Engineer Check Completed by
1650a34a-5909-4513-957d-5ae2b09a5872 | checkpoint | Client Inspector (if present)
7ded56a8-7e29-409e-b798-8aad20dcfdea | section | Supervisor Release
7710714f-ab49-4a0b-ad57-974d2df3dff5 | checkpoint | Supervisor Release to Engineering Team
d0235232-17c4-42ac-ae10-c5c868900373 | section | Casting Checklist
522a8720-c8a8-41c9-b118-27655b9dfbcf | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
472da490-509c-4b69-8989-e344412f7d58 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
5cf92a31-e1ae-4655-87a3-4049c52c7997 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
fa0e693d-3036-4516-9355-866511ae3beb | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
6e9e8f27-5e6e-439b-b3de-1f01522a26d5 | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
20d89684-5ab7-41ed-bcf1-6299d6d9d212 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
f4dbefc0-c6aa-4cf9-9bf5-15278fa39158 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
85c6ca16-6060-4127-838f-baa127930074 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
a7fa1991-ebb2-4bca-9376-209ae3ad9820 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
40810b92-3b85-4697-9cdf-183bddb607a4 | checkpoint | Concrete Placed within allowable time from Batching Plant
f72e5388-2141-45ed-9635-3deea8b2ff51 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
5280a728-3375-46f0-b9f3-9b08ea4f5bfc | checkpoint | Required Finish Applied as per Drawings
20a6fb0b-adb0-4ae3-87dd-d8247eb5dae9 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
492feee7-7d50-4b9b-b27e-2a11bc26dc67 | checkpoint | Concrete Covered Overnight
b48cacff-00b3-4970-9886-28fabea63e1f | checkpoint | Cylinders Stored next to Bed
51a0ef4e-5a6b-42ba-9015-24d4cd02883d | section | Stripping Checklist
efc191a1-0a1d-41e1-b115-686f1a0825ff | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
4afdeaef-a148-4073-af7e-da822c55cf12 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
0f2903d4-9125-40ba-ab92-299bcbf9a481 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
facfa2e0-138f-4b6b-9447-e193dc283246 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
3d78f3f4-0278-4e6d-a300-16485623862f | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
873c36b1-3d2a-43ea-b222-9a81b3869df6 | checkpoint | Lifted and Handled as per Drawings
ff64407b-0f70-4db1-af02-83638d98dedb | checkpoint | Product Clearly Labelled
8ec4dfc1-39ec-4a5b-a907-bf0c45cf6aa3 | checkpoint | Storage as per Approved Temporary Works Drawings
1c6741bd-fcac-481f-a4e5-41e6589f31b4 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
6abaf03d-25a4-41c3-b97a-395635d169c2 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
6a8e174c-a418-4641-ac99-c2fac727efad | checkpoint | Specified Finish Achieved
4bf3e3db-fd29-4bdc-96ae-c5294428a0fb | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
bb268dc2-44c8-4263-83c3-542b007e2fb5 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
8fd36aab-6ea4-40e5-b033-d238113b99b4 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and atleast 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
4df60c00-ac95-4019-88fc-9a29543f59fd | checkpoint | Temperature Logging Completed and Conforming. Attach Results
0cbbc555-4bed-468b-84ca-2c3b0597d9df | section | Any Defect Identified
702adb54-49d1-4306-94ef-8733fcc20e95 | checkpoint | Punchlist Completed
85c4b5f5-d86f-449c-bc4e-e34035c90285 | checkpoint | Repairs Required (if applicable)
fad2c4ec-b879-475e-bb63-ef1e74f395c9 | checkpoint | Repairs Completed as per approved WMS (if applicable)
1b037c1a-2c7c-4b13-8d1c-b8019935dd4c | checkpoint | Crack Map Completed
270cb206-9449-46ca-a543-0533d1f12960 | checkpoint | Any NCR Required (if applicable)
a2e74dae-2b20-41de-8310-4f3d1d0ca216 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
e107b49f-8160-4a82-b014-ab3f6c1ff356 | section | As-Built Drawings
62285be5-5bf4-43f2-802f-edb40755a553 | checkpoint | As-Built Drawings Completed, Stamped and Attached
13a76684-045a-421d-9480-a222be65fa8a | section | Concrete Strength Test Report
af582ec2-7c4a-4226-a708-17e7163bde57 | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
165d8127-2c4c-41f9-a8e1-f533dd46d7a8 | section | Transportation Requirements
cefcfc5a-07a3-4101-a5dd-0dc76668b0cf | checkpoint | Certificate of Conformance
fc6ad1a1-c702-4cd2-a862-0682101fe2cb | checkpoint | Inspection Release Certificate
e50a4542-d84d-4747-b707-b24e22793c58 | checkpoint | Delivery Notes
8c770a8a-cc1c-4a3d-83e6-f99ffeb47209 | checkpoint | Delivery Docket
c3b561be-1cb7-4021-a965-046b1ee6dcf6 | section | Final Acceptance
a547fa7e-3852-4c99-8c52-c794dc7cd9dc | checkpoint | Completed by
b59d38e1-f716-4876-a229-11fd7603986e | checkpoint | Reviewed by
058211e2-f32b-46e4-bc02-50689ac9fcb6 | signoff | INTERNAL HOLD POINT
e4c649aa-0101-4290-867d-46188fd20e66 | checkpoint | Client Representative (if applicable)
2aa3b08c-d082-4553-ae2a-882be057c4d3 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v3) |  | Byford U-Beam Stage-1 Casting
4281b298-bd34-4e54-89a1-cbc4413c950d | section | Pre-Pour Checklist
9668efbc-810f-44a7-84bc-eabc83eb3727 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
41f392ec-44d8-4944-a67e-ddfafce4b221 | checkpoint | Shop Drawings approved for Works
1cbf625b-a062-4984-bf3f-682e24e8b45c | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
41908df0-f25f-499b-9f55-3187f2d936e9 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
cededb35-6b0b-4970-8cdf-ade8870538ff | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
8cdf4d82-129e-43fc-81cd-a413426ce55c | checkpoint | Detailed inspection of Mould and cage
51759b13-ca00-4cd1-a99b-568b75597afb | checkpoint | Cover maintained and within tolerance
fcce8728-c53f-4842-8304-eb2db0b6027a | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
b2243ff0-aa7f-456c-a4f0-0f99395e482e | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
72713cdf-bda9-4c90-b705-56527f44d5b7 | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
f635d75a-0c6c-45bb-8358-c3e1a734787f | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
b3f7d55b-7d49-4484-853e-34f1063906d5 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
a3ae3a3c-d661-4676-af27-ebaf2747e222 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
087f93bd-0273-4ae0-b13b-de57af06254c | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
8e410c08-2770-4047-b95c-e31738112a1b | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
e0c54e09-5e06-4966-ab21-fe5ce0a4e91d | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
c25e9ba7-52e8-43ee-b392-1e87cb92e02e | checkpoint | Stressing Records subject to Client Review
4f182b3a-482f-4710-8715-ed4aa24d1b45 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
05192cba-ee3f-40f0-8e01-609573b3300a | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
fa511556-c928-4d92-9790-d254d366e47d | checkpoint | All Cooling tubes installed as per drawings
95c26491-aaae-46d8-9bb3-086533197839 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
2b47f116-eaef-455a-bf48-cd52f5c0cb17 | checkpoint | QA Engineer Check Completed by
f6653d57-3309-439f-8af9-d0cfc6012a01 | checkpoint | Client Inspector (if present)
37f2b377-0c68-4af2-8355-82cf1b311775 | section | Supervisor Release
d1a2d56d-d83e-4064-bb2b-e18e85719782 | checkpoint | Supervisor Release to Engineering Team
59d436cc-3995-4a4c-93f9-f3d199e0f5a9 | section | Casting Checklist
64ab27c5-534e-4ae1-98fe-38bdc33019fa | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
14c791ae-460e-46ab-8961-880a1c4ef008 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
841a1f73-1848-431d-b842-4e714acbdf61 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
aa0b87d1-3fa7-49c2-b619-0d21716f9764 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
b9682912-9e7f-4048-957b-606b7180dfee | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
92f20cd1-b672-4973-b894-0c389868b651 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
1b5f9956-4ad7-404f-8d4a-2743250e8281 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
4d76ab10-311a-40b3-bc26-8076909d3117 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
a2135ece-be25-4e38-a16c-2daafdd371ed | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
16e738f4-de42-4329-851c-90010d1d76bb | checkpoint | Concrete Placed within allowable time from Batching Plant
a192f73f-c41c-4d8f-b2b2-90a54680f8b6 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
0226e1ef-540f-4fb2-87fb-78cab39edf5e | checkpoint | Required Finish Applied as per Drawings
02c6ba6b-5d52-4965-a36f-14304132c030 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
ddeca55e-2af1-47dd-bae9-72bf005206db | checkpoint | Concrete Covered Overnight
46b8c0e3-28d2-467a-b857-273e2f13013e | checkpoint | Cylinders Stored next to Bed
d5d937ce-a679-44ea-b7d0-6b6dad45381b | section | Stripping Checklist
6ea1eab0-be1f-4a00-8303-4d241ec0241b | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
c5c3ed6b-6594-4367-bcba-fff95855c3c1 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
7f9a1e4b-9b71-45c7-8f42-835ffea3138d | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
d0b81178-c4c7-42ea-9c6c-1e567e6567fc | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
9b52489d-648f-45e6-8bfd-3d9eabb60342 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
1cfcb858-786d-455f-84b6-7736e6620874 | checkpoint | Lifted and Handled as per Drawings
33c3b8b8-2fed-4123-983f-426801064d69 | checkpoint | Product Clearly Labelled
21df6bee-bcc3-4408-b74a-76e9ac77e31e | checkpoint | Storage as per Approved Temporary Works Drawings
8a43a89a-df13-4d04-9bf7-fdd52fab0f91 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature does not exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
ea69e858-5d4a-405d-b643-7a6598b3668d | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
dd6b8636-fd34-44fc-bcf1-39c5afe19a76 | checkpoint | Specified Finish Achieved
95d657c8-c0cb-4997-a675-f3222f560a51 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
709ff950-4074-48b9-8ce0-1657f15f3275 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
50193ab6-9b39-4535-a3a7-9d5160c6ebcb | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
ed90e5e8-c45d-4c3d-8295-0d327ed78075 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
24c0d1db-00eb-4cda-aac7-3d139cff5486 | section | Any Defect Identified
e9cf81a4-c4ca-4065-80a8-291970086971 | checkpoint | Punchlist Completed
b3e70e5a-ed18-4e7e-ad3d-60a38c3b0d6a | checkpoint | Repairs Required (if applicable)
48104fd0-d05d-42f8-abdd-e809a000866d | checkpoint | Repairs Completed as per approved WMS (if applicable)
406fdc3a-392b-4b21-9f22-2dc812207034 | checkpoint | Crack Map Completed
08117b7e-cf8e-4ca8-b7c9-c0f621acdd22 | checkpoint | Any NCR Required (if applicable)
9598be9d-e30d-459a-a57c-7eb96472dbc4 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
18e8feeb-2ad1-4807-9094-f9ebc2f0babd | section | As-Built Drawings
0bb701f7-a914-4ce4-aa43-31936c9618da | checkpoint | As-Built Drawings Completed, Stamped and Attached
95ba54b0-a603-444a-9903-b95abb9939c4 | section | Concrete Strength Test Report
de667db7-4773-4ca4-9539-03c883e96874 | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
6c2af489-fca9-47ad-a1dd-14be0bc9c0ee | section | Transportation Requirements
aff1d30e-b2a5-4c7b-bd73-7413628329a2 | checkpoint | Certificate of Conformance
3d8ae805-4e3e-4316-a3c5-9e7fc549ad90 | checkpoint | Inspection Release Certificate
b8ce5777-9b8b-444a-8a60-a0e9a2d53379 | checkpoint | Delivery Notes
56a1118a-6dda-48e6-8eba-c158ce14a283 | checkpoint | Delivery Docket
10f0bc55-2154-4c40-ba94-2b5948a03232 | section | Final Acceptance
b64ecaca-17b4-464a-bd9c-dfeb93b8affc | checkpoint | Completed by
d1af3d35-1f19-4e55-8000-3c0c0977c9e1 | checkpoint | Reviewed by
a0bb38d3-0978-4e36-9f5d-0d23e60ffb4f | signoff | INTERNAL HOLD POINT
d9e43b73-2527-4b6a-a4f7-5467c6d9a2fe | checkpoint | Client Representative (if applicable)
ea7abaf4-6151-4d8d-a065-065ff82ca70b | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v4) |  | Byford U-Beam Stage-1 Casting
16744d98-b285-420b-9065-47c700dc7438 | section | Pre-Pour Checklist
f5b48e28-a0c2-47ce-b5e8-0e66dff49d78 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
b55ce491-ef97-44a4-ae95-123553c193bd | checkpoint | Shop Drawings approved for Works
dd3b7a3f-a806-49d4-962d-d3f7b8972b01 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
bdff19b4-abb6-4306-a298-5cb12ecae2f6 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
a34f9105-a8b0-4a2d-8b1a-eb0e177a0002 | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
0f144171-3f31-428c-acbd-88d2dedc565c | checkpoint | Detailed inspection of Mould and cage
a4978289-48fb-4235-ab9a-e66a1ccaa206 | checkpoint | Cover maintained and within tolerance
b7db9148-7875-44ec-a21f-65d77946a27b | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
25b391f8-f583-4082-b4b5-e91035552263 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
40c38cc9-6bf2-4c3a-9662-187771a9d2ad | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
ca67e1ab-63f8-486c-9a56-c42ca5c05732 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
32e58ca2-3b89-49eb-bb6b-5be45dc35486 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
2608413e-b9c9-4df2-80ef-829e9d3760a8 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
8840b824-96cd-4a49-bd7d-12c78bf0e39c | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
1b4ccfe9-9695-4de2-b19c-8c314b827d05 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
efeab47b-3e26-49fa-aba3-03364b131f13 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
f7faf14e-696b-4fac-82be-29ba00ecd303 | checkpoint | Stressing Records subject to Client Review
0a08af7d-ceca-47f5-a1e8-ef81cb4657d0 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
65d3dea5-0b68-4dec-8ea5-b73a6c614af7 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
ecd86088-6def-4d65-991d-061c073288c6 | checkpoint | All Cooling tubes installed as per drawings
35c4f241-a07c-47cc-ba50-a7d404889661 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
cd1ca22c-6265-4ad5-929d-4bd9b02e017a | checkpoint | QA Engineer Check Completed by
f1babe87-b99a-4152-aa1e-edeb9c06a2d3 | checkpoint | Client Inspector (if present)
4c6185c3-0abd-4997-b55a-6f82c25b6af1 | section | Supervisor Release
1cd6902c-1bcc-4b38-aee7-af81bb41f1dc | checkpoint | Supervisor Release to Engineering Team
f7b2cda9-c085-401b-a272-7bf3a5ab19e8 | section | Casting Checklist
3088baa5-cb3e-471d-889c-6cf4a22151aa | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
771b296c-ecce-4da9-9056-aafd535c2fc6 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
3fc36ceb-6b13-4ac2-a207-5c1d2c575136 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
262bde5f-953d-4a45-9e5c-55ca5cdf4540 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
3fda9a15-af15-42d0-b5de-9be7a2022606 | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
604c77b3-fd68-44cd-9fbb-b1b6e666576a | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
82111a96-f817-4618-9ed1-558ab4b30057 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
7f377b6c-fb22-42ee-8548-d71de53fc939 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
85017a60-1a9e-4844-b3dd-6ddf6ca9fd0f | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
30d68a63-ac72-456f-870b-15700436342c | checkpoint | Concrete Placed within allowable time from Batching Plant
eec992d3-718d-4ad1-8b3f-1e6a5c08fdbe | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
6c900237-0d85-4213-a187-b7c9ece0ceda | checkpoint | Required Finish Applied as per Drawings
dc513e48-ef09-4f9a-aa52-0fc68070c9a3 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
2cab1da8-1edd-4b80-b46e-d4a91cd343e9 | checkpoint | Concrete Covered Overnight
70ddb220-7477-4d19-8168-580e449ed118 | checkpoint | Cylinders Stored next to Bed
4cecd54f-e03a-4d1c-ae4a-1c4ad500c006 | section | Stripping Checklist
d33e9883-9d01-4a60-8b32-b89ab86ab902 | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
fdf43226-18d1-4188-b6c5-dbb3e80a321d | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
31336773-930c-4c36-ae21-09e4c90cd2d5 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
a831a68d-7f42-45a9-adef-4881c16cec44 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
47538485-9689-4600-9de9-2d2241dedd32 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
0ca63518-5f67-4ac4-aa61-5d1c9af87706 | checkpoint | Lifted and Handled as per Drawings
f4e59221-fbb5-497d-8f31-aaa1ab935fd3 | checkpoint | Product Clearly Labelled
72381f9c-b758-4c25-a4a8-deb69f65bd45 | checkpoint | Storage as per Approved Temporary Works Drawings
22b190a5-1bb7-441a-93ad-91a36b30dbc3 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
42dc2ba1-fb55-4feb-b866-71e0c68b7e00 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
94e5de1d-3ea3-40a8-afa5-06849c50f57c | checkpoint | Specified Finish Achieved
61c9b91a-d98d-49c7-a0ad-f8897551805e | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
7644c8ca-b857-4add-9f63-3b34a2a19339 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
a7bb909f-701d-469f-84bc-c0c44cd42f6f | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
fab0f99a-4d67-4aab-be8a-423264d4a5f2 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
fccf01f8-877d-40f7-a1ee-44f898612ab5 | section | Any Defect Identified
31a2d2c5-c353-435d-9df5-8d4112a11529 | checkpoint | Punchlist Completed
916cca62-42e1-4ea9-bf3e-458385dde062 | checkpoint | Repairs Required (if applicable)
3abffb29-6b96-4f38-8081-d5db3a18c03f | checkpoint | Repairs Completed as per approved WMS (if applicable)
6da2e659-ca7a-4a0a-bca0-f8cc737bd8f4 | checkpoint | Crack Map Completed
63acf965-5557-4e8a-aa0d-84ed1d7e1f1f | checkpoint | Any NCR Required (if applicable)
d880e160-757c-482d-b392-cd0d07b9a42b | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
0fd6addf-cf47-4913-a965-abb131e4f904 | section | As-Built Drawings
2d9175ce-be55-429c-ab3d-c2f5dc5a3c0b | checkpoint | As-Built Drawings Completed, Stamped and Attached
84689bb3-0a27-4864-a516-2ce58c45ca9a | section | Concrete Strength Test Report
065ba022-a1ed-407a-9f35-17d02d458bba | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
c35fe3e1-f447-47fb-9901-2eb20cdbf337 | section | Transportation Requirements
dba9a7a1-70ea-4bd8-b328-23a0c47eeebd | checkpoint | Certificate of Conformance
b43cc1a9-f1f4-4434-a26d-1c6b5b7ffa09 | checkpoint | Inspection Release Certificate
aed2e077-72cd-4597-b05a-afb2fe76a622 | checkpoint | Delivery Notes
7dae3aff-29eb-4b8b-9cfd-51745674ec6d | checkpoint | Delivery Docket
8ec676cf-eb95-4214-be38-e9261b72b7c3 | section | Final Acceptance
f544a5f0-f529-4aa9-ae91-f1e85fed8a0d | checkpoint | Completed by
620ea82c-b84f-4d37-85c1-dd91620f4ae9 | checkpoint | Reviewed by
e9f0de51-955e-4e56-9b38-7151978ae3ed | signoff | INTERNAL HOLD POINT
ea6cecd7-e6a2-4296-9ceb-71277918fe6e | checkpoint | Client Representative (if applicable)
62bdad12-82ae-4271-bc89-2debeb3addae | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v5) |  | Byford U-Beam Stage-1 Casting
1b1b440c-5a18-4c57-ac0c-9074e13c2685 | section | Pre-Pour Checklist
1a291fad-9b7e-4618-93a0-1bfff11e0544 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
d3cf1fd0-2266-4186-8fc0-58b4987b4fac | checkpoint | Shop Drawings approved for Works
739089d1-a6b3-44ac-9d28-2f1b65c29528 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
381a28be-d28b-4a87-ba58-31b91f2e8b80 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
4535edca-caae-4978-8c60-dbbff0de524c | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
f155caf0-47fc-470f-9baf-9a019c6899a8 | checkpoint | Detailed inspection of Mould and cage
da31a7c2-134a-413f-a2dc-ae40b0f9267d | checkpoint | Cover maintained and within tolerance
2fbaa658-283d-4ed1-a0ca-623c94510297 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
89d741db-ee2e-4efe-849d-fde648c3a13e | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
7b5d9be1-9495-45a9-b36e-5e5fce14e7c3 | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
4226ad74-c696-4624-991e-647aa6d7c7da | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
b1bd01ee-bf01-4eb3-ba7d-f5d47d3d7c8c | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
338d7c9a-0810-491e-9c4f-a41be850ca84 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
77bdb0e3-fe34-4455-94c0-efa27d7e29b1 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
56991184-d5e9-49e0-95db-6c256eeaf4b1 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
b64daf8c-ebe9-4874-992a-f13a7a37a552 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangementr verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Mutli-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
005796b5-741c-4337-93c9-5aee5626bd77 | checkpoint | Stressing Records subject to Client Review
f60970e2-4f62-4e06-a93e-5565410b5e7e | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
e350b963-0f9a-4eb6-a471-9743147f3667 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
f808d145-74cf-4e61-898a-17a1ee05744e | checkpoint | All Cooling tubes installed as per drawings
142b530e-bd05-4998-b414-b53e9b1c6b2e | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
2b394658-1394-47f6-a143-ee65ca36e942 | checkpoint | QA Engineer Check Completed by
4f178805-d844-4aef-a933-c5ab5b3820ee | checkpoint | Client Inspector (if present)
23b09e8e-9587-48c7-9605-dede3893246c | section | Supervisor Release
14e8143e-2cf8-4ba9-a114-6f4975f44eca | checkpoint | Supervisor Release to Engineering Team
57c80b52-9587-441d-9c29-a0fffe4839bd | section | Casting Checklist
d18bfcb0-a595-4398-952b-bef09b142afa | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
f623377d-7c46-4fff-8042-72898547e344 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
7ff25190-997d-44f2-832a-f6176a132e71 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
56660cea-363a-4f7e-b6b9-891127611966 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
fee5efeb-4c2b-4be2-a739-baf477657e8e | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
f93f04ae-c1ef-4d28-983f-2c9a40a1d763 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
d29704c1-9f32-4d81-9166-559caeebe8fd | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
b1bd22bf-c05b-4c5e-8cdb-32f85e4d057e | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
b32bea16-6c2a-40d5-a463-016508daeaec | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
d25bf2ad-1b30-40ef-81ae-0f4dbef15987 | checkpoint | Concrete Placed within allowable time from Batching Plant
1dc102f4-3968-458f-9963-bb68e0952d9d | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
06ea2e2f-31cd-42da-9d33-9e46f81443c5 | checkpoint | Required Finish Applied as per Drawings
9f3d66be-46f7-4975-b47b-3a94d96ca509 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
fe3ae268-bfee-462e-9455-bcf30aa58f80 | checkpoint | Concrete Covered Overnight
17695593-bee1-47e9-a6a8-b7dc84d3351a | checkpoint | Cylinders Stored next to Bed
999aa7e6-348d-4e6f-b273-a9bbccf703ba | section | Stripping Checklist
a46326b8-96e0-4380-8a0a-f1e3be38c99b | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
3c46ded3-5a0b-4f7f-b2d8-6d0869acb1d1 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
2b496297-1898-402a-85c4-689c83056e8f | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
cd1eaf01-af71-4cd8-851e-410233c03dde | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
f6be81c8-a9c5-4a1c-a26e-f95291e3728b | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
0dbe3b4c-238d-47ed-8511-6f9dfbb9f1b6 | checkpoint | Lifted and Handled as per Drawings
0928680d-0759-40f9-b2e7-9b56d224f006 | checkpoint | Product Clearly Labelled
4b3fe9dd-cbaa-4da3-8677-502b75643a21 | checkpoint | Storage as per Approved Temporary Works Drawings
f4488890-d2ae-47ae-8299-bc8de095c648 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
0e83ccb2-f70b-447e-b184-83f7defa145a | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
aacdfc7b-72d3-4647-be28-a66f4c392a6a | checkpoint | Specified Finish Achieved
6f140038-ed3a-4858-aa34-c8fd141f5f78 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
156dede2-65c2-4f2e-be8a-7aa10668d8cb | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
a5c85fa1-d77c-4833-a019-eb75dd874066 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
6c3c734d-65f9-4d56-9e67-35a97c1c5745 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
51c333a4-60d9-4e7e-94fe-c5972f83ce35 | section | Any Defect Identified
3da307c5-9645-4b67-b287-d57ca2c30d45 | checkpoint | Punchlist Completed
0bac4e6b-e34b-4811-bf84-0c8e1b3eb4de | checkpoint | Repairs Required (if applicable)
5673237c-27d7-48ad-942b-095455997022 | checkpoint | Repairs Completed as per approved WMS (if applicable)
7e51243d-e785-4f77-98a0-c71fd631eb49 | checkpoint | Crack Map Completed
f3756da5-1b03-4b3f-a97f-5c03fc33f5ce | checkpoint | Any NCR Required (if applicable)
bead0ee9-bbeb-4f08-abfe-2e807dd4bb44 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
cbfbea84-5a2c-421e-9fe4-2182dbad39ef | section | As-Built Drawings
54cfb20e-db41-4029-8e55-03cef3c531ef | checkpoint | As-Built Drawings Completed, Stamped and Attached
61cd656f-f572-4033-840a-7ff10581198b | section | Concrete Strength Test Report
0af5ff20-170d-4d54-8029-e08e72becd2f | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
b7627a95-520e-4eed-bf3c-55aaf1384183 | section | Transportation Requirements
ce2a2392-113f-4db3-a5bd-d1b227b01e00 | checkpoint | Certificate of Conformance
434267a4-6b35-4c32-8ceb-89d80041ae1a | checkpoint | Inspection Release Certificate
451c2fcf-bd49-4455-86fb-61cad6441e57 | checkpoint | Delivery Notes
e052749c-63fc-448a-9b7d-cddd9c5cc509 | checkpoint | Delivery Docket
e228b169-eaf2-4304-92dc-c8d273bc58be | section | Final Acceptance
1f179a7f-acb5-47b8-bca4-922a73bc5cfe | checkpoint | Completed by
10648b87-b6ba-471d-b585-ef05a81061f0 | checkpoint | Reviewed by
c1a50fc0-0876-4647-a1b5-af5bde8e2422 | signoff | INTERNAL HOLD POINT
8a87bf67-0165-4c15-9129-339ec8ac9e56 | checkpoint | Client Representative (if applicable)
f97c04cb-e84f-4111-a04a-15a36666c047 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v6) |  | Byford U-Beam Stage-1 Casting
5ecc6c1c-8604-488b-b893-7ee4611f2848 | section | Pre-Pour Checklist
9f9daa56-af15-4fb7-b0e9-d9ae33de7925 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
5d540e87-eab5-441c-a2be-0cc9c10e0378 | checkpoint | Shop Drawings approved for Works
414ba0cf-6fb0-46ff-9269-ddd0e826dc65 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
0453c80c-e6dd-4dcb-b765-55d9ca47a5d0 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
5644c2c3-e7c8-46f8-9b92-f2c0b489cde8 | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
911b3c55-93ce-4666-9242-57c7d7d1f5e9 | checkpoint | Detailed inspection of Mould and cage
0f06d059-05c9-4698-9bcb-f137be4f364e | checkpoint | Cover maintained and within tolerance
dcd24123-1050-49d1-9d9a-81a23c5504e1 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
99195206-d988-4893-8247-217bfbf58f54 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
93c511a8-fbf5-410a-9140-f0ed1b39423d | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
d4ccbce2-2833-4857-aa6c-14b718996fa9 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
4a89e171-783f-4371-9df3-fcc417dcd367 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
5cf50ae2-4781-49dc-ba8b-9675c339f936 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
5327f771-0b17-4cb2-b8b1-d258c7957e46 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
9bb7fc88-b26c-4a88-b866-be7753bca25e | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
e2b78500-542c-4774-bbf6-643274404f5a | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
4785fb5c-fcdd-4346-9bc4-7e4d0890008d | checkpoint | Stressing Records subject to Client Review
c6d4f67b-a6a4-4415-b434-88dcd96b26de | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
fc283d20-3091-490b-bd9c-09cbcfb3d9cf | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
9cdde248-7f53-4e43-951b-81e15a7f707c | checkpoint | All Cooling tubes installed as per drawings
d5311910-5419-4bc5-9be4-bf78cb84a27b | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
cd28d381-d3c5-4247-be4b-16121985c662 | checkpoint | QA Engineer Check Completed by
733e0fcc-dd5b-4e27-99de-d6d96f6044b3 | checkpoint | Client Inspector (if present)
a3755b3d-192a-41b6-84f3-aee03505bdc9 | section | Supervisor Release
d1e2e20f-c83c-43c7-ad1f-f188bd65747a | checkpoint | Supervisor Release to Engineering Team
cccf3d2b-4143-430c-af0d-95b0ae3ce4fa | section | Casting Checklist
9c449893-f5be-46ed-b61e-44ab69dd00f2 | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
db624138-0225-4c2a-8c59-9b127659d4a5 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
d9735afd-36b7-4d6b-bea1-4895a5eb0717 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
7a4ccadc-a99b-4a0d-8b5f-5355224b413d | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
cccd79fe-e913-425a-8dc9-b1a4d1650f69 | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
e0ea1b75-9977-427f-8dfd-79c774954f93 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
839c01e8-6987-470b-91bc-6a5aa2e2c0fb | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
6f3f0c7a-574f-4fa3-ae51-ea9b7fc86358 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
08fecb49-d7ee-4cc0-9ec3-6a61a9ba0283 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
a0b025e7-1918-445f-a8b6-abd615b25434 | checkpoint | Concrete Placed within allowable time from Batching Plant
0cf6a427-3c26-4350-ace5-6a2b3659f93d | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
fbb978b0-2e8c-415a-bd95-72daba6e3024 | checkpoint | Required Finish Applied as per Drawings
197f653f-2d71-46c4-898a-2c7edf281f84 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
47801c60-fdda-40b6-a301-68215f3ac1db | checkpoint | Concrete Covered Overnight
1bc262ec-3379-45bc-9e00-366bbb73fde6 | checkpoint | Cylinders Stored next to Bed
44f764bb-6392-4359-8b29-f82646a44088 | section | Stripping Checklist
664561d6-82f6-4179-bc48-c14ce75d9d43 | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
cae13cb1-3c20-46bc-ba7d-bd9c1e6baf99 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
5a499d6a-05e5-42a0-86b6-04ca46735e01 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
b860d7bc-e7e6-4355-b381-b154649a5d25 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
1c6c5b72-2b95-49bf-9397-f269c2dc04f7 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
68e06c43-603f-4e1d-a545-623e6a08ec58 | checkpoint | Lifted and Handled as per Drawings
7aea5fb5-ead9-4ecf-b114-59df6dad46fe | checkpoint | Product Clearly Labelled
2532c7f6-a9f7-4571-a49d-1b86aa1b3a82 | checkpoint | Storage as per Approved Temporary Works Drawings
cf6edfaf-eca0-432b-9a47-c6c950d6e97b | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
37df03c0-f279-4d0c-98c7-f956ac3eecf4 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
726e2bb0-13f5-4cc5-b88a-3b9f8348c5a1 | checkpoint | Specified Finish Achieved
43bdece9-ca5f-478a-96e7-f95e01cbc9ee | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
09838d21-9bce-4ef6-9568-6032533f9391 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire (Attach Pictures)
833743b2-cf24-45a0-8ee5-7557cd9a9e23 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and atleast 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
dad62a14-18e5-4d8f-aff6-7ab888755899 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
03b65f75-7bb0-4705-8b96-f20244bdb3a8 | section | Any Defect Identified
5281d86a-d58b-4c3e-a31c-8a88a4998da5 | checkpoint | Punchlist Completed
38c96f34-1901-4f6b-a40f-46985c672747 | checkpoint | Repairs Required (if applicable)
14020edc-6c16-4620-93e3-6e054959d1c9 | checkpoint | Repairs Completed as per approved WMS (if applicable)
b0fc0a74-135a-4bcd-8128-323d5e5c84e8 | checkpoint | Crack Map Completed
c166e15a-9dc8-4c48-9ed8-46596bd63a55 | checkpoint | Any NCR Required (if applicable)
d12433c7-9ac9-4834-9f0b-89c98c65e4a9 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
fc222699-83c8-4e50-9ba6-e5746490d2bf | section | As-Built Drawings
20918cf1-8b82-447d-ba73-21148504474c | checkpoint | As-Built Drawings Completed, Stamped and Attached
36d88ad5-cae2-49e9-bff8-9e7be7dc6b7d | section | Concrete Strength Test Report
1559bdcb-1637-44ea-b976-e0cd99211bf5 | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
8b1a3ca2-45cc-4a80-b03a-a4b89b7ff9b6 | section | Transportation Requirements
18010854-bc98-4fbc-9e07-2e68eae08397 | checkpoint | Certificate of Conformance
056f9500-9f6a-492e-a024-80b12bec9e38 | checkpoint | Inspection Release Certificate
3b346d18-e6f6-4829-9639-1ee26a3e03d0 | checkpoint | Delivery Notes
0595c502-0551-4a40-a3a9-00f5ae4d1d3a | checkpoint | Delivery Docket
a7861972-4389-466d-b03a-729d36c2b0ee | section | Final Acceptance
8a4f3352-2178-482c-9694-cc3627eef3e5 | checkpoint | Completed by
be4d2b44-0315-44e5-81ca-0954ad3e460c | checkpoint | Reviewed by
8cb318d8-a2fb-4fb9-94dd-26937ed62a7c | signoff | INTERNAL HOLD POINT
8061f469-6d04-4c41-a87d-23a49468f227 | checkpoint | Client Representative (if applicable)
98f82a63-c6bb-4343-8f90-38870db25e05 | checklist | Ω (Deprecated) Byford U-Beam Stage-2 Casting Checklist (old version, v1) |  | Byford U-Beam Stage-2 Casting Checklist
68e3499e-4ec3-4ceb-a224-7c1e41b0083a | section | Pre-Pour Checklist
6eefdc89-3e7d-4048-80d9-f15ef1ebd19e | checkpoint-no-value | Details
1233fbbe-8a90-5695-bf6b-28144e51953d | textbox | Cast Number
d6de33d6-1d6a-59cc-aab5-58e1f9ee90b2 | textbox | Beam Number and Orientation
acb384d1-e98c-5a02-9f7c-1128a2c5f72b | textbox | End Diaphragm
ac5291bc-9b21-45c7-8d84-994c2fdbf8f2 | checkpoint | Shop Drawings approved for Works
2016a2e5-4c55-4309-b921-d8d41e29515c | checkpoint | Mould and Sacrificial formwork Dimensions are within Shop Drawings Tolerance
4c1b674a-8bd8-50e8-959b-bec5d6dadc3e | note | Length
822d1104-8a27-5ed9-980e-888b7bf6caaf | note | Width
830ee2ae-8950-5298-a691-e9600cf10537 | note | Height
bab4373d-5276-50ed-954e-45ea96aec8c3 | note | Straightness
b82d264a-3d32-5473-8664-32a90bab9013 | note | Cross-section
d17caf36-2f56-45aa-8839-eaab07f481c9 | checkpoint | Condeck Surface Checked
a0273126-e254-5157-8d98-f128fa5c6b52 | note | Cleaned
9bb4e700-f5d2-5e02-883e-e5072418e64b | note | Sealed
3ec0752e-0691-5a4f-86ac-8445eadef662 | note | Oiled
8cd57883-99a0-42f8-ad58-66984ad264eb | checkpoint | Reinforcement in Accordance with Drawings
800fadac-1be9-5858-94f4-5d4746740084 | note | Reinforcement size
0f320d4a-3d88-5e76-9d42-76621d58e218 | note | Lap Length
f61d890c-4ba6-5c8f-bcd8-10b22c2f1c07 | note | Splicing
62881279-32c4-593b-b849-3eefda69eb96 | note | Bar Chairs
b31c7adc-8ff0-5948-b00d-593cf326b1e2 | textbox | Stitch pour Reinforcement lapping bars spacing maintained and template plate installed
12cb8723-6db8-5a57-b575-655471779936 | textbox | Blockout recess around lifting Hoops
e6843dea-b3b0-4e97-9a47-a3efa46611d0 | checkpoint | Detailed inspection of Mould and cage
eaa4facd-1d2f-4b08-80e6-3990a928d2c8 | checkpoint | Condeck (Top Slab) - Verify all brackets fixed at slab thickening
b6a05ddc-b33c-4577-9ddc-3cc72a035764 | checkpoint | Cover maintained and within tolerance
8529a34d-76d8-4f31-85db-6967eb88a0b0 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
9f215da9-19e9-5047-a80a-c229bb1325f1 | textbox | Ferrules M16x96 (Handrails)
8d90112a-ec60-5a67-a2f3-d316d5261991 | textbox | Ferrules M10x45 (Expansion Joint Cover)
d1b00e18-ceba-57fe-9b5e-6d4e7db97304 | textbox | Ferrules M16x45 (Ladder)
49d2450b-c55f-5f52-8737-b23eef564e73 | textbox | Ferrules (Other type, specify)
7b93bdc5-d314-438a-a850-e6d332b3e4f6 | checkpoint | All Stainless Items are installed in accordance with Drawings
1e328254-d184-5f54-943a-e1976e1eb331 | textbox | Other type, specify
848bea4a-5fd2-4663-ae39-9d8132912600 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
87db205a-a14e-5be0-b795-5d53984ab585 | textbox | Earthing Terminals (FDB-16)
09abc58f-8a0f-5f60-96e2-32bee1276a84 | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
a020b351-e865-5d5e-a4b5-b441cabfd625 | textbox | <20 mOhm across cage Length
4ef34acd-9e10-5711-9e70-4735a0a2bbd0 | textbox | Checklist Completed (North & South) (attach results)
64866f6c-d90f-4fa3-a3b6-3e21dbf3f2aa | checkpoint | All Temperature Loggers are installed as per Approved WMS
7f2ff394-48d1-5d12-a9a5-88aa58174bf6 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
98201a77-f60d-42e1-aeac-0e247f07a663 | checkpoint | All Cooling tubes installed as per drawings
abc7bb6b-54c6-46e9-9079-dd2011873c1d | checkpoint | QA Engineer Check Completed by
13c337bd-ac29-48ff-981d-c8f0c3da8696 | checkpoint | Client Inspector (if present)
641990f8-5fbf-49c7-9db8-78772196809d | section | Supervisor Release
270e0471-ddaa-4fea-bf93-bc6830d4ef5d | checkpoint | Supervisor Release to Engineering Team
63475a55-b247-4c9f-a6af-8f9688b42a90 | section | Casting Checklist
88d83b51-14fd-4dd9-888e-f52da4ab48e4 | checkpoint | Casting Information
1a647942-8258-57e6-b6ff-621161085e77 | textbox | Cast Date
fecc0c3a-5096-4881-90b6-cccae4487b09 | checkpoint | Concrete Delivery Dockets
d392af45-5195-5119-892d-80cfe0b6a20e | textbox | Concrete Delivery Dockets (list all)
c64283ea-038c-4d06-8fc5-48ddcb739795 | checkpoint | Total Concrete Volume
60fa028a-b7ea-54d1-954a-1213bd11e8e1 | textbox | Volume (m3)
39897cd6-ff27-4861-8aee-a711a8c2cbdc | checkpoint | Mix Design Verified
f8a395fa-8391-5639-a09e-c5241875a63d | textbox | Specify mix used
eba528a8-7ff1-4e49-aeee-27a8ef33b623 | checkpoint | Ambient Temperature within Limits
a4f51cbb-ff6a-5071-bca5-5481459038f1 | note | max 38°C
2002f385-03af-43f4-858e-f106bb05accb | checkpoint | Concrete Temperature
897bf355-b709-54f5-9399-3a7efa254455 | note | max 32°C
d2f2f96e-3a73-4cbf-a3b8-a4fa69c044d7 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
8c53b798-3f67-45b1-a665-758c3169c99f | checkpoint | Trucks Tested for strength
1db14c07-5972-5f2c-9497-617ae1c2a547 | textbox | Test Report Reference Number (list all)
4b7e892d-b8ce-4bb5-8a6e-9496502a8a60 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
b59b4ded-7fa0-4694-a5a9-b00f8590f345 | checkpoint | Concrete Placed within allowable time from Batching Plant
319cc792-6968-4cc3-b6c5-a99f41eb2d97 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
718d8a30-99dd-4f73-83ac-380c831d2579 | checkpoint | Required Finish Applied as per Drawings
292f6f49-a744-4a83-8f6e-8a8a44f1fbc0 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
413d70ce-bd3e-463b-afc4-419b411a10de | checkpoint | Concrete Covered Overnight
516f68de-00f2-4e61-8f20-57944d7a8169 | checkpoint | Cylinders Stored next to Bed
031a6c14-2f56-4f87-a028-eff4d714973f | section | Stripping Checklist
076e0db6-0059-4127-b3ab-4f013bf30fb2 | checkpoint | Date Stripped
901c78d2-ef96-5ae6-a1f7-9a653c24de1a | textbox | Enter Date
850503af-24ff-4d57-ba84-aaf78a56acc4 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
f0b85fdc-6c4d-511a-a42b-626445232756 | note | Conversion KN to MPa = Reading / 7.851
786038d6-bea8-5d36-850d-c5b0f8eeb594 | note | Stripping strength 20MPa
ab2f98ba-453f-546d-8399-ab6d61235c1c | textbox | Stripping Strength (Stage-2 Casting)
be8099a8-54d6-474a-8ca9-5ab2fc0d7bef | checkpoint | Lifting Strength Achieved
ddd53939-10f1-5062-be90-0c69a5b2b2d6 | note | Lifting strength required for stage 2 casting - 20MPa
990eb32e-733a-5942-8ad7-1dc6175f29d7 | textbox | Specify strength at time of lifting
16864bfc-1338-4dfd-882c-4b69230bc084 | checkpoint | Curing Strength (Stage-2 Casting)
775b182d-e021-55ec-9a45-7abb946c1815 | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
c4a6b006-d64b-56cc-af22-7a32fa98085e | note | Tarped until the curing strength achieved
02c30163-e235-48e7-87f1-1703e463bf18 | checkpoint | Lifted and Handled as per Drawings
bb4a283c-bd7e-475d-a1b7-f3d1aa8f65c6 | checkpoint | Product Clearly Labelled
3aa16a9a-e718-4a6c-a90a-c2b5aee249db | checkpoint | Storage as per Approved Temporary Works Drawings
810abbdd-62e8-4356-bd02-e764a528a4f3 | checkpoint | Secondary Curing as per Approved Methodology
9a1677df-6ab7-45e9-b757-ae5877ee264d | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
df44e42b-2e80-5f94-ac7f-80765b72e6f9 | note | Length
e4265a90-0641-5ae7-9983-17040cae58b3 | note | Width
7bb4ba7f-c14e-56fd-9171-dbeee66caa97 | note | Height
ff36979f-97bd-5709-a920-421e847495e8 | note | Straightness
f932effb-f869-5bc3-b54d-3dc7703f8e53 | note | Cross-section
30ccb5b5-812e-4b9b-8f3b-6c2bfd14644a | checkpoint | Specified Finish Achieved
c35933d3-afe2-483f-8653-4170bdb5ed17 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
a4c9f700-bb5d-5e3a-a5ae-51c28d8141b9 | textbox | Ferrules
3cde73a1-6070-5769-9afb-cb3e15618119 | textbox | Stainless Items
f6ffd1c4-9b9b-50c3-aac9-88cfb320a9fb | textbox | Lifters
8d91365d-45e2-5a6d-abc6-191ce31f5767 | textbox | Blockouts
13bd3877-1b7a-42bf-b918-89927084649f | checkpoint | Post-Pour Works Completed (As Required)
7a542891-b623-52f8-ae88-77c1c09fb89f | textbox | Ferrules are Cleaned and Capped
80630288-7f59-5868-b4d3-3428afa34d9b | textbox | Roughened Surfaces are Greencut
915898d3-a5d9-5e68-9706-7a0fa68a24a2 | textbox | All Miscellaneous Items are Completed
d6e3d8bf-4ab1-4dc9-abd1-2585855323bb | checkpoint | Temperature Logging Completed and Conforming. Attach Results
b27b11ea-6c6b-4acb-8c20-3dbdaad30d3d | section | Any Defect Identified
3b98eaf7-717e-4b08-92e6-2c0f193e079f | checkpoint | Punchlist Completed
802199c4-5558-40fa-a321-79a686c16752 | checkpoint | Repairs Required (if applicable)
8093547a-ee5b-4731-923d-f89189fd48a3 | checkpoint | Repairs Completed as per approved WMS (if applicable)
99cec26b-bb2c-4c06-919d-15ca8569b6d8 | checkpoint | Crack Map Completed
dca1dbb7-0aee-4152-ad0d-39cedf858014 | checkpoint | Any NCR Required (if applicable)
0c873deb-8fee-488b-89cb-f98a99faca72 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
2ab4d46d-a47b-47af-8a0a-812e74c51c85 | section | As-Built Drawings
eb5d1254-5417-4d2b-8863-ea78b86c8750 | checkpoint | As-Built Drawings Completed, Stamped and Attached
f4df64ac-f83e-4122-8da8-59131910cf70 | section | Concrete Strength Test Report
d5a1cee2-30d1-497d-9924-b455d50c06e2 | checkpoint | Concrete Strength Test Report Received
72ed3bf3-f25d-562e-9513-1b400cbb5e33 | textbox | Concrete Test Report
009f2cbd-af76-54bf-99ce-3bcdafdfefd1 | textbox | 7 Day Strength (List all)
bde663bb-3906-572f-9122-80785c06ca94 | textbox | 28 Day Strength (List all)