## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
a0e9b0e9-f145-4563-a445-c31d14db3046 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v1) |  | Byford U-Beam Stage-1 Casting
1b283145-9444-42cc-86d4-7c38d61cc7b4 | section | Pre-Pour Checklist
34eb53e8-3762-4da2-9dd0-3cfa8ec76271 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
bca35014-dcf4-4ce1-886f-9d682980d4ae | checkpoint | Shop Drawings approved for Works
f656237f-1e93-43e5-9e64-2de978e3f465 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
5ced35c8-a6de-4316-abd5-d16386a3e515 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
3e79e8c0-bff8-4b13-8f03-d5c49d5e601a | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
73325ba1-df01-4195-8db7-dec36c028e92 | checkpoint | Detailed inspection of Mould and cage
e24f6dfe-d5f1-4186-a525-d4cc656ec91d | checkpoint | Cover maintained and within tolerance
4b276b4f-1b04-48ea-a1e5-e45b22cb7ec0 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
d23968b0-8e43-4210-9ea6-d82f890a0c64 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
6c534ea7-ba65-4442-9940-e5496cfdc34c | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
c6c80186-6f4c-43bd-a6e2-92fff1b65498 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
2355acbc-c061-408d-82bc-4d247667621e | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
ee341819-7665-47fe-84cd-a72f1909bf47 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
5df617b8-e1a4-49ad-930a-ca610f481d3a | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
9ed13afc-e62d-4446-a0df-e1db36c11028 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
5a11a7b0-b7fb-4a0b-bb64-373b982ee9f4 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangementr verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Mutli-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
7ffe0f24-b8fc-43d2-95d6-f722ca9116af | checkpoint | Stressing Records subject to Client Review
b7ccfb81-71b0-4489-9cfd-af807ee2f336 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
eb17fd1e-1b18-4d7b-8f08-374f2506d759 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
3a71a13d-2bfc-46e7-8017-689c85344f72 | checkpoint | All Cooling tubes installed as per drawings
1184bb1f-03d2-48bb-8018-e60e6ae3950a | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
356b7072-d85d-4f73-bc58-70887926aef6 | checkpoint | QA Engineer Check Completed by
99faac90-15b3-4a19-8154-43fc8d5f517c | checkpoint | Client Inspector (if present)
977002ac-7d4f-4018-a294-e4cbbd1d4c9a | section | Supervisor Release
236a0495-482c-4a98-af3f-093da395c35d | checkpoint | Supervisor Release to Engineering Team
4e39cc15-9c4b-44ba-8069-91cf45e7ba88 | section | Casting Checklist
67d33390-ecca-45d7-bbe8-6344b689379a | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
34fd634d-6622-452b-88ae-fb87ba2b8237 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
1f43ee4a-b478-466e-8f59-9f6a1f3d5304 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
85d5022a-792e-4580-a2e5-ad65c7f9cece | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
8d6500f8-b29a-4b7f-8a9a-d61032d3755e | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
2956e49e-9a58-44a3-b385-281b5415b99b | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
d501ec00-d49c-44e3-92a9-317483922c8e | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
f695eb0e-7e3d-424d-b7ac-c4d2f7f3e0d5 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
bc324c2b-adee-40f4-a3f3-f272d89cdaaf | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
49af8714-c82c-4dfc-8d0f-68fecd29eedd | checkpoint | Concrete Placed within allowable time from Batching Plant
18ecfb61-a3e3-4207-8d6a-504cba7461fb | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
d3e17bc2-f332-4502-9c35-b47caf67f7cd | checkpoint | Required Finish Applied as per Drawings
9ce32ce4-392e-4bac-959c-f073a316740e | checkpoint | Retarders applied on Green Cut areas as shown in drawings
980ee978-0055-460c-b4c7-b940ff9f30f8 | checkpoint | Concrete Covered Overnight
f743b25b-f405-495c-adcf-128df4ab20a2 | checkpoint | Cylinders Stored next to Bed
66813685-59a4-4baf-8596-e5fcf17bf705 | section | Stripping Checklist
b8398943-2e34-4fbd-8eea-bd998103b54e | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
6a3eaa61-562b-4d35-bacf-9665ecccb02d | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
0fd2af72-69ff-48fe-8245-88ca4ea0db5f | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
6ec9907e-8da6-4e60-a6bb-6ec61e8ca37f | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
b753d217-63d9-454d-8664-97dfb498da50 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
c7b9632c-6155-4006-adc0-c8163164fd01 | checkpoint | Lifted and Handled as per Drawings
4aea4ed2-5ade-410a-92b3-0616f7a6604a | checkpoint | Product Clearly Labelled
d8586f61-b348-4593-a35e-555ee686ad06 | checkpoint | Storage as per Approved Temporary Works Drawings
5c7010b5-547d-4556-b1c0-098ff804b995 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature does not exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
df2720c6-8e8a-4924-a259-81d259c04a8e | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
393ea6ab-422f-43a6-8de4-7c1189902535 | checkpoint | Specified Finish Achieved
8d59663c-7207-4d9a-af63-5ed89411693e | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
f94eeef2-a80f-41bf-8b7c-f1937ef36927 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire
d0b5905b-24c8-48ca-b1e0-5377125d2553 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
5edf2845-e52e-4445-a0cb-8a38f812b75c | checkpoint | Temperature Logging Completed and Conforming. Attach Results
f4eba698-951b-4f37-a98a-2dc7dd18239e | section | Any Defect Identified
ea0ce409-f14d-4bcb-9a49-32d0662beb78 | checkpoint | Punchlist Completed
9df015d7-0e9e-465e-96b0-e0929aad9042 | checkpoint | Repairs Required (if applicable)
17aac10e-0d1f-4904-896f-83ec1131927e | checkpoint | Repairs Completed as per approved WMS (if applicable)
1b25b13f-243e-4d8b-9564-def2e17b7660 | checkpoint | Crack Map Completed
f9779003-f90c-4ae1-8582-a87b598a6fa2 | checkpoint | Any NCR Required (if applicable)
04d2f7c3-f652-425f-bc1d-03ff5e4a26d4 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
1aa4adb4-6f84-4f7c-9ca7-b36439c98b5d | section | As-Built Drawings
88e1a23f-8b57-491f-8ed6-232c4178359c | checkpoint | As-Built Drawings Completed, Stamped and Attached
07a649aa-2895-47b7-ac63-598dd16f4f74 | section | Concrete Strength Test Report
0e893350-206d-4ccd-ac1a-c3fcef34e35f | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
8004d94e-4b54-4019-908a-39031e3de29b | section | Transportation Requirements
bba6ea79-9f52-43ea-ba05-2a4aacfdff66 | checkpoint | Certificate of Conformance
6fe71b55-0f51-4644-be2c-68cdb6ec80d7 | checkpoint | Inspection Release Certificate
95bace19-dd45-4f35-b988-b6023204932a | checkpoint | Delivery Notes
31542ef5-2aeb-400a-8f37-8c433765d29d | checkpoint | Delivery Docket
47f1f9ac-57c0-443d-befb-792347c7993e | section | Final Acceptance
6f2879df-abb9-4e59-9758-1a103be4314b | checkpoint | Completed by
8d0976ca-90ec-4d0d-bc3f-714af951b19d | checkpoint | Reviewed by
6d5271be-9ef0-41ee-ba42-66c1ea67cc7c | signoff | INTERNAL HOLD POINT
a838f616-38a3-475d-8884-d74867d7001f | checkpoint | Client Representative (if applicable)