## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
4e5d198a-4f2a-4507-89fa-fbb4b4eb2c20 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v2) |  | Byford U-Beam Stage-1 Casting
023f7196-a4b1-47ef-91ad-e81a88283f88 | section | Pre-Pour Checklist
307a56f5-10e6-4577-9110-38cdb7f2937f | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
dda59448-a973-4a76-9011-fd0c0ca4cc5d | checkpoint | Shop Drawings approved for Works
10e7ba12-aba2-431a-86d8-afac863ddc85 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
5cc4ffce-b49c-4ff4-8dd6-db8fb5afa671 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
69f81d7b-406e-4998-bd05-cad41bb01a4c | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
2fc72fe5-2e1c-4de0-859f-e1d7ff7d0fc8 | checkpoint | Detailed inspection of Mould and cage
01a17418-32a8-43dd-a20f-66a2eedbd7dc | checkpoint | Cover maintained and within tolerance
029fae10-b775-4cf3-9884-12f68614fb17 | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
12b84248-dd90-4809-b187-ca54cb1d98b9 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
debbedcb-ef98-4632-b445-1849743f35ba | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
85aa444f-a967-4c31-8b7d-b58ae8d4ca03 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
757c8ae4-9316-4faa-843b-38ede2e0b15a | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
0c5b8ee9-1b91-4966-8a17-9bfc6a304561 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
db0ad82c-1436-4522-89b7-d331cf3638f6 | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
014ef517-a7e8-44be-956f-c9151ceb3bc3 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
f3d5490f-86ee-47de-957d-83d1aba19f07 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangementr verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Mutli-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
84d4ee06-9fdd-48b0-a492-d7e1ff2a50fa | checkpoint | Stressing Records subject to Client Review
a6a02d9a-3356-4f26-8aea-df6aefeef974 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
6b47284c-4f2b-4ac5-bf04-def772e35af9 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
cca31838-53d0-4e06-9388-5ab156be4282 | checkpoint | All Cooling tubes installed as per drawings
e04f6d54-5bcf-4b01-8f53-60e9bdede152 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
e9733a5d-9dc5-463e-8d16-77203d623100 | checkpoint | QA Engineer Check Completed by
1650a34a-5909-4513-957d-5ae2b09a5872 | checkpoint | Client Inspector (if present)
7ded56a8-7e29-409e-b798-8aad20dcfdea | section | Supervisor Release
7710714f-ab49-4a0b-ad57-974d2df3dff5 | checkpoint | Supervisor Release to Engineering Team
d0235232-17c4-42ac-ae10-c5c868900373 | section | Casting Checklist
522a8720-c8a8-41c9-b118-27655b9dfbcf | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
472da490-509c-4b69-8989-e344412f7d58 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
5cf92a31-e1ae-4655-87a3-4049c52c7997 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
fa0e693d-3036-4516-9355-866511ae3beb | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
6e9e8f27-5e6e-439b-b3de-1f01522a26d5 | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
20d89684-5ab7-41ed-bcf1-6299d6d9d212 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
f4dbefc0-c6aa-4cf9-9bf5-15278fa39158 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
85c6ca16-6060-4127-838f-baa127930074 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
a7fa1991-ebb2-4bca-9376-209ae3ad9820 | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
40810b92-3b85-4697-9cdf-183bddb607a4 | checkpoint | Concrete Placed within allowable time from Batching Plant
f72e5388-2141-45ed-9635-3deea8b2ff51 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
5280a728-3375-46f0-b9f3-9b08ea4f5bfc | checkpoint | Required Finish Applied as per Drawings
20a6fb0b-adb0-4ae3-87dd-d8247eb5dae9 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
492feee7-7d50-4b9b-b27e-2a11bc26dc67 | checkpoint | Concrete Covered Overnight
b48cacff-00b3-4970-9886-28fabea63e1f | checkpoint | Cylinders Stored next to Bed
51a0ef4e-5a6b-42ba-9015-24d4cd02883d | section | Stripping Checklist
efc191a1-0a1d-41e1-b115-686f1a0825ff | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
4afdeaef-a148-4073-af7e-da822c55cf12 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
0f2903d4-9125-40ba-ab92-299bcbf9a481 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
facfa2e0-138f-4b6b-9447-e193dc283246 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
3d78f3f4-0278-4e6d-a300-16485623862f | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
873c36b1-3d2a-43ea-b222-9a81b3869df6 | checkpoint | Lifted and Handled as per Drawings
ff64407b-0f70-4db1-af02-83638d98dedb | checkpoint | Product Clearly Labelled
8ec4dfc1-39ec-4a5b-a907-bf0c45cf6aa3 | checkpoint | Storage as per Approved Temporary Works Drawings
1c6741bd-fcac-481f-a4e5-41e6589f31b4 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
6abaf03d-25a4-41c3-b97a-395635d169c2 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
6a8e174c-a418-4641-ac99-c2fac727efad | checkpoint | Specified Finish Achieved
4bf3e3db-fd29-4bdc-96ae-c5294428a0fb | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
bb268dc2-44c8-4263-83c3-542b007e2fb5 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire
8fd36aab-6ea4-40e5-b033-d238113b99b4 | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and atleast 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
4df60c00-ac95-4019-88fc-9a29543f59fd | checkpoint | Temperature Logging Completed and Conforming. Attach Results
0cbbc555-4bed-468b-84ca-2c3b0597d9df | section | Any Defect Identified
702adb54-49d1-4306-94ef-8733fcc20e95 | checkpoint | Punchlist Completed
85c4b5f5-d86f-449c-bc4e-e34035c90285 | checkpoint | Repairs Required (if applicable)
fad2c4ec-b879-475e-bb63-ef1e74f395c9 | checkpoint | Repairs Completed as per approved WMS (if applicable)
1b037c1a-2c7c-4b13-8d1c-b8019935dd4c | checkpoint | Crack Map Completed
270cb206-9449-46ca-a543-0533d1f12960 | checkpoint | Any NCR Required (if applicable)
a2e74dae-2b20-41de-8310-4f3d1d0ca216 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
e107b49f-8160-4a82-b014-ab3f6c1ff356 | section | As-Built Drawings
62285be5-5bf4-43f2-802f-edb40755a553 | checkpoint | As-Built Drawings Completed, Stamped and Attached
13a76684-045a-421d-9480-a222be65fa8a | section | Concrete Strength Test Report
af582ec2-7c4a-4226-a708-17e7163bde57 | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
165d8127-2c4c-41f9-a8e1-f533dd46d7a8 | section | Transportation Requirements
cefcfc5a-07a3-4101-a5dd-0dc76668b0cf | checkpoint | Certificate of Conformance
fc6ad1a1-c702-4cd2-a862-0682101fe2cb | checkpoint | Inspection Release Certificate
e50a4542-d84d-4747-b707-b24e22793c58 | checkpoint | Delivery Notes
8c770a8a-cc1c-4a3d-83e6-f99ffeb47209 | checkpoint | Delivery Docket
c3b561be-1cb7-4021-a965-046b1ee6dcf6 | section | Final Acceptance
a547fa7e-3852-4c99-8c52-c794dc7cd9dc | checkpoint | Completed by
b59d38e1-f716-4876-a229-11fd7603986e | checkpoint | Reviewed by
058211e2-f32b-46e4-bc02-50689ac9fcb6 | signoff | INTERNAL HOLD POINT
e4c649aa-0101-4290-867d-46188fd20e66 | checkpoint | Client Representative (if applicable)