## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
2aa3b08c-d082-4553-ae2a-882be057c4d3 | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v3) |  | Byford U-Beam Stage-1 Casting
4281b298-bd34-4e54-89a1-cbc4413c950d | section | Pre-Pour Checklist
9668efbc-810f-44a7-84bc-eabc83eb3727 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
41f392ec-44d8-4944-a67e-ddfafce4b221 | checkpoint | Shop Drawings approved for Works
1cbf625b-a062-4984-bf3f-682e24e8b45c | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
41908df0-f25f-499b-9f55-3187f2d936e9 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
cededb35-6b0b-4970-8cdf-ade8870538ff | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
8cdf4d82-129e-43fc-81cd-a413426ce55c | checkpoint | Detailed inspection of Mould and cage
51759b13-ca00-4cd1-a99b-568b75597afb | checkpoint | Cover maintained and within tolerance
fcce8728-c53f-4842-8304-eb2db0b6027a | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
b2243ff0-aa7f-456c-a4f0-0f99395e482e | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
72713cdf-bda9-4c90-b705-56527f44d5b7 | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
f635d75a-0c6c-45bb-8358-c3e1a734787f | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
b3f7d55b-7d49-4484-853e-34f1063906d5 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
a3ae3a3c-d661-4676-af27-ebaf2747e222 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
087f93bd-0273-4ae0-b13b-de57af06254c | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
8e410c08-2770-4047-b95c-e31738112a1b | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
e0c54e09-5e06-4966-ab21-fe5ce0a4e91d | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
c25e9ba7-52e8-43ee-b392-1e87cb92e02e | checkpoint | Stressing Records subject to Client Review
4f182b3a-482f-4710-8715-ed4aa24d1b45 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
05192cba-ee3f-40f0-8e01-609573b3300a | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
fa511556-c928-4d92-9790-d254d366e47d | checkpoint | All Cooling tubes installed as per drawings
95c26491-aaae-46d8-9bb3-086533197839 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
2b47f116-eaef-455a-bf48-cd52f5c0cb17 | checkpoint | QA Engineer Check Completed by
f6653d57-3309-439f-8af9-d0cfc6012a01 | checkpoint | Client Inspector (if present)
37f2b377-0c68-4af2-8355-82cf1b311775 | section | Supervisor Release
d1a2d56d-d83e-4064-bb2b-e18e85719782 | checkpoint | Supervisor Release to Engineering Team
59d436cc-3995-4a4c-93f9-f3d199e0f5a9 | section | Casting Checklist
64ab27c5-534e-4ae1-98fe-38bdc33019fa | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
14c791ae-460e-46ab-8961-880a1c4ef008 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
841a1f73-1848-431d-b842-4e714acbdf61 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
aa0b87d1-3fa7-49c2-b619-0d21716f9764 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
b9682912-9e7f-4048-957b-606b7180dfee | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
92f20cd1-b672-4973-b894-0c389868b651 | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
1b5f9956-4ad7-404f-8d4a-2743250e8281 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
4d76ab10-311a-40b3-bc26-8076909d3117 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
a2135ece-be25-4e38-a16c-2daafdd371ed | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
16e738f4-de42-4329-851c-90010d1d76bb | checkpoint | Concrete Placed within allowable time from Batching Plant
a192f73f-c41c-4d8f-b2b2-90a54680f8b6 | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
0226e1ef-540f-4fb2-87fb-78cab39edf5e | checkpoint | Required Finish Applied as per Drawings
02c6ba6b-5d52-4965-a36f-14304132c030 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
ddeca55e-2af1-47dd-bae9-72bf005206db | checkpoint | Concrete Covered Overnight
46b8c0e3-28d2-467a-b857-273e2f13013e | checkpoint | Cylinders Stored next to Bed
d5d937ce-a679-44ea-b7d0-6b6dad45381b | section | Stripping Checklist
6ea1eab0-be1f-4a00-8303-4d241ec0241b | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
c5c3ed6b-6594-4367-bcba-fff95855c3c1 | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
7f9a1e4b-9b71-45c7-8f42-835ffea3138d | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
d0b81178-c4c7-42ea-9c6c-1e567e6567fc | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
9b52489d-648f-45e6-8bfd-3d9eabb60342 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
1cfcb858-786d-455f-84b6-7736e6620874 | checkpoint | Lifted and Handled as per Drawings
33c3b8b8-2fed-4123-983f-426801064d69 | checkpoint | Product Clearly Labelled
21df6bee-bcc3-4408-b74a-76e9ac77e31e | checkpoint | Storage as per Approved Temporary Works Drawings
8a43a89a-df13-4d04-9bf7-fdd52fab0f91 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature does not exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
ea69e858-5d4a-405d-b643-7a6598b3668d | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
dd6b8636-fd34-44fc-bcf1-39c5afe19a76 | checkpoint | Specified Finish Achieved
95d657c8-c0cb-4997-a675-f3222f560a51 | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
709ff950-4074-48b9-8ce0-1657f15f3275 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire
50193ab6-9b39-4535-a3a7-9d5160c6ebcb | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
ed90e5e8-c45d-4c3d-8295-0d327ed78075 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
24c0d1db-00eb-4cda-aac7-3d139cff5486 | section | Any Defect Identified
e9cf81a4-c4ca-4065-80a8-291970086971 | checkpoint | Punchlist Completed
b3e70e5a-ed18-4e7e-ad3d-60a38c3b0d6a | checkpoint | Repairs Required (if applicable)
48104fd0-d05d-42f8-abdd-e809a000866d | checkpoint | Repairs Completed as per approved WMS (if applicable)
406fdc3a-392b-4b21-9f22-2dc812207034 | checkpoint | Crack Map Completed
08117b7e-cf8e-4ca8-b7c9-c0f621acdd22 | checkpoint | Any NCR Required (if applicable)
9598be9d-e30d-459a-a57c-7eb96472dbc4 | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
18e8feeb-2ad1-4807-9094-f9ebc2f0babd | section | As-Built Drawings
0bb701f7-a914-4ce4-aa43-31936c9618da | checkpoint | As-Built Drawings Completed, Stamped and Attached
95ba54b0-a603-444a-9903-b95abb9939c4 | section | Concrete Strength Test Report
de667db7-4773-4ca4-9539-03c883e96874 | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
6c2af489-fca9-47ad-a1dd-14be0bc9c0ee | section | Transportation Requirements
aff1d30e-b2a5-4c7b-bd73-7413628329a2 | checkpoint | Certificate of Conformance
3d8ae805-4e3e-4316-a3c5-9e7fc549ad90 | checkpoint | Inspection Release Certificate
b8ce5777-9b8b-444a-8a60-a0e9a2d53379 | checkpoint | Delivery Notes
56a1118a-6dda-48e6-8eba-c158ce14a283 | checkpoint | Delivery Docket
10f0bc55-2154-4c40-ba94-2b5948a03232 | section | Final Acceptance
b64ecaca-17b4-464a-bd9c-dfeb93b8affc | checkpoint | Completed by
d1af3d35-1f19-4e55-8000-3c0c0977c9e1 | checkpoint | Reviewed by
a0bb38d3-0978-4e36-9f5d-0d23e60ffb4f | signoff | INTERNAL HOLD POINT
d9e43b73-2527-4b6a-a4f7-5467c6d9a2fe | checkpoint | Client Representative (if applicable)