## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
ea7abaf4-6151-4d8d-a065-065ff82ca70b | checklist | Ω (Deprecated) Byford U-Beam Stage-1 Casting Checklist (old version, v4) |  | Byford U-Beam Stage-1 Casting
16744d98-b285-420b-9065-47c700dc7438 | section | Pre-Pour Checklist
f5b48e28-a0c2-47ce-b5e8-0e66dff49d78 | checkpoint-no-value | Details
84eac92c-86ff-5566-8337-b87e1ef14eb6 | textbox | Cast Number
75a33415-823d-5126-accd-f72809d0c49b | textbox | Beam Number and Orientation
4c40ea98-703e-5a88-971d-0e5838a1947d | textbox | Strand Arrangement Type
680f5732-e19a-5002-9534-d84f51fa7bb4 | textbox | End Diaphragm
b55ce491-ef97-44a4-ae95-123553c193bd | checkpoint | Shop Drawings approved for Works
dd3b7a3f-a806-49d4-962d-d3f7b8972b01 | checkpoint | Mould Dimensions are within Shop Drawings Tolerance
680f89df-1b74-5e63-9f59-f8799a7ad308 | note | Length
3c33b51a-3cbc-50f3-93eb-6c7590cae521 | note | Width
a6c4756d-8491-5a2c-8fef-c5154dc5f7f7 | note | Height
7194fabe-f0ee-5be9-8f99-a7423d45323e | note | Straightness
b51604f1-02a2-5440-83f1-3d0aeb55bde2 | note | Cross-section
bdff19b4-abb6-4306-a298-5cb12ecae2f6 | checkpoint | Mould Surface Checked
1bfc6f7b-aae5-5e2e-9088-c8d6b4de8a9e | note | Cleaned
94f4d1ab-6d65-5851-892b-115f1e586c1a | note | Sealed
0b367e3c-bf5a-5ee0-8368-658cbcf44ff3 | note | Rubbers in Place
b2e0da86-c42e-56d1-9030-39bacada7fb4 | note | Oiled
97e29f26-b5d6-55ea-9ddd-bd6e9e88e3e3 | note | Chamfers in Place
a34f9105-a8b0-4a2d-8b1a-eb0e177a0002 | checkpoint | Reinforcement in Accordance with Drawings
b476357f-248b-5b10-abc1-d42d03816a8e | note | Reinforcement size
6f5d001f-932f-5ae7-8115-3ad8bbbb8098 | note | Lap Length
8315cd7f-ce76-5a99-b36c-5a7f0fdf2c97 | note | Splicing
db0fffd1-8336-5af1-9463-af8265ed743d | note | Bar Chairs
49b53a33-9b54-5098-917e-55cdba66c91e | textbox | Reinforcement bars with couplers
80919775-87b1-590c-9ca3-d4cb161e9e60 | textbox | Reinforcement around lifting loops
0f144171-3f31-428c-acbd-88d2dedc565c | checkpoint | Detailed inspection of Mould and cage
a4978289-48fb-4235-ab9a-e66a1ccaa206 | checkpoint | Cover maintained and within tolerance
b7db9148-7875-44ec-a21f-65d77946a27b | checkpoint | All Stainless Steel Ferrules are installed in accordance with Drawings
5e2a1847-41d2-530b-9fa9-4cf64e68df9a | textbox | Ferrules KSN16M (Web)
e9ada671-1b5b-58a4-a99e-f530176c0cc3 | textbox | Ferrules M20x96 (Bottom Flange)
75fc6791-ed0c-5a86-a260-96a9d7622c35 | textbox | Ferrules M16x45 (Ladder) |  |  | Size not confirmed
45645bb9-a703-58c4-8d0e-65d8bd2296ca | textbox | Ferrules M16x70 (Web, Laingorourke Formwork)
8685bdbd-bb9e-5e95-8334-dce0cbc1386a | textbox | Ferrules (Other type, specify)
25b391f8-f583-4082-b4b5-e91035552263 | checkpoint | All Stainless Items are installed in accordance with Drawings
5f80c6de-b98e-53ff-ba1d-8ad3d9a53f6a | textbox | Other type, specify
40c38cc9-6bf2-4c3a-9662-187771a9d2ad | checkpoint | All Blockout Conduits are installed in accordance with Drawings
21d53c60-f325-5c19-9fe0-fa15ad759824 | textbox | 20NB PVC Pipe
ca67e1ab-63f8-486c-9a56-c42ca5c05732 | checkpoint | All Lifting Inserts are installed in accordance with Drawings
2b55e49e-5a59-584c-8811-9b25b6343349 | textbox | Lifting Hoops
32e58ca2-3b89-49eb-bb6b-5be45dc35486 | checkpoint | All Bartek Couplers are installed in accordance with Drawings
c700dabb-ef68-5077-88f3-67d5d942f34e | textbox | BPB28
b5aee04a-e510-5aee-9709-21141122f742 | textbox | BPB36
ed98930b-1a7c-53c3-9ee5-3e79aeb82fb2 | textbox | BPB20
2608413e-b9c9-4df2-80ef-829e9d3760a8 | checkpoint | All LENTON Couplers are installed in accordance with Drawings and staggered with KSN16M in web
cc0e0ef4-342e-58b4-b477-05411c0d50d8 | textbox | LENTON EL20A12
8840b824-96cd-4a49-bd7d-12c78bf0e39c | checkpoint | All Bearing plates in Diaphragms are installed as per drawings
bb71e454-6a7e-571a-af19-a0aa625a7ff1 | textbox | Specify Bearing plate Size/Type
1b4ccfe9-9695-4de2-b19c-8c314b827d05 | checkpoint | Earthing and Bonding is installed in accordance with Drawings
03f2c87f-f42e-50ea-ae46-4819f1f74dbb | textbox | Earthing Terminals (FDB-16)
a767f51c-e95d-5a15-a991-a3ecd21931cb | textbox | 100mm long 6mm fillet welds between bars/ 55mm long butt welds
abb17c43-bb30-581a-8764-791d88ae9397 | textbox | <20 mOhm across cage Length
88a643de-b2ad-5b34-bb61-f01864ddd335 | textbox | Checklist Completed (North & South) (attach results)
efeab47b-3e26-49fa-aba3-03364b131f13 | checkpoint | Prestressing Strands
4966043b-97c1-5923-889b-a979f69eddae | textbox | Coil Number Used for this Cast
fce23d34-bfc8-5931-bc15-396166fe50f1 | textbox | Dia and No. of strands
afab0b2f-1cd4-56d8-ab47-1ce1d55163de | textbox | Strands arrangements verified
4f01fd3d-2e5f-58d3-a45c-bacce9f5c9c8 | note | Sag Load all Strands
de160996-9edb-59e3-a614-d4537ec95dd6 | note | Multi-Stress as per Pre-stressing Procedures
46296c35-9e45-5fac-8a30-a7879817b087 | note | Verify debonding strands if any
f7faf14e-696b-4fac-82be-29ba00ecd303 | checkpoint | Stressing Records subject to Client Review
0a08af7d-ceca-47f5-a1e8-ef81cb4657d0 | signoff | HOLD POINT FOR CLIENT TO SIGN OFF
65d3dea5-0b68-4dec-8ea5-b73a6c614af7 | checkpoint | All Temperature Loggers are installed as per Approved WMS
11270652-5c46-5496-960d-62f8e87a5af7 | textbox | Ensure All temperature Loggers are Working (Check Maturix)
ecd86088-6def-4d65-991d-061c073288c6 | checkpoint | All Cooling tubes installed as per drawings
35c4f241-a07c-47cc-ba50-a7d404889661 | checkpoint | Installation of tubs
816660b8-2669-5678-a1f2-9f6f5d3f2be7 | note | Tubs are tightened and positioned correctly
dbc035e3-e77a-527a-9838-af412f46e224 | note | All Sliding arms are locked in position
50a4732b-f130-5d16-9374-980e801e00b4 | note | All accrow props are locked in position
14f3bf7d-041f-57e4-8c12-b5d81574ae58 | note | Dimensions of Tub and Webb are correct
62294d53-0f5e-5084-a28e-af2a8444db2f | note | All feet for tubs resting on mould & bolted down
a758a314-83ed-5e9c-b5e8-c4438ca441c2 | note | Tubs have release agent
cd1ca22c-6265-4ad5-929d-4bd9b02e017a | checkpoint | QA Engineer Check Completed by
f1babe87-b99a-4152-aa1e-edeb9c06a2d3 | checkpoint | Client Inspector (if present)
4c6185c3-0abd-4997-b55a-6f82c25b6af1 | section | Supervisor Release
1cd6902c-1bcc-4b38-aee7-af81bb41f1dc | checkpoint | Supervisor Release to Engineering Team
f7b2cda9-c085-401b-a272-7bf3a5ab19e8 | section | Casting Checklist
3088baa5-cb3e-471d-889c-6cf4a22151aa | checkpoint | Casting Information
06533039-ce09-58fb-9d67-4a1a88419714 | textbox | Cast Date
771b296c-ecce-4da9-9056-aafd535c2fc6 | checkpoint | Concrete Delivery Dockets
edb15e75-557c-552f-bdd8-bc51a1f190c8 | textbox | Concrete Delivery Dockets (list all)
3fc36ceb-6b13-4ac2-a207-5c1d2c575136 | checkpoint | Total Concrete Volume
4471e4f4-eb75-5de5-8a96-28f2d19a67b2 | textbox | Volume (m3)
262bde5f-953d-4a45-9e5c-55ca5cdf4540 | checkpoint | Mix Design Verified
3c381e37-ec23-52a9-98d2-458a151f3da5 | textbox | Specify mix used
3fda9a15-af15-42d0-b5de-9be7a2022606 | checkpoint | Ambient Temperature within Limits
f22424b4-83fe-57c1-9c5a-a1e8be3d4e0c | note | max 38°C
604c77b3-fd68-44cd-9fbb-b1b6e666576a | checkpoint | Concrete Temperature
1f816455-4ea0-530a-a522-938704426215 | note | max 32°C
82111a96-f817-4618-9ed1-558ab4b30057 | checkpoint | Slump within Allowable Tolerance (180+/-40) (Tested 1st truck and subsequently for every 20m3)
7f377b6c-fb22-42ee-8548-d71de53fc939 | checkpoint | Trucks Tested for strength
2cb7bd22-3a3b-5e2a-85bf-d6ff176e2ae1 | textbox | Test Report Reference Number (list all)
85017a60-1a9e-4844-b3dd-6ddf6ca9fd0f | checkpoint | Time Lag Between Trucks not exceeded 20 minutes
30d68a63-ac72-456f-870b-15700436342c | checkpoint | Concrete Placed within allowable time from Batching Plant
eec992d3-718d-4ad1-8b3f-1e6a5c08fdbe | checkpoint | No Free Fall During Pour (not more than 2 metres from ground)
6c900237-0d85-4213-a187-b7c9ece0ceda | checkpoint | Required Finish Applied as per Drawings
dc513e48-ef09-4f9a-aa52-0fc68070c9a3 | checkpoint | Retarders applied on Green Cut areas as shown in drawings
2cab1da8-1edd-4b80-b46e-d4a91cd343e9 | checkpoint | Concrete Covered Overnight
70ddb220-7477-4d19-8168-580e449ed118 | checkpoint | Cylinders Stored next to Bed
4cecd54f-e03a-4d1c-ae4a-1c4ad500c006 | section | Stripping Checklist
d33e9883-9d01-4a60-8b32-b89ab86ab902 | checkpoint | Date Stripped
5d5d3825-48cb-5137-8a1b-913727a9a156 | textbox | Enter Date
fdf43226-18d1-4188-b6c5-dbb3e80a321d | checkpoint | Concrete Cylinders Crushed and Checked for stripping strength
86a95e24-144f-554a-a852-cbf0778c2285 | note | Conversion KN to MPa = Reading / 7.851
61c985c8-560e-55c1-9375-a9a1e181026f | textbox | Stripping Strength (Stage-1 Casting)
31336773-930c-4c36-ae21-09e4c90cd2d5 | checkpoint | Verify Destressing/Transfer of stress required strength
8fc99148-2253-53c6-9364-d6f1a47d1eed | textbox | Specify Strength at time of destressing
a831a68d-7f42-45a9-adef-4881c16cec44 | checkpoint | Lifting Strength Achieved
0edb6e72-9025-5215-adb8-64d55f2d38fd | textbox | Specify strength at time of lifting
47538485-9689-4600-9de9-2d2241dedd32 | checkpoint | Curing strength (Stage-1 Casting)
3a2279aa-862d-54cf-972c-f3a24f8ff27b | note | 45.5MPa - 70% of fc (Characteristic design strength 65MPa)
70e29e2c-bada-54fb-b525-34784d33223f | note | Mould and Steam Cured until the curing strength achieved
0ca63518-5f67-4ac4-aa61-5d1c9af87706 | checkpoint | Lifted and Handled as per Drawings
f4e59221-fbb5-497d-8f31-aaa1ab935fd3 | checkpoint | Product Clearly Labelled
72381f9c-b758-4c25-a4a8-deb69f65bd45 | checkpoint | Storage as per Approved Temporary Works Drawings
22b190a5-1bb7-441a-93ad-91a36b30dbc3 | checkpoint | Secondary Curing as per Approved Methodology if required
36ae9ce6-b2ae-5d21-8d9d-03c1d1889bd2 | note | Temperature 5 degrees less than its peak value
bf472b03-0cdd-51e3-95a8-72fb49a0b484 | note | Max temperature doesnot exceed 70°C
9020a31c-1699-5f14-8de5-0e965cb554b9 | note | Differential between Core and Ambient within 30°C
e7f352e5-4475-5356-8cbe-e9732c413159 | note | Differential between Core and Cover within 25°C
42dc2ba1-fb55-4feb-b866-71e0c68b7e00 | checkpoint | Product Dimensions Achieved and are within Specified Tolerance
3623ef49-bc71-5143-a19b-77b46e62a3fa | note | Length
ebeb0b65-36f5-53ea-93de-bedcac9d8320 | note | Width
a7aae39a-4425-5218-b2f1-74a7fb644c6d | note | Height
41fe9fd4-0604-5daa-b1fe-b7f247d63607 | note | Straightness
c17424ee-d019-552e-b666-96fb936eda3c | note | Cross-section
94e5de1d-3ea3-40a8-afa5-06849c50f57c | checkpoint | Specified Finish Achieved
61c9b91a-d98d-49c7-a0ad-f8897551805e | checkpoint | Cast-in Items are all in Place and within Specified Tolerance
9f60ae23-ea2a-5950-9617-bd7575abd6ff | textbox | Ferrules
3bc39844-eaf8-5b72-af90-3bd4206e9ca4 | textbox | Couplers
6e79de90-817f-537f-ac39-f47f454ba290 | textbox | Stainless Items
666d9cb3-04f1-557f-812d-c116e0625b5e | textbox | Lifters
39b376a6-f073-5359-9137-905dd42ae620 | textbox | Blockouts
7644c8ca-b857-4add-9f63-3b34a2a19339 | checkpoint | Post-Pour Works Completed (As Required)
787e9a74-5d8d-57ec-8927-fc4d1b197e65 | textbox | Strands are Cut Flush and Epoxied except debonding strands
b393264c-8248-5af0-8c80-89b93db73a8b | textbox | Couplers are Cleaned and Capped
02502447-d30e-51b6-89fb-751c4fdc9a97 | textbox | Roughened Surfaces are Greencut
79303072-88ba-5e1d-b7ee-e9b30ee6ab98 | textbox | Water Removed out of Cooling Pipes
ebf97a14-eb3b-50aa-bb4c-b1725eeed2cc | textbox | All Miscellaneous Items are Completed
8698f9e6-b507-5bf5-947d-42d9481f618f | textbox | Bottom surface clear from tie wire
a7bb909f-701d-469f-84bc-c0c44cd42f6f | checkpoint | Survey Hog of Beams (Dumpy)
a49a273a-d8be-5e4e-be3d-46673489cd83 | textbox | First Reading (Within 2 days of Stripping)
552cd361-fbb9-5dfe-94a6-f95910f1d211 | textbox | Second Reading (After casting stage 2 top slab and at least 7days after stage 1 casting)
40b90e4d-e5f2-55fd-8945-130eb08b17a2 | textbox | Third Reading (At 28 days after stage 1 casting)
c8bce997-9181-56ff-ac96-2b314604cdcd | textbox | Final Reading (7 days prior to scheduled delivery)
fab0f99a-4d67-4aab-be8a-423264d4a5f2 | checkpoint | Temperature Logging Completed and Conforming. Attach Results
fccf01f8-877d-40f7-a1ee-44f898612ab5 | section | Any Defect Identified
31a2d2c5-c353-435d-9df5-8d4112a11529 | checkpoint | Punchlist Completed
916cca62-42e1-4ea9-bf3e-458385dde062 | checkpoint | Repairs Required (if applicable)
3abffb29-6b96-4f38-8081-d5db3a18c03f | checkpoint | Repairs Completed as per approved WMS (if applicable)
6da2e659-ca7a-4a0a-bca0-f8cc737bd8f4 | checkpoint | Crack Map Completed
63acf965-5557-4e8a-aa0d-84ed1d7e1f1f | checkpoint | Any NCR Required (if applicable)
d880e160-757c-482d-b392-cd0d07b9a42b | checkpoint | NCR Approved by Client and Repairs Completed (if applicable)
0fd6addf-cf47-4913-a965-abb131e4f904 | section | As-Built Drawings
2d9175ce-be55-429c-ab3d-c2f5dc5a3c0b | checkpoint | As-Built Drawings Completed, Stamped and Attached
84689bb3-0a27-4864-a516-2ce58c45ca9a | section | Concrete Strength Test Report
065ba022-a1ed-407a-9f35-17d02d458bba | checkpoint | Concrete Strength Test Report Received
8a9a50ff-d4ac-58e1-8dc6-0c6d34fc25d6 | textbox | Concrete Test Report
ca1bcf36-7597-52c4-8784-5c1fdd1c1310 | textbox | 7 Day Strength (List all)
787cebda-6ab9-5fc2-9497-4450a4efbda7 | textbox | 28 Day Strength (List all)
c35fe3e1-f447-47fb-9901-2eb20cdbf337 | section | Transportation Requirements
dba9a7a1-70ea-4bd8-b328-23a0c47eeebd | checkpoint | Certificate of Conformance
b43cc1a9-f1f4-4434-a26d-1c6b5b7ffa09 | checkpoint | Inspection Release Certificate
aed2e077-72cd-4597-b05a-afb2fe76a622 | checkpoint | Delivery Notes
7dae3aff-29eb-4b8b-9cfd-51745674ec6d | checkpoint | Delivery Docket
8ec676cf-eb95-4214-be38-e9261b72b7c3 | section | Final Acceptance
f544a5f0-f529-4aa9-ae91-f1e85fed8a0d | checkpoint | Completed by
620ea82c-b84f-4d37-85c1-dd91620f4ae9 | checkpoint | Reviewed by
e9f0de51-955e-4e56-9b38-7151978ae3ed | signoff | INTERNAL HOLD POINT
ea6cecd7-e6a2-4296-9ceb-71277918fe6e | checkpoint | Client Representative (if applicable)