## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Wall Closure Checklist 2 Rough In [P]
section | Wall Closure Checklist 2 Rough In
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | FCU installed in right location as per mechanical layout and the model number is in accordance with latest AC schdule
checkpoint | FCU installed as hight as possible with 5% slope towards the drain point
checkpoint | Thermostat control cabling has been installed
checkpoint | Thermostat location is correct as per RCP
checkpoint | Drains have been run to Tundish
checkpoint | Drains tested and witnessed by Boad Air
checkpoint | All wiring including interconection wiring and power from isolator to the condensers are roughed without defect
checkpoint | Refrigeration insulation is not damaged
checkpoint | Where refrigeration lines insulated and supported pipe clamps have been installed to avoid damage to insulation
checkpoint | Pipe projecting the wall cavities in balconies have been sealed
checkpoint | Refrigeration pipes are run through cavity without being kinked or damaged
checkpoint | Refrigeration pipes run is not exceeding the pipe length limits in VRV systems?
checkpoint | Is the Ductwork to FCU insulated & correct size? Is ductwork installed & sealed correctly?
checkpoint | Is flex duct running through walls squashed?
checkpoint | Is correct size & insulation of flex duct run from ducted FCUs to the grille terminals?
checkpoint | Are the uniboots for Supply Grille installed & sealed correctly?
checkpoint | Vent boxes are sealed
checkpoint | Add divider using brackets inside Exhaust plenum boxes to separate toilet & kitchen exhaust?
checklist | Ceiling Closure Checklist 2 Rough In [Q]
section | Air Conditioning:
checkpoint | Air Conditioning
textbox | Inspection Date:
checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint | Units all hung with isolation mounts and with 5% fall to drain point
checkpoint | Other services installed are not impeding access to fan coil
checkpoint | Wiring connected to indoor unit electrical box
checkpoint | Refrigeration pipes run is not exceeding the pipe length limits in VRV systems?
checkpoint | Condensate drainage is in correct location & height
checkpoint | Filter Track for return air have been installed at the back of unit
checkpoint | All flexible ducts connections to air terminlas and spigots have been air tight by using duct tape
checkpoint | All flexible ducts connections to air terminlas and spigots have been secured by using fixing ties/cables ties
checkpoint | Are correct concrete fixings used for ductwork?
checkpoint | Is the duct joining/fixing undertaken correctly?
checkpoint | Are the correct /approved spigot sizes installed?
checkpoint | Is correct size & voltage for zone dampers installed for living & bedrooms served by ducted fcus?
checkpoint | Is correct size BTOs & Y pieces used?
checkpoint | Fresh air to apartment
section | Ventilation:
checkpoint | Ventilation
textbox | Inspection Date:
checkpoint | Fans installed within ceiling areas are in the correct location as per Mechanical Drawings
checkpoint | Fans Installed correctly with rubber isolation pads
checkpoint | All Flex has been run to correct location
checkpoint | All flex are hung independent of other services and supported by intact load spreaders
checkpoint | All flexible ducts have been mechanically secured to spigots and air terminals by using fixing ties
checkpoint | Butterfly dampers are installed on the PODs grille neck and they are in a fully opened position and air tight sealed
checkpoint | PVC sleeves has been installed in wet area walls
checkpoint | Vent boxes are intalled in correct location as per RCP and SEALED
checkpoint | PVC ducts have been hung and supported indicidually by using hanging straps
section | Access Panel:
checkpoint | Access Panel
textbox | Inspection Date:
checkpoint | Access Panel location has been marked on floor as per RCP
checkpoint | Access panel location allows sufficient access equipment
checkpoint | All other other services do not impede access