## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 40e8df39-c0e7-4b2c-ad1a-a7713bf1abed |  | checklist | QA - Water Supply |  |  |  |  | Yes | QA - Water Supply | 175c3161-f59b-4a90-b662-aead000f6c2e
checkpoint-group | 6a2c2d59-3b03-4d39-a2a8-493d864a70b6 |  | section | Water Suppy
checkpoint-status | a7fec4b2-a925-4806-8e9c-be35ad843d07 |  | checkpoint | Pipe Work Secured in ceiling
checkpoint-status | e6953bb6-93bc-4e6d-b3f1-f7048dc6d7a9 |  | checkpoint | Pipe Work Secured in wall
checkpoint-status | 17bdee3c-637d-4c2b-ac0e-677c6e650700 |  | checkpoint | Pipe Work Siliconed
checkpoint-status | 44a95ede-1733-470f-8735-47afa8fe9f8a |  | checkpoint | Check for Crossovers
checkpoint-status | c270bd0a-c7eb-49ba-adf5-4a41841f0093 |  | checkpoint | Pressure Test 1500 KPA or product/job spec
checkpoint-status | 9889c9e3-bd10-4863-b30d-d1d7b81f05c4 |  | checkpoint | Visual check & photos attached
checkpoint-status | 78bbddca-fcb3-4186-b972-72264a965507 |  | checkpoint | Check all joints
checkpoint-status | dc09d168-a1e2-49ad-a770-c0ec4ba39e19 |  | checkpoint | Shower/bath outlet Crimp
boolean | 7a48ebd2-6cc9-519e-aae5-7bc0ba30513e |  | tickbox | photo uploaded
checkpoint-group | 04b7ae35-c3e7-4991-bf2b-21e2c1986d99 |  | section | Pre-line Inspection
checkpoint-status | 056d4bd2-848b-4c28-be60-7f6317332c31 |  | checkpoint | Nogs in correct Location
checkpoint-status | a66a1470-a39b-4b55-b084-a0625dfcf5de |  | checkpoint | Cylinder seismic nogs in place
checkpoint-status | d35b473e-8e07-4bf2-a4fc-4bed7709dfe8 |  | checkpoint | Vanity, shower, toilet nogs
checkpoint-status | e7aeba46-bcc5-4d0d-ba89-85bde458d9f0 |  | checkpoint | Shower mixer - Depths allowance for tiles, nogs square to wall
checkpoint-status | 771d850a-ec32-4867-bb51-44537e8a2d24 |  | checkpoint | Mixers straight
checkpoint-status | cb7a555b-ca7a-4c5f-9ecd-772c7c448be7 |  | checkpoint | Vanity Wingbacks
checkpoint-status | 977ef1f5-271c-4f8d-a712-e662ddb4a2ec |  | checkpoint | Outlets straight
checkpoint-status | 4a32aac4-5317-43c6-8835-82419d6ae407 |  | checkpoint | Outlets correct length
checkpoint-status | 1cbedbeb-5253-420a-a3e0-cfc132071960 |  | checkpoint | HWC water feeds
checkpoint-status | 9ef34aa8-1908-4989-a9cc-f77f4593262b |  | checkpoint | Capped Off
checkpoint-status | 196bd955-ca70-432b-bd24-ec7484d4d28b |  | checkpoint | Rubbish removed
checkpoint-status | 7997e2e2-8aea-45c5-a7bb-484e78cf4bb8 |  | checkpoint | Protective covers in place
label | 1b07bf31-92a8-5cb7-919f-a524b557e338 |  | note | Attach photos of completed area
checkpoint-status | 95873c37-229c-4019-a907-17eb4f3b89e1 |  | checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | b8298c6f-ea3b-447c-a249-2a238fe7a600 |  | signoff | Add Signature
checkpoint-status | f658b266-7d63-4cf3-a4d7-ab62373da49c |  | checkpoint | Pre Line Inspection Passed - Witness
holdpoint | 2dc54f4d-c0c2-495e-b9de-c5354692e7db |  | signoff | Add Signature
checklist-sectioned | 044cfe60-3878-4a9a-a305-fe3e480fadd4 |  | checklist | Water treatment test |  |  |  |  | Yes | Water treatment test | 1fa7607d-3e7b-498c-8757-1225af5ef61f
checkpoint-group | ad63dd3b-5160-44c5-93d6-507f64c3bd60 |  | section | Water reuse
checkpoint-status | 409db95c-95d2-4079-a02f-749c728a7c1a |  | checkpoint | Installed as per manufactures instructions
checkpoint-status | 3fda87a7-d8d7-4db4-addb-6a093680369f |  | checkpoint | Controls for 3 way valve operating corectly
checkpoint-status | e888d735-50e2-475a-a48f-8bc295dc4d9e |  | checkpoint | tanks T1 and T2 are full and ultrasonic level probe is installed and tested
checkpoint-status | 5f78b038-53bf-41e0-83aa-4b5652e4d7d8 |  | checkpoint | Tank level and low/high alarms
checkpoint-status | 316091a7-e4ea-43ed-a21a-de39793fb1dd |  | checkpoint | Pump control panel (fault and run status)
checkpoint-status | 5e73582b-5584-4fae-a484-e95de56e58a2 |  | checkpoint | Pump operation (start/stop) performs as expected
checkpoint-status | f5c5f8ed-2c80-46a9-81cb-4fe08a138166 |  | checkpoint | Installers name & date works completed
text | 574ca23c-c9b3-5341-aaeb-ffb6d0babb58 |  | textbox | notes and photos
text | 0706e53a-13b7-51bc-ae6f-eeb6f2ae3db4 |  | textbox | Installers name
text | 9bab05f1-c71f-52e6-9ea2-b3a068ee38e6 |  | textbox | Date:
checkpoint-status | 126d03aa-a9f5-4564-ba0b-af2c6ea4b8ae |  | checkpoint | Tested by & date
text | 525ceb8b-e669-5a7c-a69f-01b9febbcb73 |  | textbox | Tested by:
text | d42bbef3-52d3-5743-a9e4-230b1184e26e |  | textbox | Date tested:
checkpoint-status | c7ed644d-f825-4c11-85e9-2f42bb6063d0 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | c66d8a4c-1baa-4c92-9bc0-26dc89b2adae |  | checklist | Testing - water meter |  |  |  |  | Yes | Testing - water meter | 21d0ba49-ecea-40d5-b4ae-7bbded5b8974
checkpoint-group | 3aa029d8-60ee-4b11-9d9c-592cc18acdd8 |  | section | Installer Details
checkpoint-status | 121d5b40-a292-4d5a-9713-502909c9b7fc |  | checkpoint | Details
text | e9efe6dc-138a-59e3-b2f9-e20c94791d32 |  | textbox | Installers name
text | 99f678ae-79fb-557c-a3c9-a049989961ec |  | textbox | Date:
checkpoint-status | a4aaef91-81dd-47dd-8459-2f99f007f8f7 |  | checkpoint | Tested by & date
text | 8bd2079a-ca3d-5e05-8eb3-2b39ff925ece |  | textbox | Tested by:
checkpoint-status | d43f6e2a-d813-4f94-bd48-f33fdbb1a9be |  | checkpoint | Confirm meter installation matches the approved construction documentation (drawings, equipment schedule / submission)
checkpoint-status | 7b3f222a-3a15-489c-a1c7-5ecc5950cf4d |  | checkpoint | Verify communication between the meter and the meter reading system
checkpoint-status | 1ef2d2d4-1a9d-4cb4-b1b4-cd23df9485eb |  | checkpoint | Discharge a predetermined quantity of water from a downstream outlet and verify the physical meter reading reflects the water quantity discharged.
checkpoint-status | c992d18b-60da-410b-a2f9-6002ac9456d6 |  | checkpoint | Verify with the central metering system that the remote meter reading matches the physical meter reading
checkpoint-status | 694f4daf-ead0-49c9-9002-eb62a1e8a81c |  | checkpoint | Repeat test at a second time on the same day and record results (both physical and BMS readings)
text | a3b1e5e6-a10a-502d-a106-db3499baec05 |  | textbox | Date tested:
checkpoint-status | 8afa15b3-1f9e-40a5-b4f8-5590e89b91c9 |  | checkpoint | Council inspector sign off and date
checklist-flat | 58f7b21c-a10d-4a5f-80aa-5c7401948ba3 |  | checklist | Hot Water Circulating Pump check |  |  |  |  | Yes | Hot Water Circulating Pump check | 282a1aaf-a40c-4c2a-9458-1369d34749e8
checkpoint-status | 176b7a59-c68b-442b-ae1e-fa330c2400ea |  | checkpoint | Pump direction checked
checkpoint-status | cde4db15-4bc9-4341-95a8-4ecb6f3e4282 |  | checkpoint | Clip Spacing to manufactures specs horizontal/ vertical
checkpoint-status | a6abb19f-821e-41d4-8c5d-a67544cafb8b |  | checkpoint | Valves fitted correctly
checkpoint-status | d2646522-b361-43ae-a8d3-80c2a1b2f8d5 |  | checkpoint | Non return valves fitted
checkpoint-status | fff7d673-2316-4e29-82ab-e68bc8bc5066 |  | checkpoint | Installers name & date works completed
text | b8c97cb8-5986-530a-8c7f-6fef7f2540c3 |  | textbox | Installers name
text | fec39d75-f17b-5d62-8036-075ba7415462 |  | textbox | Date:
checklist-flat | 593b6708-b346-4753-918d-afd7d13db405 |  | checklist | Second Fix |  |  |  |  | Yes | Second Fix | 32105e45-e602-418f-88ee-b4af09e12a0b
checkpoint-status | 3d90b99c-91a6-4e27-a2b0-99d416f9c88e |  | checkpoint | Area & substrate acceptable
checkpoint-status | 732ebafb-3f49-46de-8c61-7d8eefc7e100 |  | checkpoint | Seal around toilets/basins
checkpoint-status | d6e8d815-e84a-48d3-a034-a066085bdfdf |  | checkpoint | Basin waste checked for leaks
checkpoint-status | 2ccb3642-27ba-4847-b71b-69afa3c8fd89 |  | checkpoint | Toilet flushing correctly - No Leaks
checkpoint-status | 71c40113-192a-403f-8ff3-218241650f5d |  | checkpoint | Shower doors installed
checkpoint-status | 04508af2-7c26-4231-8056-6be91bb50643 |  | checkpoint | Kitchen tap installed
checkpoint-status | 21ff14b5-7214-4499-a07c-fa88d0cf91c9 |  | checkpoint | Kitchen sink waste checked for leaks
checkpoint-status | 8f274f62-7228-460e-bce0-e0a24db21e22 |  | checkpoint | Hose tap installed
checkpoint-status | 5b83c967-96db-4308-a2bd-94abaa6b9928 |  | checkpoint | HWC installed
checkpoint-status | bb308f5b-a40b-4923-994f-6f0afcce6291 |  | checkpoint | Floor drains cleared
checkpoint-status | bb18fd89-d66b-4c05-915c-5bf746b2a409 |  | checkpoint | Plugs supplied
checkpoint-status | 88484e2d-dd52-4d8a-a43a-2f2960e4493e |  | checkpoint | Temp valve set to 50 degrees
checkpoint-status | d8ad5e5d-764b-427f-94d8-127ee0466868 |  | checkpoint | Rubbish removed
checkpoint-status | 9c050a29-b5fe-4b9c-b02b-464a6d3a3d93 |  | checkpoint | Area is left clean and tidy (attach photo)
checkpoint-status | fe8c0a34-4572-4480-986e-76663ad1ab6d |  | checkpoint | Second Fix completed reviewed and approved
checklist-sectioned | 827a5c66-ea5f-4931-8825-b1fada3f9def |  | checklist | Waste tanks Checklist |  |  |  |  | Yes | Waste tanks Checklist | 3593833f-e1b3-4fa3-928e-8c7c7f8c10e7
checkpoint-group | 7e08c675-9cbb-4359-b385-8f2de1194c29 |  | section | Water reuse
checkpoint-status | 46600dcc-5171-424a-ab9f-6f28f2970575 |  | checkpoint | Installed as per manufactures instructions
checkpoint-status | 20d36fa1-bb41-4414-b96d-0a154b6f4d04 |  | checkpoint | TBC
checkpoint-status | fe06b234-db24-4f42-b2ce-eb459696f759 |  | checkpoint | TBC
checkpoint-status | 4d34a2a5-6887-429d-bba6-fdfed2e09861 |  | checkpoint | TBC
checkpoint-status | e5d34753-4dbf-4207-8c70-964f9225496d |  | checkpoint | TBC
checkpoint-status | bdd30fe3-ff17-4de4-8cfe-479cb4c64b21 |  | checkpoint | TBC
checkpoint-status | 98227f01-1f7c-42fb-9758-e3177c2f8dac |  | checkpoint | TBC
checkpoint-status | c504af5a-60ae-4d70-bc4e-b2036993ad4b |  | checkpoint | TBC
checkpoint-status | 293f959d-2499-446a-aa2f-0f5e0b23748c |  | checkpoint | TBC
checkpoint-status | 18a9d759-3f6d-4617-b796-830d5934f0de |  | checkpoint | TBC
checkpoint-status | 5c57564f-bba5-461a-95a1-09dd9fbfe296 |  | checkpoint | TBC
checkpoint-status | 5c8bac3c-afba-4ee4-98be-7fb324661b51 |  | checkpoint | TBC
checkpoint-status | 9470c527-1dbb-45be-a29e-1b6662b74892 |  | checkpoint | Installers name & date works completed
text | 776b26d2-2d4d-5e56-b591-ddb563ba84ce |  | textbox | Installers name
text | 6616e107-e41d-5606-8429-beaa85f7b892 |  | textbox | Date:
checkpoint-status | 4e6f2c7c-7851-4f82-a302-0371a95b8ff1 |  | checkpoint | Tested by & date
text | 827e0772-a30a-5e19-abc0-0624b78ce963 |  | textbox | Tested by:
text | d667d95d-dd6b-5d6b-9a79-6e7cb385ee0d |  | textbox | Date tested:
checkpoint-status | b811ba20-9562-4ee1-8a61-9bae22eb9728 |  | checkpoint | Council inspector sign off and date
checklist-flat | cf2787b7-b4d0-43fb-bb3b-2c84a79b4fe6 |  | checklist | Underslab Test |  |  |  |  | Yes | Underslab Test | 46f98510-cec8-4ed5-9b79-87a0a459c5d0
checkpoint-status | ca357f63-f580-4c90-bd70-bd03b6d92b37 |  | checkpoint | Flood Test in accordance with ASNZ 3500
checkpoint-status | 9bdc0d8d-2cc9-4bab-b97b-f084680d3b05 |  | checkpoint | Hydrostatic test Plug Removed By
checkpoint-status | e5dff736-d299-44a0-b285-03e271731bc1 |  | checkpoint | Inspection Cover Replaced By
checkpoint-status | 25797c5d-a699-4e57-a7f8-106f178483f3 |  | checkpoint | All pipe stubs covered
checkpoint-status | 63bfabc8-371e-429d-ba30-21657e48fe17 |  | checkpoint | Visual check & photos attached
label | 5bf45301-8c52-5ff5-8c0f-37ef96b82469 |  | note | Attach photos of completed area
checkpoint-status | 6e99a1fb-1125-4e07-b64e-23d8d62d734f |  | checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | 40e73753-060d-4609-8ac5-d89f1550da65 |  | signoff | Add Signature
checkpoint-status | 864acca1-5b0b-4e23-b29d-017a9c26d6e0 |  | checkpoint | Pre Line Inspection Passed - Witness
holdpoint | 49d5ab56-9411-4eaf-84ae-9d93e14f8428 |  | signoff | Add Signature
checklist-flat | 25a5a442-3a67-409e-87cf-054e02aca972 |  | checklist | QA - First Fix |  |  |  |  | Yes | QA - First Fix | 4aa48c26-73d4-46d2-8214-143d26b847c3
checkpoint-status | ec29e2fa-397a-47e9-ac7f-ce1b65ff0f5f |  | checkpoint | First Fix
checkpoint-status | 96411630-2e94-412f-8739-c13053c2528f |  | checkpoint | Waste Pipeout complete
checkpoint-status | a3600bf0-a33e-42a0-8c02-348aa1940f9c |  | checkpoint | Vent installed
checkpoint-status | f877ff6b-fe6f-422b-9c3d-9e00f1eea607 |  | checkpoint | Correct Fall
checkpoint-status | 5d700087-fdc7-41ba-80f4-9be014538bd8 |  | checkpoint | Correct Clipping
checkpoint-status | cc4bb4e9-dab5-4b5b-a9ee-d837ba31ab34 |  | checkpoint | Pvc sound lagged - where applicable
checkpoint-status | 1795bd7e-ec10-428c-9b34-499bdb7a1371 |  | checkpoint | Flood Test in accordance with ASNZ 3500
checkpoint-status | 2030ac7d-0fcc-44be-bf33-9363e31560ef |  | checkpoint | Hydrostatic test Plug Removed
checkpoint-status | 3bd73175-c8bd-4729-a197-99df0af020f4 |  | checkpoint | Inspection Cover Replaced
checkpoint-status | 29849327-2abd-4d2b-85ce-c93d9e1cac88 |  | checkpoint | All pipe stubs & FWG's covered
checkpoint-status | f650fd2a-7d76-4928-ab09-424c3ee29e8d |  | checkpoint | Visual check & photos attached
label | 8a2f2f7e-2a82-5612-9eb4-fdf0c5d2cf9f |  | note | Attach photos of completed area
checkpoint-status | 397a4d28-74d2-4e3b-8123-e3ff59bc0515 |  | checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | f0263fc3-0288-4870-bff3-548dd276576f |  | signoff | Add Signature
checkpoint-status | 88c29fc7-fe33-4ada-b765-8eae5c348bad |  | checkpoint | Pre Line Inspection Passed - Witness
holdpoint | 9ada4f61-8970-4742-b8f8-0f069aaaccc4 |  | signoff | Add Signature
checklist-sectioned | c6cbdf3e-037d-447c-9e1f-6c4f00a0e413 |  | checklist | QA - Waste / Stacks |  |  |  |  | Yes | QA - Waste / Stacks | 615fbd88-01ac-4813-8e4d-0af97c385f9b
checkpoint-group | 52bab7cc-13a7-4033-9482-33740bd3ec4c |  | section | Area Prestart / Acceptance & Drawings
checkpoint-status | c2033b7b-fa7c-4df4-be73-c2e95b484bbb |  | checkpoint | Details
text | a29464f1-3aa1-5153-bab2-fe9a84c98b04 |  | textbox | Zone / Area
checkpoint-status | ee5b6603-5031-4817-8b2b-2e76cfe5b78b |  | checkpoint | Area ready for works
checkpoint-status | 2399f2d6-222d-43d1-83bc-c44b700099dd |  | checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
checkpoint-group | f429c85b-7d2b-407f-bde1-ddb859be8e50 |  | section | Pipe install
checkpoint-status | 57042d36-582f-4b4d-b87e-d8b632648cef |  | checkpoint | IE's - Test points installed correct locations (ASNZS 3500)
checkpoint-status | 6910232a-1ca7-4679-bc9d-280977dfa3ac |  | checkpoint | Pipeout completed
checkpoint-status | ed930d9f-03e8-4b51-bb9a-4e0205903eb4 |  | checkpoint | Correct labels
checkpoint-status | 6f0c39a0-e3fc-437d-8868-82ccb997dc13 |  | checkpoint | Acoustic lagging
text | 1bfa5149-5c82-50f8-846f-855230bf912f |  | textbox | Product Type
checkpoint-status | fd07653c-2b1b-4c37-996c-18f06958d302 |  | checkpoint | Correct Pipe supports completed
checkpoint-status | 3b2fe00d-46d3-4b2c-887e-ab7cbe10a530 |  | checkpoint | Seismic bracing completed
checkpoint-status | 0b7112e2-e299-4d94-bd93-78f89a5a4b2b |  | checkpoint | Vent installed
checkpoint-status | 3e7c9f43-3c9a-44e3-8773-14252292cbe9 |  | checkpoint | Correct fall
checkpoint-status | 7a2e90ee-ce21-4a99-9620-ab572529fa1a |  | checkpoint | Flood Test in accordance with ASNZ 3500
text | 201fa136-939d-548f-a619-7d36f8cc9209 |  | textbox | Witnessed by
text | 9a8b3df9-d1ec-5fc9-ac7c-5f905ca3908c |  | textbox | Representing (Company)
text | 3722fb25-2a92-59f1-ab64-43669c98c106 |  | textbox | Date
holdpoint | 2e718117-0721-404f-a7e7-6ed13cf76388 |  | signoff | Request sign off
checkpoint-status | df3d96af-5940-4e09-9551-daf89f808323 |  | checkpoint | All relevant test plugs removed where applicable
checkpoint-status | a401ff09-8161-46dd-baaf-e93fba949d6f |  | checkpoint | Open ends sealed
checkpoint-status | f8693580-1d46-4312-bf71-abc4b841173b |  | checkpoint | General photos, comments and observations
checkpoint-status | 734ca6ea-a956-4506-80d4-4c226055ee85 |  | checkpoint | Pipe Install Completed
text | 273c58f6-07d2-52b9-9389-f92ef232fb86 |  | textbox | Installed by
checkpoint-group | ab2ad3c6-e5de-44cf-9640-52676bd2549a |  | section | Area Completion/Sign Off
checkpoint-status | a75cebc5-52cf-4cca-8c5d-0cf215eeef28 |  | checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint-status | 0e2ac520-088d-47d3-a206-8325836c29a3 |  | checkpoint | All Measurements Double Checked
checkpoint-status | fa2b766e-dcae-488f-a0ab-475a2a6d0a85 |  | checkpoint | As-Built Drawings recorded (drawing & revision number(s)
text | f8ec288a-afc9-502c-8b17-67f910d1cce6 |  | textbox | Completion Date
checklist-flat | 165e6444-ccd1-4939-b7e6-353dd0f57ad5 |  | checklist | QA - Gas |  |  |  |  | Yes | QA - Gas | 6b13629f-f2df-4ccf-be8a-2e0b44744c49
checkpoint-status | edce33a3-6b93-4a20-bc33-47ffa0f0fb6b |  | checkpoint | Pipe Work Secured in ceiling
checkpoint-status | fe958f0d-b091-4f5e-9b72-14d0e1a846f3 |  | checkpoint | Pipe Work Secured in wall
checkpoint-status | 9e4b6dcd-ce44-4d47-a5d9-1465a2c8ee5e |  | checkpoint | All fittings cleaned correctly
checkpoint-status | de5c065a-cba5-4eb5-b659-ab60be93857d |  | checkpoint | brazed correctly
checkpoint-status | 1504681c-68b0-466a-931f-da3260b433ca |  | checkpoint | Valves fitted correctly
checkpoint-status | 939f1bc6-ae94-4783-9ecf-0b60d4bd4ad8 |  | checkpoint | Fititngs welded
checklist-flat | c5ebf5ca-23f4-4bf0-a2c4-b684b533f816 |  | checklist | Urinal Test |  |  |  |  | Yes | Urinal Test | 700a7fac-aee0-434d-9a04-cc8cb789b182
checkpoint-status | 7fb8a8ae-f089-4e33-bd4f-94c73f9c6084 |  | checkpoint | Livening of the urinal sensor and solenoid valve
checkpoint-status | b5d372b5-c751-4f9a-b97e-1d8271165142 |  | checkpoint | Functional test of the sensing and flushing operation, verify access to the system components
label | a4e7c092-dc5e-5f69-9d05-b8c15b67bc33 |  | note | Attach photos of completed area
holdpoint | 47b6b5b8-10a3-4dbf-ba63-ac94a4e1010e |  | signoff | Add Signature
checklist-flat | 5a20a695-09ab-485a-8ec0-752ee1f0ceb2 |  | checklist | Testing - Hot Water Main |  |  |  |  | Yes | Testing - Hot Water Main | 7e44f690-b61d-4354-a8c4-c45d3d030453
checkpoint-status | 38ad7295-844a-4c84-acb3-2ce09cb25350 |  | checkpoint | Details
text | ad28a21b-ef50-53a2-95e2-67c34af52b8d |  | textbox | Zone / Area
checkpoint-status | 11ae0567-e55d-4b42-b506-687178bccf8d |  | checkpoint | Pressure 1500 kpa or as per spec
text | b9a01f32-9592-579d-92dd-6ce98b5cf818 |  | textbox | Duration
checkpoint-status | 3e16a6ea-d1c0-4d47-811f-21be38ab6214 |  | checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
label | 65d3c152-be83-533e-8277-f12a99d6c094 |  | note | Attach photos of completed area
checkpoint-status | 8a9badd3-38c8-4b02-945c-e785b11082f5 |  | checkpoint | Pre Line Inspection Passed - Foreman
checkpoint-status | a356ffdc-2cb0-417e-97a2-a4b96c7f733a |  | checkpoint | Pre Line Inspection Passed - Inspector
checklist-sectioned | f75b65d1-b561-41ea-9744-39e07575c05b |  | checklist | Water Pump Commissioning/test |  |  |  |  | Yes | Water Pump Commissioning/test | 7ef626df-9d66-4b3c-b518-d807c2afe666
checkpoint-group | 1aac965e-0e16-4c59-9465-238e3eda7c02 |  | section | Pumpset mainfold
checkpoint-status | c8ae8b14-bbe0-4197-ae93-93672e64972b |  | checkpoint | Connections welded correctly
checkpoint-status | 83ce30cd-0bae-41b4-9c87-2da3191334a5 |  | checkpoint | Clip Spacing to manufactures specs horizontal/ vertical
checkpoint-status | 14887eb0-8e8c-4d54-99fe-bde8b5435aae |  | checkpoint | Valves fitted correctly
checkpoint-status | 343dff48-5b24-4619-a56e-65bae6636052 |  | checkpoint | Line strainer fitted between pump & tank
checkpoint-group | 7be45f63-e16e-41b6-b527-6bf5e02ec333 |  | section | Pumps
checkpoint-status | 83c746e9-c0d0-4ecb-822b-d0afe45310e5 |  | checkpoint | Pump 1 Startup KPA
checkpoint-status | f5e07e77-f6ff-4190-99d6-ecaa0cd5e49f |  | checkpoint | Pump 1 kick out pressure KPA
checkpoint-status | 30e9ede1-e156-4bfd-8084-ac48226f6af1 |  | checkpoint | Pump 2 Startup KPA
checkpoint-status | 5da3a4cd-4efe-4aa9-9629-9673b0c64259 |  | checkpoint | Pump 2 kick out pressure KPA
checkpoint-status | d9adec92-6fb7-4513-b32b-85c53daff24a |  | checkpoint | Pressure vessell pressure
checkpoint-group | b00bf6f4-f17a-4906-8ecb-5513e6336cc4 |  | section | General
checkpoint-status | a324039d-ac66-4a31-9e9e-668d2baea79b |  | checkpoint | Mains water change over
checkpoint-status | 21537333-2de4-4929-aa09-f64b34f8c8c1 |  | checkpoint | Flow test pump
checkpoint-status | a9c7a29d-cdf2-4a62-8698-b7dd744d1894 |  | checkpoint | Pressure tests pipework
checkpoint-status | 46c2f445-eacf-4d9b-84f9-2baf073d7f48 |  | checkpoint | Visual check (for leaks form valves, tees, saddles, etc)
checkpoint-status | 0b8fb09b-2676-4d7a-8af0-5eef576cbd6c |  | checkpoint | Non return valves fitted
checkpoint-status | 384dae63-c37f-40f2-981f-54af1f2d1db7 |  | checkpoint | Installers name & date works completed
text | 758f2930-279f-5b80-8d15-88cfed1c032d |  | textbox | Installers name
text | 92a38230-02ea-59a8-8d10-fa30fd007b01 |  | textbox | Date:
checkpoint-status | 67185d34-f94a-4b47-9432-a19ee95ce9a2 |  | checkpoint | Tested by & date
text | 1e8e907f-a031-547d-bb30-2c599d040bcf |  | textbox | Tested by:
text | 36def8af-c1f8-57cd-a353-e5958cd09eec |  | textbox | Date tested:
checkpoint-status | 6cc420e4-b8d2-44fb-9fc9-786e349ba09c |  | checkpoint | Council inspector sign off and date
checklist-flat | 9905505b-1011-46b9-9303-6d42d3f18048 |  | checklist | Hot Water Cylinders |  |  |  |  | Yes | Hot Water Cylinders | 85e8a4e7-bbbd-4d6a-b156-1271e23b8d83
checkpoint-status | 4d57cbc4-a2c0-4daa-813b-7c31929e3d43 |  | checkpoint | All safety valves installed
checkpoint-status | 5424423a-8a24-4941-88ec-a17bb35a6851 |  | checkpoint | Seismic restraint fitted & wooden chochs installed
checkpoint-status | 8351d4d7-4bc9-4358-b216-35b177506747 |  | checkpoint | Check all tap connectors for leaks
checkpoint-status | 72fa2a5e-86fa-44f0-ac38-0c42436f677a |  | checkpoint | Operate cold water expansion valves / check operation
checkpoint-status | f97f3039-f463-4050-bf04-ed8c7ea07075 |  | checkpoint | Test TPR valve
checkpoint-status | e77aed51-de06-4c22-8a1d-ecb99d3ed31d |  | checkpoint | Check for cross overs
checkpoint-status | 0f36daeb-e11a-4228-a693-56e5ceee33da |  | checkpoint | Check HWC For Correct Valve Installation
checkpoint-status | db7a2f6b-17c1-4a1c-a8cf-d0f067e3c44d |  | checkpoint | Test overflow & safe tray
checkpoint-status | 4fbdd7bd-cabd-4b42-98a7-57ea5cfa3454 |  | checkpoint | Check Element Position on HWC Is In A Serviceable Position
checkpoint-status | af012013-08bb-4f0d-87ea-0d2c809812d0 |  | checkpoint | Check All Hot/Cold Pipes For Correct Position
checkpoint-status | 2b169e22-4872-48c0-bd62-f102eb32a6af |  | checkpoint | Set tempering valve temperature 55deg C
checkpoint-status | a87633d8-39a9-4845-a60c-3cd4f901bc28 |  | checkpoint | Thermal lagging installed
checkpoint-status | 99461e98-b2ab-4c9f-ac3b-e9032282482b |  | checkpoint | Installers name & date works completed
text | b857ca39-cde3-50bc-8189-327f713e0727 |  | textbox | Installers name
text | 871d4e07-860d-54d9-ab97-8083f41ebe85 |  | textbox | Date:
checkpoint-status | f384619c-a64c-4a37-a577-366d1f66a90d |  | checkpoint | Tested by & date
text | ec68a44c-1a93-57ad-8e27-791a5874f2d2 |  | textbox | Tested by:
text | 61b2a982-560e-5b68-92fe-ac113a75ce73 |  | textbox | Date tested:
checkpoint-status | 592d7ce2-c7af-4944-83d3-f12a4bc8bfc2 |  | checkpoint | Council inspector sign off and date
checkpoint-status | 04beab8c-d2a0-4d0c-a986-34d87e87f8f6 |  | checkpoint | Cylinder full of water before power connected
checklist-flat | b3331a3f-8e1f-4fa7-b1e5-9b29fb1a6de2 |  | checklist | Hot Water Circulating Pump test |  |  |  |  | Yes | Hot Water Circulating Pump test | 8950927e-e22a-4a7c-b51c-b8699f3b04ec
checkpoint-status | 708d596f-ae92-4625-aff6-098546895d2f |  | checkpoint | Pressure tests pipework
checkpoint-status | b861933c-5e7e-41d4-8183-6175bcc4fecf |  | checkpoint | Visual check (for leaks form valves, tees, saddles, etc)
checkpoint-status | 9e3245c5-996b-4365-b86c-59323b8aaf66 |  | checkpoint | Flow test
checkpoint-status | b16dbcf7-983f-4e5e-adf7-53a564ca9032 |  | checkpoint | Tested by & date
text | 2e13976a-c322-5865-9e91-b6a89ecd4c3b |  | textbox | Tested by:
text | 5fd23ce3-71a3-5f9d-bf63-3e0dc0bb1032 |  | textbox | Date tested:
checkpoint-status | 73811e92-181c-49ab-9fed-054d69154a63 |  | checkpoint | Council inspector sign off and date
checkpoint-status | ef164e30-4181-449a-a0d1-08fb41af2ac6 |  | checkpoint | Fusio pipework SDR11 test
checkpoint-status | 17012c45-0894-4dd2-8a15-5de6cf7b28ac |  | checkpoint | please insesrt test sheet from Alexandra park (Aquatherm NZ test record)
checkpoint-status | 88b00ea1-c77f-402c-8552-118da7187bed |  | checkpoint | underslab test
checkpoint-status | cc6da76e-9657-4726-a7a4-f734223cec20 |  | checkpoint | Flood Test in accordance with ASNZ 3500
checkpoint-status | ce045788-54ba-4c27-aecc-3f1ba01fd5dc |  | checkpoint | Hydrostatic test Plug Removed By
checkpoint-status | bb2c783d-6151-4a63-b55e-de390edadfaa |  | checkpoint | Inspection Cover Replaced By
checkpoint-status | 8b70c1a4-33ce-4dc0-92c3-c48f369c2892 |  | checkpoint | All pipe stubs covered
checkpoint-status | 710f7228-bf99-4c30-8322-7743ee743ee8 |  | checkpoint | Visual check & photos attached
label | 2be81f97-d905-56c7-a7ee-b71d249fa22c |  | note | Attach photos of completed area
checkpoint-status | f1e2fd17-6285-4a4c-805c-38d80d6ada90 |  | checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | 84751e1a-225d-4157-b76a-8a98e5d3c7e9 |  | signoff | Add Signature
checkpoint-status | 5706d2ec-9f06-484c-bbd3-222a4202218a |  | checkpoint | Pre Line Inspection Passed - Witness
holdpoint | e67c3724-44f9-4f62-a08f-1b1e2d1f295d |  | signoff | Add Signature
checklist-flat | dd392678-650f-45b9-8f70-bb9f2a778096 |  | checklist | Testing - Waste / Stacks |  |  |  |  | Yes | Testing - Waste / Stacks | 89d66d56-7f3c-4711-bbc5-c3a6a0ff2d5c
checkpoint-status | ae75a240-bd8e-43cb-a26f-be8b24bea00f |  | checkpoint | Details
text | 9c5f8c22-596a-569a-b4b4-5bc2a0d85d28 |  | textbox | Zone / Area
text | a79124fd-ba00-5551-aa0e-e61df118d847 |  | textbox | Area / Stack
checkpoint-status | 39bf06f9-c0de-4743-b6a3-85c359d6d35e |  | checkpoint | Flood Test in accordance with ASNZ 3500 (15.2)
text | f0cb2fc8-0c64-52c0-ae35-1815dd95f1ca |  | textbox | Duration
text | b931c44c-73ff-54db-b2c6-5d83a6627a4a |  | textbox | Notes
checkpoint-status | 876da5c2-4e01-4b99-a00f-5336ecc25065 |  | checkpoint | Install Tests completed, reviewed & approved
checkpoint-status | 1933d83b-ca04-44a2-b6dd-24f9dcc96ec5 |  | checkpoint | Local Authority Inspection Passed
text | d889db36-e2da-5dc9-98da-289def68f974 |  | textbox | Witnessed by
text | 00244f20-dff0-5f41-9c51-11de996a1771 |  | textbox | Representing (Company)
text | b9001a66-93a2-5dbf-8c59-b5231c452a38 |  | textbox | Date
checklist-sectioned | a2ec74fc-9cff-4a21-b1fb-8caf75cf787d |  | checklist | Waste water pump |  |  |  |  | Yes | Waste water pump | 8a8b1d3e-9b6e-4697-a73d-86638755b1b4
checkpoint-group | 5aa5350c-0c29-4dff-85a6-3a9d105c849b |  | section | Kitchen Sink
checkpoint-status | 3da9d625-451f-432b-9226-4e8b536067f7 |  | checkpoint | Installed as per manufactures instructions
checkpoint-status | db67c0ee-397d-4535-9d18-bdeb22f012b7 |  | checkpoint | TBC
checkpoint-status | a370d7cb-b197-4929-adbd-76275f47bc05 |  | checkpoint | TBC
checkpoint-status | 8fe1073a-0f68-4d48-91c7-4a54e32d602c |  | checkpoint | TBC
checkpoint-status | 6d7b1823-5408-4e7d-b012-100245cd1cbb |  | checkpoint | TBC
checkpoint-status | 950ba99e-fe8f-4484-8f12-593f59e245c4 |  | checkpoint | TBC
checkpoint-status | deef0df7-f3a6-4e9f-91d9-f3417cdbf559 |  | checkpoint | TBC
checkpoint-status | a9610182-757b-4844-b2db-3af0508110cb |  | checkpoint | TBC
checkpoint-status | f37bad8e-1653-4a71-9964-4c143b37df84 |  | checkpoint | TBC
checkpoint-status | 9d80be49-8d9d-4bf3-a35b-08ce9737f2c3 |  | checkpoint | TBC
checkpoint-status | ffb11c6b-de1f-4316-8df4-52656978d8bc |  | checkpoint | TBC
checkpoint-status | b9a31e45-ee46-4a10-8c79-2b8b2d83778e |  | checkpoint | TBC
checkpoint-status | b3681db2-35c6-4376-ba39-16f36a7e2848 |  | checkpoint | Installers name & date works completed
text | 860b75fc-8ded-5fc7-bdc5-8cb845c8d155 |  | textbox | Installers name
text | bb9d4cc9-1e22-54e5-83a4-4af7dc4e1629 |  | textbox | Date:
checkpoint-status | c6eb2486-0793-498e-8df2-99b18f232642 |  | checkpoint | Tested by & date
text | e3cfde33-7ded-55c9-bf5c-df48955b29bf |  | textbox | Tested by:
text | 4ee1d741-502d-5568-bfe6-65282489923c |  | textbox | Date tested:
checkpoint-status | df6e91f9-8d55-4fe2-b6c6-04f7d257dd5e |  | checkpoint | Council inspector sign off and date
checklist-flat | 879815bc-2d35-4146-9456-0d1f6acc0885 |  | checklist | Hot Water Cylinders Test |  |  |  |  | Yes | Hot Water Cylinders Test | 8abfb1ce-d396-4950-b2b6-3da9c5c58e36
checkpoint-status | 4abba905-03ea-4d7d-a9fa-02135ed36fa6 |  | checkpoint | release TPR and CW expansion valve
checkpoint-status | 1f2da30d-0024-40a7-83ec-0369070548e9 |  | checkpoint | Test overflow & safe tray
checkpoint-status | 45256bba-1e2c-470d-a9be-0760e7df48b2 |  | checkpoint | Set tempering valve temperature 55deg C
checklist-sectioned | db3311d5-7c62-4fde-8663-191453f94bb7 |  | checklist | Cold Water Booster Pump test |  |  |  |  | Yes | Cold Water Booster Pump test | 96954230-5219-46a8-91e1-fe3ee60b0cc3
checkpoint-group | 57d9d677-5459-4124-abe0-f100c143c620 |  | section | Zone / Area
checkpoint-status | a0becc77-e7fd-4e4c-b87f-8d26c9028726 |  | checkpoint | Details
text | 2557c498-12cf-5f02-992a-d8c85601d7f9 |  | textbox | Zone / Area
checkpoint-group | a43e7940-2213-47c8-9fd8-ce9389090803 |  | section | Pumpset mainfold
checkpoint-status | 20b8dca1-03bb-420a-b270-151ad0f80609 |  | checkpoint | Connections welded correctly
checkpoint-status | 696a419a-ad3b-4461-98da-2bac24c9eefa |  | checkpoint | Clip Spacing to manufactures specs horizontal/ vertical
checkpoint-status | 09cb9a2f-c93b-4f7c-8e0d-e105051ca4ed |  | checkpoint | Valves fitted correctly
checkpoint-status | e9f3cce4-c1ad-4b0e-948b-f69d44cc8f27 |  | checkpoint | Line strainer fitted between pump & tank
checkpoint-group | d95ad585-54b3-4413-b349-7a49e6235f94 |  | section | Pumps
checkpoint-status | 93034ca4-6f52-41c4-9c93-b5fe1d706c5b |  | checkpoint | Pump 1 Startup KPA
checkpoint-status | 55d021f2-4d6e-43b8-9090-9febf7a1773a |  | checkpoint | Pump 1 kick out pressure KPA
checkpoint-status | 126a4aab-d277-48f1-965e-5a03a812f8c1 |  | checkpoint | Pump 2 Startup KPA
checkpoint-status | 6103beb5-bae7-4083-9a0b-5c374252efe0 |  | checkpoint | Pump 2 kick out pressure KPA
checkpoint-status | 738b1bfe-8151-431c-aeca-963187d4fc73 |  | checkpoint | Pressure vessell pressure
checkpoint-group | 26ee97a8-046d-4a43-b7a2-cb543f87942d |  | section | General
checkpoint-status | 85536256-1cc3-423b-a42c-520161ee9caa |  | checkpoint | Mains water change over
checkpoint-status | 528c6996-0cd8-4142-8bb1-b6dc7368654e |  | checkpoint | Flow test pump
checkpoint-status | 63acb064-45a4-43a8-8dae-c0cff6eef27f |  | checkpoint | Pressure tests pipework
checkpoint-status | a4ee54a4-bcb9-41aa-bb34-6933f0d49a88 |  | checkpoint | Visual check (for leaks form valves, tees, saddles, etc)
checkpoint-status | 1d27627e-a5f4-4d60-8efd-d97364588178 |  | checkpoint | Non return valves fitted
checkpoint-status | 2bf6e8cd-6ad8-4e23-a8ce-ca78d3035016 |  | checkpoint | Installers name & date works completed
text | 5c540fb5-27d0-5d35-8082-a44dc56bf652 |  | textbox | Installers name
text | 0b616b70-8dbd-55ea-93e5-37635280db78 |  | textbox | Date:
checkpoint-status | 37b537a8-e73a-4cde-a985-5f45de4361ff |  | checkpoint | Tested by & date
text | 9a8e74ba-62b7-564b-886c-0fb5cde3cacc |  | textbox | Tested by:
text | f4f59766-36b5-5e91-ade7-d38009a9f19f |  | textbox | Date tested:
checkpoint-status | df5a67ec-c49a-434d-9d97-8b2593c136d1 |  | checkpoint | Council inspector sign off and date
checklist-sectioned | 2f41503c-8b62-4912-a33b-73626922ad09 |  | checklist | Cold Water Booster Pump QA |  |  |  |  | Yes | Cold Water Booster Pump QA | 9dd6badf-1bbf-4905-a587-5258d032e241
checkpoint-group | 0a1d78bc-01d7-4467-a7a2-45dea61e3c25 |  | section | Zone / Area
checkpoint-status | 936da3d8-2f39-49e2-bdf0-bb3b541d3077 |  | checkpoint | Details
text | b537ac7e-2b0d-5cb6-9c4f-f8ea1ddac0d4 |  | textbox | Zone / Area
checkpoint-group | 3f87a138-90a8-402f-be55-4251b3e92e19 |  | section | Pumpset mainfold
checkpoint-status | 51d60ad9-2cf0-443c-b643-8c006c683cfa |  | checkpoint | Connections welded correctly
checkpoint-status | 518d4441-76f3-4bc2-a71b-68d18504117a |  | checkpoint | Clip Spacing to manufactures specs horizontal/ vertical
checkpoint-status | f451052f-a2c7-4456-abdf-aa70f75e6896 |  | checkpoint | Valves fitted correctly
checkpoint-status | 233e5bdb-186d-420f-84f7-6fe4107d1540 |  | checkpoint | Line strainer fitted between pump & tank
checkpoint-group | 5160c232-2150-401e-820c-5a966a175df9 |  | section | General
checkpoint-status | df4d8302-4b98-43f7-a038-1a6e88dd864f |  | checkpoint | Visual check (for leaks form valves, tees, saddles, etc)
checkpoint-status | a1569e94-8a3d-4452-bd94-185f7de0328c |  | checkpoint | Non return valves fitted
checkpoint-status | 092976b6-72da-4423-adc0-d95e077d6ddb |  | checkpoint | Installers name & date works completed
text | f2c3091f-b363-5df6-9fb0-a5db868302cd |  | textbox | Installers name
text | 79586dd8-cd9b-5a69-b4f7-d9d391a2222c |  | textbox | Date:
checkpoint-status | 6c84cbf2-e283-4de6-aa8e-b3408d2f1a03 |  | checkpoint | Tested by & date
text | c51a1ee6-7a89-5841-9af7-edcac1f82e8c |  | textbox | Tested by:
text | becaec8d-c17f-5813-aad9-830c8f7aa44a |  | textbox | Date tested:
checkpoint-status | d2c4be21-ea17-49a9-bfaa-a5cd0ff4be1a |  | checkpoint | Council inspector sign off and date
checklist-flat | 3d8ae2b6-6284-423a-8567-e019de388045 |  | checklist | Testing - Cold Water Main |  |  |  |  | Yes | Testing - Cold Water Main | b0353419-cd08-438f-98e9-072d432848da
checkpoint-status | 87b64b0b-f6c3-4f48-bde6-e186c3bb7584 |  | checkpoint | Details
text | d8aa8b0f-c74e-56a9-a2ae-1707bedcf953 |  | textbox | Zone / Area
checkpoint-status | a7a796ba-0cc1-4ee4-8919-dd177f8011d1 |  | checkpoint | Pressure 1500 kpa or as per spec
text | e34213e8-0f3c-51b6-9956-13418db94a2f |  | textbox | Duration
checkpoint-status | e16628aa-f706-4213-a751-6c8bb271e5c6 |  | checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
label | a8e42958-dacd-5574-aea3-1eb202d468b1 |  | note | Attach photos of completed area
checkpoint-status | b257d2fd-335e-4d7c-8d1b-d7f086718e54 |  | checkpoint | Pre Line Inspection Passed - Foreman
checkpoint-status | 43066205-87e6-44cf-b024-5972e724089a |  | checkpoint | Pre Line Inspection Passed - Inspector
checklist-sectioned | 93190f20-cc8d-419e-aa95-43b0e3b0ebcc |  | checklist | QA - Basement Underslab check |  |  |  |  | Yes | QA - Basement Underslab check | b71ed7ae-2be5-4f43-8a8b-4c45306697a2
checkpoint-group | 258ac990-8f27-4763-a48d-78f240e2a636 |  | section | Area Prestart / Acceptance & Drawings
checkpoint-status | 6889f97c-cfeb-49ad-b9b7-f13597fa2c6f |  | checkpoint | Details
text | 67858437-0676-58dc-8869-d38acdd475af |  | textbox | Zone / Area
checkpoint-status | 1c2d4596-a05f-4504-a2b9-2dc0005a0435 |  | checkpoint | Area ready for works (grids setout, area accessible and approval to start)
checkpoint-status | 46e69fb8-fd92-4b9c-b987-59ef99087293 |  | checkpoint | Current Dimensioned Slab Set Out Drawings numbers and revisions recorded
checkpoint-group | 691349b1-09e4-487f-9be8-0f353c298c74 |  | section | Under Slab Pipe install
checkpoint-status | 54b94dcb-7aac-4e09-be33-801818f4e9bc |  | checkpoint | Install Tests completed, reviewed & approved
text | 412d85ca-9872-5640-82b8-4c64b33adb1f |  | textbox | Test method used
text | a51a766d-0564-5fd9-9568-9ecec5e653b6 |  | textbox | Duration
checkpoint-status | b618fbca-5073-4b30-9517-008e0e4a3656 |  | checkpoint | Local Authority Inspection Passed
text | 5fb1ccb5-48e9-5c2e-95f3-2890bc120f34 |  | textbox | Witnessed by
text | 3521c077-f590-5602-95fc-bc74e5d71370 |  | textbox | Representing (Company)
text | 1c03581a-05e9-50e2-b966-64e1e473f5e5 |  | textbox | Date
holdpoint | 6d523dae-a2b8-4a49-9128-e15118153550 |  | signoff | Signoff required
checkpoint-status | 93ae9dbb-6c8c-4702-9d20-8b5f09f9abb5 |  | checkpoint | All relevant test plugs removed where applicable
checkpoint-status | a644183d-0ba6-4467-a7af-4fc4a22f51a2 |  | checkpoint | Open ends sealed
checkpoint-status | 418e1899-2707-4089-ae6b-2ed694f3a7d0 |  | checkpoint | General photos, comments and observations
checkpoint-status | 58921df1-514a-4162-9976-0b0ad3576938 |  | checkpoint | Pipe Laying Completed
text | 6de19ff2-cb99-59fd-9d0f-f5a3bf7649eb |  | textbox | Laid by
boolean | 86d25233-9616-5715-b94f-586d1c522c63 |  | tickbox | Bedding Sound
boolean | 4fc0a9f6-d0d5-54fb-8357-33add3573ed4 |  | tickbox | Soil Removed
boolean | 3d9cccdb-9b5c-5537-9238-131b4b0f3ab2 |  | tickbox | Trench Compacted
boolean | 0d0da319-faba-5098-ad46-a65788613e99 |  | tickbox | Hard Filled
checkpoint-group | b8850cef-ddb4-4439-8407-36c2980c4505 |  | section | Area Completion/Signoff
checkpoint-status | 3e2533fc-31c7-465f-ba66-af56a0e55bdf |  | checkpoint | Specified Protection Around All feeds/pipes penetrating slab
checkpoint-status | 27f4ba4e-b00a-44e0-856a-c7dd903dd13e |  | checkpoint | All Measurements Double Checked
checkpoint-status | 050850a8-d801-4c0b-9afd-416cb9f9d4b0 |  | checkpoint | As-Built Drawings recorded (drawing & revision number(s)
checkpoint-status | a2d4d0a7-3f57-4051-b2da-ec7dd763ba95 |  | checkpoint | All relevant under slab works completed, reviewed and approved
text | 14097450-c2ab-54b3-8c7d-dbdfd41b77f5 |  | textbox | Completion Date
checklist-flat | 39625590-8bc2-497b-ba99-f287e4354560 |  | checklist | QA - Hotwater Checklist |  |  |  |  | Yes | QA - Hotwater Checklist | bc74bb80-2285-43d6-94a1-7a29eb144b3c
checkpoint-status | db1f0495-3608-4bcb-9cd7-ea990b8244eb |  | checkpoint | Connections welded/crimped correctly
checkpoint-status | 34427819-8baf-4495-9c20-f2a9eb4dff1d |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | e6fd13dc-5868-4f4e-ad75-58d0af19b618 |  | checkpoint | Checked for crossovers
checkpoint-status | 43dae667-5036-40d3-b60a-719117bc516d |  | checkpoint | Lagging installed and neat
checkpoint-status | 436c48e9-420e-45ad-8c32-f49c2d9a3532 |  | checkpoint | Labels installed
checkpoint-status | 9eb23b48-56af-457f-a2f8-86145c8e6454 |  | checkpoint | Correct valves fitted correctly
checklist-sectioned | 189078cb-7dfb-42b0-b4c7-5e86ab558a47 |  | checklist | Hot water main |  |  |  |  | Yes | Hot water main | ce1fb316-6ea9-4850-8ff2-d92901542f69
checkpoint-group | 779db6e5-3a2f-4b20-a697-47d45088575e |  | section | Hot Water
checkpoint-status | 1dca6864-ccc7-4ef8-a800-dbf69d94412f |  | checkpoint | Connections welded/crimped correctly
checkpoint-status | 56a23159-163a-4150-af96-1c93e8fb5f62 |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 8848d891-8b17-44cd-9588-6639d3fd78ae |  | checkpoint | Expansion loops installed
checkpoint-status | 002593fc-fb0b-4d32-8ab2-9020b01c3d5e |  | checkpoint | Lagging installed and neat
checkpoint-status | e8abf5aa-3126-4900-bd73-39764525537f |  | checkpoint | Valves fitted correctly
checkpoint-group | 8cccf2a2-a852-431e-ba4d-d90ca8045c15 |  | section | General
checkpoint-status | 71e89a33-6333-4ae1-88a9-fa43488d43e4 |  | checkpoint | Open ends of riser capped for testing
checkpoint-status | b9ad8a1d-677e-4e07-a1f1-1e3d2054ddc0 |  | checkpoint | Checked for crossovers
checkpoint-status | a1a6e7ec-52d1-4ea2-88c0-5b45a67ddc74 |  | checkpoint | Tidy work areas
checkpoint-status | 5b538ddb-f927-438f-af5d-2f585ceadf65 |  | checkpoint | Pressure/ Bounce test to fusiotherm specs
checkpoint-status | 2fc419ae-f969-45f6-ae28-5d28e85c06cd |  | checkpoint | Visual check (for leeks form valves, tees, saddles, etc)
label | db23bc31-4765-5275-bfbf-aa525a1ac164 |  | note | Attach photos of completed area
checkpoint-group | 00f94428-b6f6-414d-bd5d-3531401d712b |  | section | Pre Line Inspection Passed
checkpoint-status | 318d2590-43a3-4109-958f-dc8f187833eb |  | checkpoint | Pre Line Inspection Passed - Foreman
holdpoint | a9ad772a-5557-411c-9003-66874de79741 |  | signoff | Add Signature
checkpoint-status | e020c302-201f-489a-b4d0-e1c919fd775a |  | checkpoint | Pre Line Inspection Passed - Inspector
holdpoint | 156c344c-b478-49a4-a628-1773add93067 |  | signoff | Add Signature
checklist-sectioned | aadb8559-fd32-431a-8a32-591b3d9e00b2 |  | checklist | Under sink Pump test |  |  |  |  | Yes | Under sink Pump test | ea178fd6-2d98-4383-ac08-d143ce4e2702
checkpoint-group | 36c115f1-7eaa-473f-949d-0752ca1da51b |  | section | Unit check
checkpoint-status | 7d8469f8-73e2-49b2-98e6-11c5834f2a11 |  | checkpoint | Area acceptable and ready for work to begin
checkpoint-status | 6451b818-76a1-4258-89a4-7aacdb4e9729 |  | checkpoint | Pump mounted on base, & housing condition good - no leaks
checkpoint-status | 046cb35f-cce0-4703-ba48-432487ed9de0 |  | checkpoint | All isolation valves set correctly - non return valve, isolation valve
checkpoint-group | 5f4058e6-eca4-47d0-b223-bd479e45af95 |  | section | Electrical
checkpoint-status | fb207b79-e466-421e-9c34-322a3480609e |  | checkpoint | Local isolator located
checkpoint-status | b6221a9e-c504-4c69-9861-2fa627b0bd89 |  | checkpoint | All power and control wiring correctly installed
checkpoint-status | 0aa4b8ca-d21e-47a0-bb6d-19d1aa5ce9c2 |  | checkpoint | All electrical connections correct and tight
checkpoint-status | 11a3dd35-8498-4f10-b66c-ba55311d050c |  | checkpoint | Controls point to point check completed
checkpoint-group | 443712ac-8872-4e34-a00a-b578225ba6cd |  | section | Float levels
checkpoint-status | 7f175649-76e7-48fa-82db-927c6e60fd9c |  | checkpoint | invert - low level alarm
checkpoint-status | 0a83ad69-8213-44e7-96dc-8cae7dea43ef |  | checkpoint | invert - mid level for dual pump operation
checkpoint-status | d0aea7dd-5da1-4efb-a678-663bfa01c9ba |  | checkpoint | invert - high level alarm
checkpoint-status | 9a78ec73-9ad3-47d6-8f07-ba9c8ee8dca2 |  | checkpoint | Rail / lifting chains installation
checklist-flat | 1d5b8523-4ffd-4590-8cc7-6c6807e1d59e |  | checklist | QA - Coldwater Checklist |  |  |  |  | Yes | QA - Coldwater Checklist | ed5137a4-9dc5-42e1-a9fe-b20e3bbd9876
checkpoint-status | f6ba777a-66e6-4b9c-95bb-51a9dbcc3e7f |  | checkpoint | Connections welded/crimped correctly
checkpoint-status | 6d16102f-bd6a-43ed-b5e0-8426799f7907 |  | checkpoint | Clip spacing to manufacturer's specs horizontal/ vertical
checkpoint-status | 0eecb1c3-ee9d-4158-bd78-c82d97e202b6 |  | checkpoint | Lagging installed and neat
checkpoint-status | ced98ea3-ff6f-42cd-9a75-4990c5dd4c57 |  | checkpoint | Labels installed
checkpoint-status | 5ff8b448-23ae-435c-869c-19a6dc7b280b |  | checkpoint | Correct valves fitted correctly
checklist-sectioned | cd71fcd9-2cbc-4df2-aee9-9ebe3de49b05 |  | checklist | Gas Reticulation Test |  |  |  |  | Yes | Gas Reticulation Test | fc43d695-0e31-442b-94fd-99a8470b764d
checkpoint-group | 8b5a7b1a-b31a-40a6-b35a-ee1c77361d03 |  | section | Details
checkpoint-status | 82392bf8-de19-484e-bebc-5302057815d4 |  | checkpoint | Client and Installation Details Confirmed and Logged
text | 6fa6c29e-03bb-5d9d-a428-98a7f4da4c0a |  | textbox | Client
text | adc9900d-d17c-5dac-848d-2b1a5f85fc99 |  | textbox | Client Address
text | 0225ca69-bce7-5af1-ba1e-3936ec2aef27 |  | textbox | Installation
text | d050d2f5-6046-5a0f-bda2-68b828fcd8ab |  | textbox | Installation Address
text | f48a2431-1362-577c-b167-ceebe855e7e5 |  | textbox | Description and Location of the Gasfitting
checkpoint-group | c29d959e-3b0a-430c-9506-c7972011df63 |  | section | Gas Details
checkpoint-status | eabdc93c-3fb8-470f-943a-207654491a83 |  | checkpoint | Gas Details Logged and Tested
text | 8db85d41-0c33-573d-9352-23a7d7f72dcf |  | textbox | Gas Type (LPG or NG)
text | 235f5ab5-63c7-57f1-a314-9414c0448361 |  | textbox | Gas Supply Pressure (Kpa)
text | 9e3b71e8-b9d3-5718-a2a5-5eab5250a95c |  | textbox | Date(s) Gasftiting Performed
text | 24da73e6-64c2-55bf-a724-fe83ef572c95 |  | textbox | Date of Gas Connection