## Symal Infrastructure__CC0371 Pa
Step Id | Warnings | Rich Type | State | resource | type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4
da115af4-b8d4-40ea-8310-0718e3f0e0fd |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction
faf0f822-577f-4542-a72e-763cd4be25af |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1
d26b2756-0622-49e1-8a89-8e2bdfdcad87 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A
50e09560-cb59-451c-8d2d-e2a690c43360 |  | folder-normal | pass |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works
afa21860-d25a-478c-8fdc-b8b034bd4d45 |  | folder-normal | pass |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Proof Rolls
1daff1db-5438-45a5-96ac-68b998f19054 |  | checklist-flat | pass | SYM-Proof Roll Record | checklist-flat | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Proof Rolls | SYM-Proof Roll Record Lot 1
192618bd-f7c4-50d9-a924-77d42e5b2a65 |  | checkpoint-no-status | no-status-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Proof Rolls | SYM-Proof Roll Record Lot 1 | Details
07aeb44f-46a1-571c-97d1-195dc4519c73 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Proof Rolls | SYM-Proof Roll Record Lot 1 | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
5da460a1-8215-5532-9b6f-5ecf92afd02d |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Proof Rolls | SYM-Proof Roll Record Lot 1 | Request Sign Off
81a67d3b-2b3b-40af-97c8-02062352828b |  | folder-normal | pass |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1
c94da3f3-95f0-4cd8-bd41-7a6ced757b64 |  | checklist-sectioned | pass | 60406081e2570c3b9b12945dc12e2bbf3492079dcacab745f76d98f768b688f3 | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A
a9efba5d-7259-540e-8de4-a515bc86987d |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries
8a19e8f0-9485-5bc1-b5e2-a51daa7f910f |  | checkpoint-no-status | no-status-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | • What is the lot size? Maximum lot size = 1 days production or 4000m2 (Attach markup if Available)
e6fdbf73-f474-5618-88df-a46fe35b0006 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | • Has the work area been set out for line and level?
83a26123-cb4b-509f-ab77-d35589c18804 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | • Has the material being excavated been inspected with category agreed upon by Superintendent?
830a286a-5144-5ccf-8779-14182c3436ac |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | •Attach Imported material test report (If Available)
58bbf49f-59f6-51d0-baa1-85ca5c0ce14f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | •Is Material Approved By CYP D&C JV
89c653d0-e333-5eae-bc57-d6874ba7db91 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | • Attach latest IFC Drawings
687011f7-23fc-5497-89dc-95878cfe0cb0 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
97a4bbc9-5976-50cf-b23b-4d88f885a759 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | •Is the area in cut / fill / both?
c8d3bb14-afbf-5b5d-8ec9-880cd7ffefa8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
19580434-797e-52c4-90bc-7a419d63bedd |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 1.0 Preliminaries | Request Sign Off
769b5b41-37fa-567e-86b0-6fbb274cee73 |  | checkpoint-group | not-applicable |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut
80a6c798-0e2e-52eb-b896-2ec191c84bd0 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Has the cut surface been trimmed to an even surface free from loose material?
63d124a0-1d56-547d-a205-b86f4e2167f1 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action.
8f05af18-2aef-523a-88ce-2c7c879693fc |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
640e3528-daec-56ec-ad8b-774eedbc6e21 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Has all approvals to proceed acquired?
fc378550-f287-59ce-8cc4-f16d152fac85 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Is Dewatering permit Completed (if applicable)
3f55d504-5e2f-5fc5-ae81-f3b3645a9cd2 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
4cd6cac2-3ece-5b48-9360-39f26d7f6bd7 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Has the subgrade been adequately compacted achieving a mean value density ratio of 98% Standard? AttaTest reports (If required).
52bcf0e3-2b6e-5b30-a012-deb326bffd3f |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Does the layer withstand test rolling without visible deformation or springing?
5720351d-03aa-574c-a24e-3afaf32945b6 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Complete Proof roll report, attach or add to lot.
1e1de5d7-f8b9-5b06-bde1-849da8c6a463 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Attach Survey report of area
d5804528-7387-5c22-9c97-28362e457eaa |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Has rectification process been submitted to the Superintendent for review?
dfadc29a-15a7-5baf-aca8-5b234dac5784 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water.
750f2076-1d2e-5550-8160-a873b3ab7e9e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
e4b7f13c-6117-5b9b-8658-78ffced27c64 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | • Attach site photos for all stages of works.
7c823b54-bf9b-59fd-b721-a6d5509163c6 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
18f90005-349a-5ea3-93e5-69ed8459e74c |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 2.0 Bulk earthworks - cut | Request Sign Off
efcc59cd-82bd-56fd-9b5c-d0b27444595c |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill
d570deed-0e93-5b0c-98b3-150f7370bf44 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
164bf5d9-4a72-5a2f-94ce-f517b1b0ba5b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | •Attach fill Material test report.
8fb06802-1079-5ee4-bc6d-bf30fc1aad9c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Complete Proof roll report, attach or add to lot.
4ccde7e8-5176-5148-a55b-d79c1604a9e5 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Attach Survey report of the area of works.
e7b97e18-dfe3-5106-919d-c5b156d46c16 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Has rectification process been submitted to the Superintendent for review? (If Required).
2d72e912-c961-53b2-928f-7fcc4976e0d5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
f0277191-64c4-5561-84a1-415fbb2b9545 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Has fill been placed in maximum 200mm compacted layer thickness?
8dc5bce4-094a-559e-aef6-1c42229ccb97 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Attach as built report of the area of works.
c88c35ab-67fd-5c1a-b965-b4f4fba598c0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction? Attach Test Report
1ec17948-756f-57e8-9243-6c37861edeb9 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Has the layer been adequately compacted achieving a mean value density ratio of 98% Standard? Attach Test Report
090069a9-d96e-57a5-ba88-51c838bb1f20 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041?
9b0b8191-338c-57fc-ab5a-5eea62daf5e7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | •Confirm If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested (Attach Test Reports)
c407ca11-daae-560a-be83-24463cc4ac1b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Does the layer withstand test rolling without visible deformation or springing?
dbc84219-7491-52a5-b382-6e61c84b50c2 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Attach Survey report of area
c66113f9-d612-5632-8aca-c6958ec26e6c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | • Attach site photos for all stages of works.
b6fc7c9d-f8bf-5e0f-b92b-759818e8cba0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
ea567795-dea0-5a3f-8525-1e2b4e9d2384 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 3.0 Bulk earthworks - fill | Request Sign Off
587c8dce-f5cb-5c0e-a30c-b7c347880e12 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check
fb5d813b-fb78-5928-8649-0956dacf9bf3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
441182f7-2b76-53dd-8253-4d0ecb6f283b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements?
5de5126d-4df4-59c3-a393-8a163dcefa28 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | • Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm
cff519c2-0e85-53fe-a284-5c4985155ae5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | • Attach as built report
527ddc10-1fa9-557e-ad3c-023b15450388 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | • All Test reports received and reviewed.
f1bda34b-befa-5287-bf3d-611816178dc6 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
e69798ca-553d-5192-857d-d8902c220c0b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
a27c4e48-1b88-54c9-addb-be4d5887fb27 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1 | SYM-ITP-001 - Subgrade (Rev A) - Zone 6A | 4.0 Conformance check | Request Sign Off
84bf4c49-a5e9-4321-aebc-af084938b766 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 1) ITP-001 - Subgrade Works | Lot No - SYM-PURL-SUB-6A-1
0b2e3d97-6b43-4368-8b3a-838a9ac2ae50 |  | folder-normal | pass |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works
dfbd9910-a5e5-4d2e-a05b-bff1e9e38363 |  | checklist-sectioned | pass | SYM-ITP-002 - Flexible Pavements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1
08a53f1f-7583-57c6-b619-43b963564bdb |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 1.0 Preliminaries
ecf664c7-29d2-541f-aeef-f8479faabaf4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 1.0 Preliminaries | • Has the work area been set out for line and level?
183bbed9-41a2-5ac4-8124-9e0b947c964a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 1.0 Preliminaries | • Has the previous layer passed acceptance criteria?
33a2e586-2f2a-5b4f-ae0b-727f47d2178c |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 1.0 Preliminaries | Request Sign Off
a97fe3da-bb64-5731-8e1e-0fd93ad3f54a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 1.0 Preliminaries | • Is the correct material being used?
7ac9105c-bd5d-525b-9c94-b8caff5d46a5 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 1.0 Preliminaries | Request Sign Off
f5a1659c-29d9-5955-bd9c-ea70eaca7a45 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 1.0 Preliminaries | • What is the lot size?
1e0bc363-5b05-5a15-ac55-a13fbfb6464d |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction
196f6e57-8b1f-56c6-bb5c-f0c3d3396c24 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • Is the pavement intended to be Lower Subbase or Upper Subbase?
32fecfa7-e85d-5a6e-8d9c-ba080e3ed999 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
a24f7caf-6282-5058-b84a-aab4813acbc0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • Place and compact layers so that the surface finish is smooth and uniform.
6624d72c-0461-58cf-8d78-04c43423bf31 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | Request Sign Off
53646d0d-b4c7-5507-b7ef-bc9d7153a8dc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
ad3faa07-ed6f-56b7-9806-a59ab24d0cc2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • Area shall withstand test rolling without visible deformation or springing.
4007d53f-6abe-5085-86c6-cb22cc465025 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | Request Sign Off
d8f312e2-5b53-5fdc-a922-fd43e6fb7ea6 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • What quantity of soft, wet or unstable material is present?
20de5d94-dab9-55ab-a55b-060351c135e5 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • Has rectification process been submitted to VicRoads for Review?
4e465f46-a2f4-5a24-a87a-7154655f7d3f |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | Request Sign Off
b0bf7069-918c-5e06-8d01-399a5befdc40 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
21c8cd20-e2ad-57d2-8ddb-5ed0eed89918 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 2.0 Pavement Construction | Request Sign Off
5df73b9a-4d3b-53b6-870e-970cf36fe625 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 3.0 Testing
604deee4-4c0f-54c9-a5ca-563d5387ec8c |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 3.0 Testing | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
ad923d15-87d3-5f5e-878a-ce6a9320730c |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 3.0 Testing | Request Sign Off
e29897ae-678f-546b-aedf-47d597d59e9e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 3.0 Testing | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
1285fd85-96c9-569a-b103-2725966b8869 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 3.0 Testing | Request Sign Off
0919e08d-1463-5873-87fc-f314b3064688 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 4.0 Completion
a767bb60-7974-5f06-acfd-80d51633e0dd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 4.0 Completion | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
caf6de1d-06bf-589c-9ed3-217c4936b458 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 4.0 Completion | Request Sign Off
dca79f8d-365a-52f1-89e2-63f8c3f8d8f4 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 5.0 Work Lot Close Out
79bad27b-7fb0-56bb-ab8b-1518b76c01f1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 5.0 Work Lot Close Out | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
9a29148c-202e-545b-a41e-f77ef848b8ce |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 2) ITP-002 - Flexible Pavement Works | SYM-PURL-PFLX-6A-1 | 5.0 Work Lot Close Out | • All Product Non-Conformance(s) recorded and closed (if applicable)
3ccb05f5-59b0-4ba1-9327-b06853c130a8 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing
3f516b66-3e21-44d6-8784-07a7018f964a |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1
418cfcea-4492-40e4-b48e-fec7e8d905df |  | checklist-sectioned | work-in-progress | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A)
2b955fa0-e732-59d3-8384-147a2a656f4c |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities
84420711-f71a-50dd-ace2-2f8132f479e0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | • What is the lot size?
f8e60f1e-9617-5e29-8dd7-d64fcd9e68fc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | • Is the asphalt mix design considered “General” and does it conform with VicRoads Section 407? Has mix design been approved by CYP D&C JV?
3038f269-6258-5326-8842-9234dee80c38 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | Request Sign Off
620203e2-8aa4-5c69-bdb4-d2961e95c0a5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | • Has the previous layer passed acceptance criteria?
1e542cb6-2480-5d04-96c6-dd4477904d2f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | Request Sign Off
9de82e64-05c8-5ab6-8f13-cfcb79d214a9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | • For intermediate and base courses surface to be above 5 degrees Celsius. For wearing course installation, surface to be greater then 10 degrees Celsius. Has the above criteria been met?
1f60d8c0-5a40-5230-9280-ae018f4726eb |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | Request Sign Off
17ff2be1-48ae-5334-abad-f33bbcaac417 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 1.0 Pre-start activities | • Have the existing pits been raised/lowered to meet the surface level of Asphalt?
6348926b-4f9e-5f59-af78-0b437b44fcc7 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation
a01855ae-e7a0-57fc-b695-15e88085ac26 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from CYP D&C JV.
ab5c050f-c7b3-53c0-9e05-ab290000255c |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | Request Sign Off
908926ab-8814-5096-8e11-ac5854099733 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | • All transverse joints shall be offset from layer to layer by at least 2 m.
d0955d94-17e9-5265-937b-4878d80c5657 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | Request Sign Off
660d6123-00f2-55ab-a38a-69a3ec4e9b3e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | • At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
80c75e84-f388-5d8b-9f8e-6c4f98317bb3 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | Request Sign Off
1f50009f-8543-572c-9774-c57590a05004 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | • Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified. Asphalt shall be uniformly compacted Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
9b3ffe93-0603-5a11-b38c-f7c9a66623ad |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 2.0 Hot Mix Asphalt Installation | Request Sign Off
f1c341e8-b9c9-5adf-8dd6-067e364d252b |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 3.0 Completion and Compliance
70fa9836-b3a8-51e5-b985-da8e7a8c9947 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 3.0 Completion and Compliance | • Thickness < 50 mm: 94.0% Characteristic Density Ratio
06e23d99-789f-5c07-806c-2698813c6634 |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 3.0 Completion and Compliance | Request Sign Off
e71ab48f-2efc-575f-8ab8-2a8b49874f18 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 3.0 Completion and Compliance | • The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements (mean +/- 5mm, standard deviation 8mm)
8f86fe9c-35e4-5df1-821a-fdee0466d7cc |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 3.0 Completion and Compliance | Request Sign Off
b586addb-3703-5653-b90b-43a9db28e167 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 3) ITP-003 - Asphalt & Sealing | SYM-PURL-ASP-6A-1 | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | 3.0 Completion and Compliance | • Surface finish - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
52af23a8-02e3-420c-b2d4-90d5248f96ca |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works
3ac65bea-6e71-4af4-ad68-5b11746885fa |  | checklist-sectioned | work-in-progress | f9f600f0b8a5bb70000383b01dc244abfc5b59ce9280d4545a6dc0ac7a7e9696 | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1)
8edf37f5-14af-5eeb-b812-5e19cddcf4ba |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries
c005df70-54c4-510c-b92d-3f4df71d8934 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Concrete mix design approved by the Superintendent and a registered mix and Material properties meet project specifications
d6be55b9-6536-5617-9cfa-b46313bc15a9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Are the drawings, complete & current?Attach Recent IFC Drawings
ce2f3a4e-d746-570d-a3ac-67db340b9740 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Is the work area clearly pegged out for line and level?
779b8596-25d7-55a6-bd07-39f4d07a4803 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Is edging constructed over Pavement layer?
cf68cb1b-e728-5328-9749-ae3161e0bb2e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Where edgings are constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
4303d039-d0a9-5446-8ea9-a78066412f7a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Is bedding for footpaths and surfaces compacted to 100mm thickness unless noted otherwise.
f12e0f0c-b350-5cfd-9c04-03b0a1c8e551 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Is bedding for SUPs, bedding compacted to 150mm thick unless noted otherwise.
0d15dcac-7426-53e9-be8f-321ee7c627cb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Bedding shall be moist but shall have no free water on the surface before concrete is placed
cbc0df1b-ca7f-59fb-8f0b-445992071e35 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Is bedding material used for cast in place concrete paving works compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
2549cd01-ca07-5108-8281-498394328198 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Is bedding material for shared use paths compacted size 20 mm Class 3 crushed rock or Class 3 crushed concrete in accordance with Section 812 or 820 respectively, and Section 304.
e5ab79f4-b382-5d55-8b17-b690e9183a07 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Are pavement lots tested for compliance with the specified compaction scale for moisture content no less than 85%
39a6d8c4-3835-5a95-ba54-6795c36026d2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Is fill material used below bedding tested to Table Compaction Requirements
a147a8cc-b27c-59e9-9be4-a4e06dc0a74d |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | • Relevant permits have been signed and approved.
7f8b414f-4c60-53b7-826f-e19d50d3da6e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
9343fc87-2cee-5e89-8901-e6ff7625b0e2 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 1.0 Preliminaries | Request Sign Off
ea6f2166-236f-53ba-b837-cc8e3bb4e73d |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation
252cc7fa-6f10-56c4-94c9-d39b8498b749 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Formwork has been installed correctly and sufficiently braced.
d8f0f545-ca4d-580a-afae-ee7a5b3985a3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Formwork set out has been done as per latest design drawings and specifications
6ef79419-bbbd-5f6c-9686-3d223f60db1f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed
6c22485f-80a6-5b92-ab10-79259a90db66 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified/Sockets
92c5fc26-765a-51ef-ad54-33fbe22688aa |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Mesh installed with 40mm top and sides cover and 50 mm Bottom Cover
3bef9dab-586b-52e9-bde9-39d24d9730a1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Tolerance - As per specifications and Australian Standard
cacbac85-62db-545c-ab96-57db4313c3ad |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Steel is free of excess corrosion, loose millings, oil or other contaminants
e6fc65e5-c2a4-51bc-bede-366dd67ef5f1 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Required Connection Details - U Bars/ Z Bars/Cogs/Starter bars Verified
9abb881f-67f7-5f71-b441-fa93789696d2 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Correct concrete cover and chairs on sides, bottom and top Verified
13c8989f-ed71-5783-9f04-6ca9f0406282 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Has steel reinforcement been placed correctly with adequate cover?
73b1eab8-e77f-5cd8-8fa7-f1eec5e87d15 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Have tie bars and joints been installed at the correct intervals?
d72babc3-c68a-59a3-bdfa-b041d8f21d69 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Pour area is free of loose debris, oils, water
89a9f03c-7499-581e-a51f-6aa8825cb1da |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Have any services/penetrations/blockout located within the Pavements been installed, surveyed and pinned down
e59d5b73-0993-5d8f-823f-4f044e5df8ff |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Concrete Testing Lab Representative will be available during concrete pour
b02be278-5b87-5f81-92e8-ac69b7a83511 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Sufficient vibrators are available during concrete pour
238165bb-decf-535a-8197-0ff52f49aad9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • CYP D&C JV informed of concrete pour date and start time
aba5bd7b-1b2e-5f0d-81a2-c0a6b1751884 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Attach subcontractor ITPs
8bc9c792-1da0-506f-92a0-29a172963a52 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | • Attach site photos for all stages of works.
91cd0fcd-ffb9-5002-a549-5bde8b10f516 |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
111038a0-5b27-54a2-85fb-4699ee7ad0a7 |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 2.0 Under screed/Concrete Pavement Installation | Request Sign Off
3acfe327-73ab-59ee-b48a-78ce647ba840 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete
dd92bc40-4c29-5d3b-861b-178082801c1d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Is concrete temperature as per VR703. and not mixed when the air temperature is lower than 5°C or greater than 35°C.
00f17eef-51a4-56eb-882c-2a404d4cda77 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Is discharge Time 60 minutes unless mix design is approved by Proof Engineer for 90 minutes.
88253118-1faf-517b-89c9-4afcb9d2bd68 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Is concrete thoroughly compacted and works carried out as per Australian Standard & Project Drawings/ Specifications
435f7a83-5c9a-5f9f-a16d-c78dd3c67f3d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Are concrete samples taken in accordance with 610.16(b).
60583741-7399-5f34-8ae6-e1c8479fa157 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Is specified slump tolerance within 610.16(c).
c2e322ac-96a7-5e83-b72d-ddc353cbb85f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Is concrete mixed for not less than a period of three (3) minutes prior to discharge.
c1983ca7-b905-53ad-bc9a-f0e9c23939f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Is the maximum time lag between truck loads on site shall not exceeding 25 minutes if a continuous pour
49e836a0-861b-541f-8065-c67b76055a1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • A minimum of one of vibrator used at all times while the concreting is in operation
111b02f5-57c3-5e49-ac12-77eec8102d7f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Were forms/cast in items monitored during the pour.
0536be46-188a-5f91-9830-f38741a476c6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Concrete Dockets Received
c9464b57-e620-5c47-bb6b-9344b1de1453 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Concrete Fall achieved as per latest IFC drawings
50e40c56-4f74-5cc9-8796-f42290545c08 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Concrete pour record attached
10bb6729-636b-5769-8e3f-ac534ba00369 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Concrete test results attached.
16d5fcc5-b004-5fe2-a08c-62a9be298d57 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | • Attach site photos for all stages of works.
ab252854-50f5-563b-b7e5-cab5aca220bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
77c3b3b2-ee0c-5cf5-9145-1f67d3b537ef |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 3.0 - Placing, compacting and finishing concrete | Request Sign Off
a6cd2eca-61e4-5423-9eaf-030c1e756efe |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing
eee64fb5-3a19-5f3e-9e03-1f1b0ccd6319 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Did concrete achieve the required finish as per specifications
a7bc9f46-93bd-530a-8209-7f5e2001a9b2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Are hidden concrete surfaces of concrete paving have a Class 4 surface finish in accordance with AS 3610.
50d368c0-c90c-5a59-943c-1c42437eecfc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Curing agent applies as per project specifications
7a3b6d10-7a58-5fe4-b099-5c49dd2a6a52 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Concrete reached design strength to strip formwork. (Attach test results)
e0a10806-1078-5fb6-8f7f-e7c76f08e946 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Any identified defects after stripping rectified
dc7e39f6-c74a-5110-9f80-79299615475a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Were expansion joints placed at intervals less than 10m.
9a0db5ec-4619-5f62-b659-e9f1a20ac841 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • As Built Survey completed and report attached.
6ac4f9e4-249c-5e1d-9948-646265d99f84 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Concrete test results attached.
1bd4fc12-7130-5f54-b194-cebd2d729c0c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 4.0 Post Pour/ Finishing | • Attach site photos for all stages of works.
4044fc85-9c4f-5275-a7ba-d70cf2a842c0 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 5.0 - Backfilling
4fa92deb-fe83-509b-bc1c-8da61ff7dc5f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 5.0 - Backfilling | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
ffe4f0bc-f4d7-5072-848e-839d2982852a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 5.0 - Backfilling | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark.
7474639e-03e3-596c-a3c0-27292a8cf21e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | SYM-PURL-PCON-6A-1 (6A - F3 CONCRETE POUR LOT 1) | 5.0 - Backfilling | • Attach site photos for all stages of works.
7373d729-b04c-4049-8332-f6e138c78527 |  | checklist-sectioned | not-started | SYM-ITP-004 - Underscreed Concrete Pavement (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked
5218b0c8-5752-58a2-b52f-ceece857c6fb |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries
21b4ba98-725e-549c-8b1d-1840b766faa3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Concrete mix design approved by the Superintendent and a registered mix and Material properties meet project specifications
d9be5565-7ba1-549f-b124-b2644e8ca134 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Are the drawings, complete & current?Attach Recent IFC Drawings
975141cf-32b1-5268-a152-49dd5edcb818 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Is the work area clearly pegged out for line and level?
c6889fd0-6959-5e24-b648-831e7f408967 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Is edging constructed over Pavement layer?
7ffd504b-3acf-5b8b-95de-b167b5b16023 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Where edgings are constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
57475118-b39c-58c0-8721-2f3b36b19905 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Is bedding for footpaths and surfaces compacted to 100mm thickness unless noted otherwise.
9de05194-7b85-5a29-91c9-80298568a214 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Is bedding for SUPs, bedding compacted to 150mm thick unless noted otherwise.
68144410-7472-53a7-b61a-408a98e596c5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Bedding shall be moist but shall have no free water on the surface before concrete is placed
d01c74a5-24f5-5185-b900-1776a5c63046 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Is bedding material used for cast in place concrete paving works compacted size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
4ab0a167-9c8c-5961-9584-04f0a0ec411f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Is bedding material for shared use paths compacted size 20 mm Class 3 crushed rock or Class 3 crushed concrete in accordance with Section 812 or 820 respectively, and Section 304.
062e173c-cda1-55a0-a718-1f85086d8f1a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Are pavement lots tested for compliance with the specified compaction scale for moisture content no less than 85%
fe8e01f8-d0fe-5d84-9414-9963666113d5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Is fill material used below bedding tested to Table Compaction Requirements
53aee1cd-0ae6-5954-a484-7a3047602e6d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | • Relevant permits have been signed and approved.
9f87f50a-8b8b-56b8-b63f-c3e5c1c8b986 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
10634796-ccc9-5288-a6a9-dad943d5ef3a |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 1.0 Preliminaries | Request Sign Off
a65cf7f3-9cd0-5525-9b87-186400349392 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation
18c7831d-31ac-5e4e-a20c-3284297c311e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Formwork has been installed correctly and sufficiently braced.
535f620d-472e-5047-941d-5d43554e94c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Formwork set out has been done as per latest design drawings and specifications
38f89041-489d-5f4b-af92-22a3cc6dcff1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed
bebfc450-552c-5ca3-bd4b-be235f7fca25 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified/Sockets
ced7c77d-03ef-5856-a50a-20bbb1f0fc40 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Mesh installed with 40mm top and sides cover and 50 mm Bottom Cover
ed8b8423-f658-5f57-8b35-08142b294cc2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Tolerance - As per specifications and Australian Standard
fbad11ef-e0ce-501b-b66d-108401ea3e24 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Steel is free of excess corrosion, loose millings, oil or other contaminants
e37f9e1d-3fda-502a-9bb3-e053e74bc0b4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Required Connection Details - U Bars/ Z Bars/Cogs/Starter bars Verified
45223b99-056e-536d-9491-f61397f59efb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Correct concrete cover and chairs on sides, bottom and top Verified
ffa34aef-320e-59ae-9a32-af1c852fe97c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Has steel reinforcement been placed correctly with adequate cover?
bf53f2d0-79e3-5ce9-aa5d-f9fc69e9ab7c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Have tie bars and joints been installed at the correct intervals?
ec122d79-d4b8-599c-9360-b1b304a6a23f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Pour area is free of loose debris, oils, water
5e3c4067-4b53-56a9-94ff-8d2449fbc681 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Have any services/penetrations/blockout located within the Pavements been installed, surveyed and pinned down
3fb157a7-442d-5f66-ba32-cb64c8444ecb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Concrete Testing Lab Representative will be available during concrete pour
39f9fce7-6e4f-51b0-96da-b87d21528cd2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Sufficient vibrators are available during concrete pour
31fa80f9-8f5b-5f95-aac9-3176699a5125 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • CYP D&C JV informed of concrete pour date and start time
8794c1ad-8445-59bf-a1a6-7715d45e631f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Attach subcontractor ITPs
483d080e-fde4-598b-ba09-52f1c776ee93 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | • Attach site photos for all stages of works.
dde73916-30c4-52c8-8706-5d52312c999f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
2adfd439-194b-5713-8efe-ee162f8ee9c7 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 2.0 Under screed/Concrete Pavement Installation | Request Sign Off
34a23ab3-29f1-569c-9a74-4c853ea83220 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete
790b41ef-0a73-5133-b53c-955900ec3468 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Is concrete temperature as per VR703. and not mixed when the air temperature is lower than 5°C or greater than 35°C.
b96efc7f-3e56-56e7-9319-eb7766b5008f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Is discharge Time 60 minutes unless mix design is approved by Proof Engineer for 90 minutes.
7b909098-7b48-5146-8c8e-ae3fa468f41c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Is concrete thoroughly compacted and works carried out as per Australian Standard & Project Drawings/ Specifications
2e6bb2b8-297e-59de-8910-9db6884bcda0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Are concrete samples taken in accordance with 610.16(b).
abc84f41-90f2-5de6-9092-ec59c8f6daf7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Is specified slump tolerance within 610.16(c).
2e8f5010-e9ed-5a95-947b-a71896424749 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Is concrete mixed for not less than a period of three (3) minutes prior to discharge.
5a69e331-8d0b-532e-a14d-a8403b3099d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Is the maximum time lag between truck loads on site shall not exceeding 25 minutes if a continuous pour
9e26bcb8-7b6e-57d2-a8e2-389b0b0bf6c3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • A minimum of one of vibrator used at all times while the concreting is in operation
5b148a12-14b8-5306-930e-9eee077fee95 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Were forms/cast in items monitored during the pour.
1d817b53-a79e-5ba7-a987-9a001b543ed4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Concrete Dockets Received
b85060c7-b95d-555d-a03d-def4c83ce89a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Concrete Fall achieved as per latest IFC drawings
9d824b77-de8c-5bc7-beac-5ed115c7dae5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Concrete pour record attached
b7bb43b9-c5b8-56d7-9b99-c0dd9db8cd5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Concrete test results attached.
31863c6d-3cae-5473-bad2-a748f8a96971 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | • Attach site photos for all stages of works.
960d4a33-15f3-5ad4-a9d5-332a31331feb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
de4f5243-70b5-5821-be86-5db947d0ce28 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 3.0 Placing, compacting and finishing concrete | Request Sign Off
18c97b33-c1e3-587c-afa7-87334b11d952 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing
84ba6efa-7437-5deb-8a2e-9629ef4e8943 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Did concrete achieve the required finish as per specifications
2a99458a-a774-5171-a9d2-123ad94c26e4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Are hidden concrete surfaces of concrete paving have a Class 4 surface finish in accordance with AS 3610.
1de6cf00-d745-5ee4-8c7f-9471c61a4373 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Curing agent applies as per project specifications
81c9d2af-bac8-5286-b585-b9c163e4e9f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Concrete reached design strength to strip formwork. (Attach test results)
132078df-a369-5c40-9598-da6ffdde1fbb |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Any identified defects after stripping rectified
4baec8a5-82fb-5e4c-8fc7-623ae121f992 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Were expansion joints placed at intervals less than 10m.
911b0a6c-1147-5a28-94b8-e9b14b1f28f0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • As Built Survey completed and report attached.
ad27455f-a9b7-5fa1-ab74-842518a3e45f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Concrete test results attached.
ab3024ff-d8f6-5543-b974-bcdb193d147c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 4.0 Post Pour/ Finishing | • Attach site photos for all stages of works.
d966afd2-63f2-5006-9452-fe11f2c09597 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 5.0 Backfilling
7b3cf36f-8ce2-5982-9eac-0d08405ed23a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 5.0 Backfilling | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
27bca08e-aadc-5597-a2a3-6f2f3242aad3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 5.0 Backfilling | • Were the positions of any existing conduits passing under edgings marked by a chase in the edging immediately above the conduit together with a suitable identification mark.
3f73292c-5eed-5f83-80d9-a278e555118a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 4) ITP-004 - Concrete Pavements Works | CONQA test - delete once checked | 5.0 Backfilling | • Attach site photos for all stages of works.
79827cb0-2ac6-4549-ae10-230a76814107 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 5) ITP-005 - Kerb and Channel Works
ba8e4ee1-5fa2-483b-90ac-0ff73fc38f54 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works
913c7ed6-8d77-4820-9e52-2dadf6f737b1 |  | folder-normal | pass |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS)
fc2ca4ca-5803-440a-b043-f60bb6480247 |  | folder-normal | pass |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS)
671c0456-befe-4f3e-b757-5d505f86f825 |  | checklist-sectioned | pass | d032980dd3ed5765c5e694e78e7e3b094b14386a52f19751f657f16f78f2aee2 | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase
3d7f932d-398a-548d-89bc-2d4b41597724 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details
91b55c45-04ac-51e4-b73d-71853ce0ecb8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | • Is Mix design approved prior to placement and material properties meet project specification, AS 3600, AS 1379.
53340aa8-0b95-5931-8087-80f5f742e3e2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | • Is the work area clearly pegged out for line and level?
2df14572-1015-51fd-90a3-6cf174acfb07 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | • Are the drawings, complete & current?Attach Recent IFC Drawings
406c11da-dc97-54ce-bb6c-61182269d514 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
a325db8c-9304-5f89-bd73-66794367a567 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | • Relevant permits have been signed and approved? Attach completed Permit
81505d7f-7a41-5f70-9105-08ac2020cf4c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | • Extents and levels correct to relevant drawings
7689fcf3-9146-52e0-a081-22532a3bb042 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | • 50mm Blinding to be placed as required to allow working surface and protect excavation.
6049a71d-9cf9-5737-b633-7b21b591a039 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
09da0dfc-9279-5002-ac8f-884154496282 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 1.0 General Details | Request Sign Off
ccb149c8-a40e-5824-bb82-3a2a8c28cdc8 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation
a2a5ab06-6edc-50e1-ac53-0cecf69dcfa4 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements.
309d0ed0-c69c-568e-b3bf-2e823c32d5a5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Has the surface shall be thoroughly moistened with water and excess surface water removed prior to placing concrete.
4a63313b-bda8-506a-bd1b-ce546735cd6e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Formwork has been installed correctly and sufficiently braced.
dccfe33d-6985-5fe6-94f7-4032de446d2b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Formwork set out has been done as per latest design drawings and specifications
79350a6b-8b61-5cd2-ae7c-1c1a91ebd495 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Were Construction joints/Expansion Joints/Isolation Joints /or any type of joint as specified in the drawings Installed
baa0478b-cdd6-51b1-a5f8-ccaa08093925 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Any Backfill/ Underlay Material as per drawings & specifications
6d38eeb9-e1b5-59eb-9a0e-53fe709c1efa |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Was Installations of Cast-Ins/ HD bolts/ Chemical Anchors/Block out Verified
e3bd03fa-7bec-5eda-b7b8-985e864e047a |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Is the concrete member of height greater than 2m and a formwork design obtained with a certificate of compliance from a Proof Engineer forwarded to the Superintendent for approval?
48865e5b-96d1-58bc-917f-78f51a75b4ea |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Attach formwork design and approvals
64c5afa9-0505-51d2-af42-20ceb06919a3 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
7d245148-0d6e-5a16-b5c8-72ed95fd3c31 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Steel is free of excess corrosion, loose millings, oil or other contaminants
e617ef1a-05f4-5eca-8ac2-8e87f27f219d |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Required Connection details - U Bars/ Z Bars/Cogs Verified/Starter bars
bb5c3825-a1dd-5fab-ae3d-fab0cb34b595 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Correct concrete cover and chairs on sides, bottom and top Verified
2abfbb1e-62b1-5fd0-883a-06c2a0890846 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Has steel reinforcement been placed correctly with adequate cover?
ccae3ff9-b7b0-58f9-a315-eb9f2ff63fab |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Have tie bars and expansion joints been installed at the correct intervals?
6f357594-2577-54d4-8411-072897d059c7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Pour area is free of loose debris, oils, water
189cfaac-d2be-506e-a5d1-4541ae20f9e7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Have any services located within the slab been installed, surveyed and pinned down
65a77b84-c02c-5ded-a2cf-58e3df256ab5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Concrete Testing Lab Representative will be available during concrete pour
dbd7d29f-e9a6-51c9-9feb-36b28744eb3c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • CYP D&C JV informed of concrete pour date and start time
64c1e987-7c74-5619-bb63-2e8117611b43 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | • Attach site photos for all stages of works.
ccb0111e-1143-529b-b18e-51faaf252676 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
55b7b4a0-9246-5ec9-934d-da96a91276c8 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 2.0 Insitu concrete Element Installation | Request Sign Off
37a14ce4-fb44-54b7-afd1-ddb6e3562c1f |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement
53b426b7-04f9-5592-a734-977de7e133ed |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C
c21f7b55-669f-5e33-9f38-6dd3cfbc55ff |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | • Has Concrete been tamped/vibrated to increase density and prevent voids, honeycombing or surface defects.
4165f9fe-0296-55bf-8081-a0e1f4995a7e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | • Has a minimum of one of vibrator used at all times while the concreting is in operation
db84c0db-6500-5313-a1f8-a2498918b40d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | • Ensure monitoring forms/cast in items during the pour
93036ad9-b584-5136-b9cc-68ac784a4401 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | • Concrete Work(s) completed to specification/drawings & Area left clean/tidy
7eaa898b-ca7b-55a9-b032-ba6c31bca755 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | • Concrete Dockets Received, Attach last Docket
4075219a-9d12-55e3-8679-0c9c7e0233c9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | • Attach site photos for all stages of works.
eaf76a45-b7bd-58fa-ad47-4a90c398db0b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
2f633453-3f43-50ac-92ae-c9defed9b1f7 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 3.0 - Concrete Placement | Request Sign Off
72e53542-e4d8-5694-9429-b8bf96985c4e |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour
ed2f2b52-3cb4-5298-b5c8-52c8da75287b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Was Curing agent applies as per project specifications
e0dbf3e5-a9c1-5fe9-926e-fa61935a3938 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Concrete reached design strength to strip formwork
b195c8b9-18b3-5084-ace3-b22e94f80dd0 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Any identified defects after striping rectified
39ccb506-dd52-599c-a543-395f0bd9a1dc |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Attach Subcontractor’s QA
0244c2f4-eea4-52a9-b38b-007cbb7c65d2 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Does Backfill material comply with Vicroad specs, Project specs and drawings?
8e19293b-ad7d-57f7-8c39-0521bc5fa860 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Were as Built completed? Attach report if applicable
634013b1-5870-5aac-bdd9-5ef92f2d8575 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Concrete reached design strength to strip formwork. (Attach test results)
b4643b21-118e-5126-928f-7601b74ea8af |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Were expansion joints placed at intervals less than 10m.
419af658-3119-5254-a457-9886459ac8c5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Attach concrete Test Report
9202ca20-7aed-5fae-8f69-5fe9f50b0442 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Attach As built report
c1bee73a-50c6-5ed0-8612-829161e3befe |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | • Attach site photos for all stages of works.
d6e08674-ec7b-5fed-ba89-3ee45ab4a747 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
49b74093-c3e8-5eb0-be36-8e839c1cd08e |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Insitu Pit height increase | 4.0 - Post Pour | Request Sign Off
fb15cf79-b438-4ca0-9ea7-628fb2920c7e |  | checklist-sectioned | pass | a9f8628c35431a802e3fbcf6c9ff378fde8af9a729a7c8df8a5097ccb658bd69 | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing)
9a90e06e-8fb0-5b64-afc0-0f28058ec02a |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover
b79d1409-fd9b-5037-8a4d-93f3e752781f |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings?
57afcff5-b364-598c-88f8-48f28db32920 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Have subsurface drainage connections been cored at appropriate dimensions?
291c4566-7a4f-56f6-aff1-b52a3a8765de |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Test results for fibres and fibre content (if applicable) (Compliance Certificate provided by Supplier)
64ef4e5e-e08b-5cf8-9613-f7fc52dbcd32 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Have pits greater than 1.0 meter been fitted with step irons?
840343cd-18a2-5c33-8927-9329fd97971e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Step irons shall not obstruct openings or be fitted to a wall which has openings.
93c38eef-8b5d-5f9c-9ca1-dad45b40454a |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Have step Irons shall be installed in accordance with the manufacturer’s instructions and are an approved proprietary type?
ba350720-84d6-51bf-87a1-bb1f851e3bd1 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Material Conformance Certificates
0b9e484e-953d-59da-b9e2-f0b4ba65297c |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar?
42e63d85-5fc1-5a6c-bfb7-2f746367c44e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Surfaces shall be finished uniform in appearance with a Class 2 surface finish in accordance with the Specifications.
37e3a26f-5293-58d8-9f26-f5b50bbc1ca5 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar?
1ffac5cb-60ce-5e66-9d0a-23956ced0a8c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Attach site photos for all stages of works.
cd4c8380-b90c-5748-a791-518297d5fb85 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | 5.0- Fitting of Covers
39f5f175-7ed0-56ab-ae35-ff31170d407a |  | checkpoint-no-status | no-status-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | Details
8663f2fe-115d-55c9-9cbe-39e6101a932d |  | checkpoint-no-status | no-status-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | Details
e899fb39-19d0-5045-8c32-626cf6995057 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Attach Survey Conformance Report
f230ec34-73ff-5f0e-b393-7eecadfa4f81 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | • Attach site photos for all stages of works.
c1fefe74-3173-55e6-bf00-64a81ca3e631 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | HOLD POINT- Sign-Offs completed - Click to Attach Signature(s) below
206b2cac-c8db-5181-9988-27c4381cb94c |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | SYM-PURL-SWD-6A-2 (6A - RAISING EXISTING PITS) | Pit Covers (replacement for existing) | Installation of Pit Cover | Request Sign Off
6afb27bb-d180-4c5c-b587-3630f36544d0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes
1feec781-3ea8-4217-98f8-5ce044efa11e |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2)
aa8f91b7-1e28-44f1-b72c-dc8b0cc6512e |  | checklist-sectioned | work-in-progress | SYM-ITP-006 - Stormwater (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2
15507701-c626-5ee2-8d54-96076e8edc88 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities
c178d26a-e5ec-59d7-b2ac-79e9ccfe3bbd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Are the drawings, complete & current?
55f6bb55-1f9d-5d6f-8d0f-77d14a75d7dc |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | Request Sign Off
a728f6d4-e7ad-5bd9-9296-dc72cde627ed |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Lot shall be defined from pit to pit (or endwall, where applicable).
75180c9e-3f42-5161-9569-daf3f53036aa |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | Request Sign Off
666aa3be-42b3-54fc-8d21-f78e64961716 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Is the Box Culvert free of defects and to drawing dimensions?
c25976ae-d296-5509-8d9d-4dc4cf321d55 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | Request Sign Off
763793b4-7605-5c95-9304-00b8bcb474d9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Is the Pipes free of defects and to drawing dimensions?
ec122c07-b7bf-514f-9f47-2d43e2c92a49 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | Request Sign Off
01700642-5bfc-5bc9-9b78-18914711d442 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Have proposed precast Covers, Grates, Lids and Pits been approved for use?
6be42677-2eab-5d8c-afe9-86fb96e9cf60 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | Request Sign Off
1e52b9ab-d443-5d88-9e36-8f79e06784b4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Is material free from perishable matter and lumps?
0340e483-b3df-56fb-998e-72350ff21c1c |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | Request Sign Off
e8c4f45c-e53a-56b7-957b-3c2fe4bf7333 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Pipe/Box Culver/PIT Size & Class
bd801f93-ac46-5f8a-a2ab-ff30b370cbe2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 1.0 Pre-start activities | • Stage/Zone
a3442ac6-f711-58d7-beca-64c768fe6b8b |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 2.0 Excavation
9064add3-52ed-5285-bfbc-079b581ef99b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 2.0 Excavation | • Is the trench clearance width between 300mm to 600mm?
c1bae95d-475d-508f-af61-8216de5f1cfb |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 2.0 Excavation | Request Sign Off
6d08366b-f286-522f-80ca-96803f85bc16 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 2.0 Excavation | • Is the pit excavation not less than 400mm from external pit wall to side of excavation?
adf8ee9a-432a-557f-ad12-db173ab3dea1 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 2.0 Excavation | Request Sign Off
f15bce1f-08fb-569d-8178-c5973a53ab04 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 3.0 Bedding
8eaba403-a8c7-5a38-a8c5-443cd4a8b7fd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 3.0 Bedding | • Is the Pipe Diameter less than 1500mm? If so, has 100mm of bedding been placed?
f10d84d2-614d-5fc5-9766-d7e26f404586 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 3.0 Bedding | Request Sign Off
38cd7261-ca55-5186-a2ce-a39a2cb6505b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 3.0 Bedding | • Has bedding been placed and compacted to a thickness not less than 80mm on clay foundation?
7925554e-a0a9-5cbf-806b-b6cb43fbf7e2 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 3.0 Bedding | Request Sign Off
b3787e64-c2f1-59de-a91e-eb49b4add94f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 3.0 Bedding | • Has bedding been compacted to refusal?
b834459b-88a6-5ee7-b69e-e16fed0cd1ac |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 3.0 Bedding | Request Sign Off
0f5b95c0-47d1-5826-b779-aedc05f1b3ad |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4
09b60a4b-6bfb-5641-b782-b8223e7edd71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | • Are pipes being laid from downstream end?
b712736d-e6eb-5efb-a124-61f5b07474b7 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | Request Sign Off
59e56ec4-fe86-506c-b1fc-dbd4eb1a4b6e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings?
2980e6af-433b-5aeb-91ab-f3aa3e00a025 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | Request Sign Off
022cd3dc-d50d-53eb-bb69-42ce1769f95a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | • Have pits greater than 1.0 meter been fitted with step irons?
6f47f340-8e7c-5fad-96f8-f52dccdc2ca0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar?
9f16d6c3-078e-5d73-ad17-6c2e7b8afa20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar?
eefea4ea-5804-5dc7-8fd7-00ff47440c26 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | Request Sign Off
0edb9d48-2fca-5bf0-8987-ce6df827e946 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | Are rubber rings to be used on rubber ring joint pipes clean and free of debris?
96dbc9f7-b9e4-5581-bcc4-813939efb338 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | Request Sign Off
fdb816fe-ddf9-5979-9dc1-d4879f53bb26 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 4 | • Fitting of Covers
8379f8d6-11c6-50e6-95f6-ac338f0d04f4 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 5.0 Installation of Box Culverts
df6003f9-8715-5104-95be-e09124bc0dca |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 5.0 Installation of Box Culverts | • Have consecutive sections of box culverts been firmly butted together?
fabd6400-98ee-5d70-b48e-a4b2a8220b28 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 5.0 Installation of Box Culverts | Request Sign Off
bf83f00a-afd0-5cad-af76-d12a6a98b2ff |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling
62ac1934-e338-5216-9e59-2defe7d4c71b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | • Has the haunch zone been extended from top of bedding layer to 1/3 pipe diameter? Haunch zone material to be same as bedding layer. Haunch zone to be compacted to refusal in max 150mm layer.
9fad1fbf-200f-5d0d-ad89-525ff6527459 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | Request Sign Off
59b49418-3be4-553c-b339-73049d33054c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | • Has the pit been backfilled in layers not exceeding 300mm? Pit backfill to be compacted to refusal using hand held equipment.
08ba0fc5-f817-57eb-aba9-772fca85b7e3 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | Request Sign Off
e2b59d01-3083-5d06-801a-742fec69509a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | • Has the pipe been laid with adequate fall and invert levels within ±10mm of design?
c088b1e3-f3e3-5da3-8a16-f8bc4a656d01 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | Request Sign Off
13b572ee-7db8-5c29-b402-796c2f96b1c1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | • Has a total of 3 compaction tests taken place, per lot, inclusive of pit compaction, achieving 97% compaction?
e73f44e5-c3f7-51b6-ae7e-25218ab44c5b |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | Request Sign Off
37473ea3-b04e-5b41-ad3e-4e1193b21b0e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | • Have all storm water lines been inspected by CCTV and found to be free of defects prior to placement of pavement?
170e34ce-d09e-5798-9d4d-e531efb15ebb |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-PCON-6A-1 (6A - PV-5.1 to PV-5.2) | PV-5.1 to PV-5.2 | 6.0 Backfilling | Request Sign Off
c642b9a3-f99c-46ef-98d6-ec10d19c4007 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2)
25dc78da-7dbd-4e6d-b62f-7e0ec8b3c9a8 |  | checklist-sectioned | work-in-progress | SYM-ITP-006 - Stormwater (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP
588af46b-69a8-5e20-9a58-5cae87324efd |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities
25019892-ce34-58ab-9269-9d28d8318c82 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Are the drawings, complete & current?
56e05636-2e98-5bb4-8b79-1bfef04ccc02 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | Request Sign Off
0481159b-1bff-5686-9eba-128bf6ea297c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Lot shall be defined from pit to pit (or endwall, where applicable).
355d6248-a590-5f03-856e-fd587c716f4b |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | Request Sign Off
e773d89c-621e-5c44-a03e-ba5257138fd7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Is the Box Culvert free of defects and to drawing dimensions?
c7644c69-fe34-5fe7-a968-43ed13aeb235 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | Request Sign Off
dae68db3-5d14-5c22-b0ee-2c307322961f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Is the Pipes free of defects and to drawing dimensions?
08dc37cc-f594-5071-b8e6-58227e866534 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | Request Sign Off
0d6a8d00-12d1-589a-9d16-0a28674b4976 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Have proposed precast Covers, Grates, Lids and Pits been approved for use?
d13eccb8-0013-50f5-b251-ddc7ab1c1506 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | Request Sign Off
b6a105db-d477-5d15-a8cc-fd1a9e9315d0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Is material free from perishable matter and lumps?
18b3947e-8bc0-5249-a03d-187000536086 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | Request Sign Off
dfe8dcf2-3af9-58df-9708-013f97a26c74 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Pipe/Box Culver/PIT Size & Class
fc600394-cec6-5382-980d-47919062ab56 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 1.0 Pre-start activities | • Stage/Zone
226ca91c-ddcc-5d6c-9800-1c2c33863cd3 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 2.0 Excavation
578802b2-c924-5659-86dd-4ef6a709b65a |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 2.0 Excavation | • Is the trench clearance width between 300mm to 600mm?
95e9217f-5851-5f88-9077-f324923ac2ca |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 2.0 Excavation | Request Sign Off
c1e21926-e735-50c8-b5bf-89085d14c9be |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 2.0 Excavation | • Is the pit excavation not less than 400mm from external pit wall to side of excavation?
6e5b38cd-5aa8-5e9a-8bc2-8759a0c48efd |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 2.0 Excavation | Request Sign Off
85c13338-1cd5-5978-b97d-d4c4573abdbd |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 3.0 Bedding
4f1f37e4-8613-5547-9c33-c15e4389d13c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 3.0 Bedding | • Is the Pipe Diameter less than 1500mm? If so, has 100mm of bedding been placed?
712092f6-fb80-53e4-9367-47a2089c8abc |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 3.0 Bedding | Request Sign Off
148d07e9-d78f-5d47-8efc-125cffd06f19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 3.0 Bedding | • Has bedding been placed and compacted to a thickness not less than 80mm on clay foundation?
8c9a8288-08fc-5e61-9381-463e193950a5 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 3.0 Bedding | Request Sign Off
1e2f9234-a859-5804-b9ea-a2e7dadfe03d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 3.0 Bedding | • Has bedding been compacted to refusal?
1a7f5781-7c9e-5e87-90e6-4fb15d38baf8 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 3.0 Bedding | Request Sign Off
fe1327c5-afef-5012-ab1a-35393b5ae461 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4
c7476ca8-4d72-52ed-b317-b8233f89079a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | • Are pipes being laid from downstream end?
be1dec1f-a9cf-5b50-846c-26a14d15e3bd |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | Request Sign Off
3dfd778c-91c4-5349-b328-8d6c8a24be1e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings?
dd43cb14-b39a-5cc8-bb0e-95dfcee190f8 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | Request Sign Off
04ed202f-d2bd-5b14-9d9e-df28b940ff53 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | • Have pits greater than 1.0 meter been fitted with step irons?
7b9f22d2-1767-564e-8551-a9b21030a5b2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar?
037474cd-4327-5d50-b013-2842d85ce306 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar?
415bcde2-51b5-5d90-a8c3-d862e66e7d5d |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | Request Sign Off
896240fe-9bee-56c9-987e-b7519f4bd548 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | Are rubber rings to be used on rubber ring joint pipes clean and free of debris?
a3c8c2ec-5b9a-5984-ba91-0b57b0c00e8e |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | Request Sign Off
116ed576-9372-5fb8-acab-192d6a764327 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 4 | • Fitting of Covers
dc53dc70-3e3d-55f8-9b76-64b8c23c0333 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 5.0 Installation of Box Culverts
ba814bad-dbea-5c4f-8422-973e08a9ba65 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 5.0 Installation of Box Culverts | • Have consecutive sections of box culverts been firmly butted together?
5ce27d76-18f6-509e-a5c5-4a505c85abfe |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 5.0 Installation of Box Culverts | Request Sign Off
34c0afa9-78a6-5dcd-a8b2-bf779b414956 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling
6b55eedb-d9d7-5c0d-b0d1-23a845b4616b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | • Has the haunch zone been extended from top of bedding layer to 1/3 pipe diameter? Haunch zone material to be same as bedding layer. Haunch zone to be compacted to refusal in max 150mm layer.
99b5ea91-5dcc-5c2c-8636-0c1de37f3c04 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | Request Sign Off
d7df78d1-875d-5ea9-bf38-9cde5932b973 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | • Has the pit been backfilled in layers not exceeding 300mm? Pit backfill to be compacted to refusal using hand held equipment.
2cdcff3c-eb7f-5d4c-b195-d301a42ff177 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | Request Sign Off
2a06d93d-18f1-56f3-a341-bdd57e8d40ac |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | • Has the pipe been laid with adequate fall and invert levels within ±10mm of design?
dfa83168-a39d-5d9e-8c25-744551910bf3 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | Request Sign Off
8456916f-a0ff-5578-ad29-b9ac0d417790 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | • Has a total of 3 compaction tests taken place, per lot, inclusive of pit compaction, achieving 97% compaction?
50e79c6e-a978-5bfd-9e69-567491d0f8e5 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | Request Sign Off
7145c351-4acd-5362-932f-556591917cfd |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | • Have all storm water lines been inspected by CCTV and found to be free of defects prior to placement of pavement?
4fa78505-8118-5994-b035-557019a83252 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | 2. Installation of Stormwater Pits and Pipes | SYM-PURL-SWD-6A-3 (6A - PV-4.1 to PV-4.2) | PV-4.1 & 375MM RCP | 6.0 Backfilling | Request Sign Off
5447ae0f-7c54-47b3-88ec-4922d716cd98 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1))
6b033fd1-a734-4f9a-ab21-33757b13e5a1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1
9c68ae30-bf0f-47d2-bf1f-0294f39c023f |  | checklist-sectioned | work-in-progress | SYM-ITP-006 - Stormwater (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element
5128e9e8-2843-5d3b-b069-ddd8c257b572 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities
e154eb49-cbad-589a-994b-ea2dd6c4ffad |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Are the drawings, complete & current?
4f498084-ae05-5991-bb4a-184cbf146f41 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | Request Sign Off
dd80887f-88f2-56b2-af41-ac8d8c90b83a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Lot shall be defined from pit to pit (or endwall, where applicable).
d37c6d11-593c-5461-a841-a8383eaf64b5 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | Request Sign Off
a7050255-c6f2-5cc9-8ec9-5c344d221438 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Is the Box Culvert free of defects and to drawing dimensions?
a47b6266-b396-53c4-9b2c-39221ed9ebe3 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | Request Sign Off
f277e39d-1f86-5379-ac4a-c00a20c3487f |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Is the Pipes free of defects and to drawing dimensions?
4c4e85b9-ff57-5e2b-8498-849f5a807f5f |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | Request Sign Off
a22ca2be-5134-50de-bf61-f8334b92dedd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Have proposed precast Covers, Grates, Lids and Pits been approved for use?
6e641c47-e4c5-5e0f-9aff-91098e4d0a8f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | Request Sign Off
17f006bc-3829-5bcd-b904-45d3d5ec9e65 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Is material free from perishable matter and lumps?
315471ed-193a-5403-a899-bbfcb298ed1a |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | Request Sign Off
3419057f-fa26-5038-bd02-2b6d5e8ed559 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Pipe/Box Culver/PIT Size & Class
8688049e-d12f-5bbb-b4f4-2f36549f0937 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 1.0 Pre-start activities | • Stage/Zone
84202c5c-54bb-5fc2-be9e-472aab7f8828 |  | checkpoint-group | not-applicable |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 2.0 Excavation
e9d49663-5bbc-5e77-a629-ab8c685fbc4e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 2.0 Excavation | • Is the trench clearance width between 300mm to 600mm?
4bfa9412-f30a-5a25-868f-21ccf1ad17c0 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 2.0 Excavation | Request Sign Off
25242222-efea-558c-9492-79e96927e8db |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 2.0 Excavation | • Is the pit excavation not less than 400mm from external pit wall to side of excavation?
67bb3475-f3f0-52d6-a409-16fb2b88ccd1 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 2.0 Excavation | Request Sign Off
370070cd-6f86-5217-a581-d337f82257a9 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 3.0 Bedding
6c77b05d-1953-5b30-a9de-72cd363cc92c |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 3.0 Bedding | • Is the Pipe Diameter less than 1500mm? If so, has 100mm of bedding been placed?
2e089418-a758-5e2b-90cf-77465839ec58 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 3.0 Bedding | Request Sign Off
4cdcae7b-df46-5794-ae67-ada285a8aa5f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 3.0 Bedding | • Has bedding been placed and compacted to a thickness not less than 80mm on clay foundation?
3938c47b-e9ad-5ba3-b667-08dbd5888939 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 3.0 Bedding | Request Sign Off
9c6612e5-46dc-5c62-acae-96e434d7f76d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 3.0 Bedding | • Has bedding been compacted to refusal?
2f78e18e-03a0-5935-9e7e-3e910637125b |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 3.0 Bedding | Request Sign Off
949a02de-4273-5482-abfb-ca98c93e9d6b |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4
4aa21e30-fca3-507d-9fc5-2d7a3318615e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | • Are pipes being laid from downstream end?
4c935b1d-e8c9-5bdd-8f2f-d3d2f7278ca8 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | Request Sign Off
0e78bec5-ecef-5667-8329-4f5da05d3e0e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | • Have pre-cast pits been installed at the correct location and to the dimensions shown on the drawings?
f4275764-8f41-5f1e-a387-ae4a235ec92f |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | Request Sign Off
00904f2f-d147-588f-b8dd-8c71dd1b3af1 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | • Have pits greater than 1.0 meter been fitted with step irons?
018f568a-46f7-547f-a879-aac651c0e368 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | • Has the drainage pit floors been smoothly shaped from the inlets to the outlet for a height of one third of the diameter of the outlet pipe with cementitious mortar?
ea503f63-549a-5d90-82ef-219fb1f9ded8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | • Has the joints between drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar?
02215f81-8353-52b7-838d-dcefa3fa8bd3 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | Request Sign Off
9c7d98a7-8e0d-5ee3-aec2-5fb9a209c9a7 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | Are rubber rings to be used on rubber ring joint pipes clean and free of debris?
f92be144-c4cf-5a37-955f-f2bd9a43478d |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | Request Sign Off
bbb7c2ee-ac62-5640-9983-110c975f9541 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 4 | • Fitting of Covers
e5b9ee85-6c62-5710-b712-99e22ac50e83 |  | checkpoint-group | not-applicable |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 5.0 Installation of Box Culverts
3d13b97d-92f3-545e-81f4-30d5cf97699b |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 5.0 Installation of Box Culverts | • Have consecutive sections of box culverts been firmly butted together?
57b13ff3-25c2-536e-addc-02dc11eac785 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 5.0 Installation of Box Culverts | Request Sign Off
5edc10ed-a2d4-5b51-87f1-a7da45bab013 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling
71db368d-12a3-5b87-9feb-b7d02dda4b09 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | • Has the haunch zone been extended from top of bedding layer to 1/3 pipe diameter? Haunch zone material to be same as bedding layer. Haunch zone to be compacted to refusal in max 150mm layer.
8e43bb3a-765f-59ea-9aa2-c8d6ff263356 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | Request Sign Off
34a7eb3a-b134-54fa-947d-52da4177e1d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | • Has the pit been backfilled in layers not exceeding 300mm? Pit backfill to be compacted to refusal using hand held equipment.
45b19b03-4c55-5983-848e-18a8cd1d6289 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | Request Sign Off
eb261ddd-be99-5b15-80a4-44789e45f698 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | • Has the pipe been laid with adequate fall and invert levels within ±10mm of design?
47c0e928-68d0-5c92-9342-84cb8d323749 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | Request Sign Off
0a464a74-8832-5e66-bf32-a1625f0ecf3f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | • Has a total of 3 compaction tests taken place, per lot, inclusive of pit compaction, achieving 97% compaction?
c93ae1f5-9af2-5639-a046-323a8383792e |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | Request Sign Off
8d5b334d-ee55-57e5-aa95-38b572a53bb8 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | • Have all storm water lines been inspected by CCTV and found to be free of defects prior to placement of pavement?
4287c082-2535-52a2-947a-56415dc672b7 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | Stormwater Pit Element | 6.0 Backfilling | Request Sign Off
47d6259e-155e-4734-a3ab-6ecaf46d3ce1 |  | checklist-sectioned | work-in-progress | SYM-ITP-007 - Subsurface Drainage (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element
a008b5c4-b0df-55e5-b9f1-3281cf9d41b8 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details
72095e6e-eef0-5726-9cb6-7307ef736b7b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | • Material classification and source
9072482b-3666-5558-bf81-5cdb42453fe4 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | Request Sign Off
56d2520c-b65f-5ef7-8522-3e85e0faf264 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | • Is the work area clearly pegged out for line and level?
107808b5-837e-532d-8902-24df1b8d5572 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | • Has the method of compaction shall be in accordance with the Contractor’s quality procedures been submitted for review by the Superintendent and approved?
3154c149-7ce7-55a3-8ccb-385f33455fe4 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | Request Sign Off
2222a650-f770-5433-b1b3-0190dece45d6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | • Are the drawings, complete & current?
398b8464-de59-567d-829f-1694807c38c0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
04c2602b-8cf9-540f-8a7a-e0538f921a5d |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 1.0 General Details | Request Sign Off
9af95546-1b80-5be7-af71-0eee85414e3b |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation
5e213487-b19c-5239-b19d-0b8d2dd6a7b6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | • Attach As Built Report
c970e68f-53c0-5899-bbf9-460429fd4d91 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | • Has the Pipe Class and size been confirmed as per latest IFC drawings drawings and project Specs?
e9c1c602-6c90-5d64-aaae-7f1bfaf76c07 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | Request Sign Off
5e547754-d89c-5102-8b24-5c5851b0e49a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | • Has the outer covering of the subsurface drain been covered in a geotextile surround if specified?
67fcb62c-2216-549c-9cca-ec5ad9002d24 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | • Has material been placed in <300mm layers and compacted with minimal disturbance to pipe, geotextile and trench walls?
ff916689-a120-58e8-b249-67ba51090892 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | Request Sign Off
b57e2d00-b0bf-5cc7-8c0d-01d19d6b138e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | • Have access points installed at intervals of between 100m and 150 m?
2abd1e7f-d06b-5290-aeb5-920bff961e37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | AGI Subsoil Drainage Element | 2.0 Subsurface drainage materials and installation | • Has the pipe been flushed with water to remove any debris or blockages in the pipe and it’s working correctly with a smooth flow?
b7251b29-5f8b-4e16-bbab-d8535d27d468 |  | checklist-sectioned | work-in-progress | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element
81edf513-99b0-540d-b24c-47c00f82e6f6 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 1.0 General Details
a3da6bf1-cb22-5e52-867e-b79b0bea4228 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 1.0 General Details | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379.
d95da9d9-bbed-58dc-b471-c2e2f68c0a6f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 1.0 General Details | Request Sign Off
6bdc8811-2f57-5c53-a76b-2643084a6277 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 1.0 General Details | • Is the work area clearly pegged out for line and level?
498b944d-beb8-5255-8cd3-c3e5599a16d6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 1.0 General Details | • Are the drawings, complete & current?
c4545e7c-21bd-57aa-b76d-8129dc23616b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
96083605-af3b-5a2d-8345-23d7d1660503 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 1.0 General Details | Request Sign Off
3c6e6976-3a5c-580e-9330-010ab3d5f808 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element
c099d88b-5b1b-5cec-9414-9c53e369b13f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements.
0a184228-bb9d-5d69-8848-1a8023fc7c91 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | • Formwork has been installed correctly and sufficiently braced.
3b948e6e-b52b-5e6b-8c83-67f25367dfbd |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | Request Sign Off
ea4ac725-ad8f-5f45-b002-b62356064965 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
e1990e21-70a1-55cf-9de7-0dda44a053ff |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | Request Sign Off
efdeecae-65da-5c30-a11a-e05c1f491871 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | • Has steel reinforcement been placed correctly with adequate cover?
83984efe-796d-5474-9dbe-96cbf4ff8520 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | Request Sign Off
0d3dea26-6856-52bc-a507-7d43f121bb61 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C
b138e03d-131c-5faf-9a3c-1f9bb354d87c |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | Request Sign Off
cee8511a-2c03-59c7-a4c9-db5e129baaa9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | • Was Curing agent applies as per project specifications
bf7a9604-5ef1-5f88-80d6-e8c32281361b |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | Request Sign Off
232f4b5e-d513-5e30-95ec-b8192d011db8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
47f2abb7-e5af-5d1a-b39c-d45789a1f7c5 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 6) ITP-006 - Stormwater Works | SYM-PURL-SWD-6A-4 (6A - PASSIVE IRRIGATION TREE PIT (PV-TP-GS-5.1)) | PV-TP-GS-5.1 | In-situ Concrete Element | 2.0 Insitu concrete Element | Request Sign Off
6fd306c2-796f-43b9-b036-66df26969d65 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works
871f8db9-b15f-47cf-98c3-194a349a2fb5 |  | checklist-sectioned | pass | 270feca16f2b9578956176e93920539d0b272cbae80e090b79f989c95d6047f9 | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH)
d4dcc2e9-8c00-565f-a599-4544465fd6c3 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details
6e797493-e871-5b19-9138-5629f80c462e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | • Material classification and source
4370542e-c4f6-57be-9fc7-790339cc4fed |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | Request Sign Off
67dcfffd-4456-545a-aa11-ba88a294ed87 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | • Is the work area clearly pegged out for line and level?
e6cd95e7-b954-517d-8b67-524effca496c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | • Has the method of compaction shall be in accordance with the Contractor’s quality procedures been submitted for review by the Superintendent and approved?
e11e0bf1-3126-59b1-b699-1de259057974 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | Request Sign Off
200cbd41-9726-5005-8933-071332320570 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | • Are the drawings, complete & current?
d7efc33d-f714-5d82-8405-964b8926dff8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
2e58814e-b8c6-570e-9806-92fd5d14910a |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 1.0 General Details | Request Sign Off
6daedd1c-1e04-5ab4-bd78-b5dfa878eb6b |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation
a3a6af18-c522-56f1-a4a2-a4cfb449aafa |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | • Attach As Built Report
74a268a0-ac5e-531c-afec-1aa0e7ef24d4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | • Has the Pipe Class and size been confirmed as per latest IFC drawings drawings and project Specs?
4cf59f95-a1c2-59e3-b0d2-ab1b9bc658df |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | Request Sign Off
af4b5341-508c-5e06-a629-7301d5addd64 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | • Has the outer covering of the subsurface drain been covered in a geotextile surround if specified?
1ab0618b-7c04-5b22-b32a-3174714acb43 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | • Has material been placed in <300mm layers and compacted with minimal disturbance to pipe, geotextile and trench walls?
d401348f-1194-5b77-a8bd-3687645addf6 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | Request Sign Off
e230d049-c5ed-5604-99e3-7656421be14d |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | • Have access points installed at intervals of between 100m and 150 m?
755867b8-5541-538f-a985-3d0984ba409a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-1 (6A - AGI WITHIN STRUCTURAL SOIL TRENCH) | 2.0 Subsurface drainage materials and installation | • Has the pipe been flushed with water to remove any debris or blockages in the pipe and it’s working correctly with a smooth flow?
a029c66b-3efc-4427-8f2e-9a4cbf30f4b7 |  | checklist-sectioned | work-in-progress | SYM-ITP-007 - Subsurface Drainage (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN)
a5a1f8ec-d664-5b6b-9ac5-b83c72496d3e |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details
658e65f7-dcec-5ca6-ae65-682f5b000f1c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | • Material classification and source
088355fa-219b-59d7-9b87-2caf2644c4c1 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | Request Sign Off
0fac14fd-c626-5d43-b810-8c04b1802470 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | • Is the work area clearly pegged out for line and level?
a9b8f2f1-4705-54e3-b1ed-f846f367f185 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | • Has the method of compaction shall be in accordance with the Contractor’s quality procedures been submitted for review by the Superintendent and approved?
a334a70f-0ba4-5027-8ff6-28c1bf08231c |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | Request Sign Off
0b7b5292-9851-5cf3-bc37-5c14cbf5a1a1 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | • Are the drawings, complete & current?
093e1f91-1467-5d4e-9286-dbfb96142f89 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
3b7cbddd-fbbf-5251-86d4-4dc35003e107 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 1.0 General Details | Request Sign Off
809a24d0-13a3-5538-b814-8ef2f6be0aa4 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation
f7da27ec-c889-565b-ade1-89bf9ad2f91e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | • Attach As Built Report
e9106985-aee3-5205-a619-10684ea805a6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | • Has the Pipe Class and size been confirmed as per latest IFC drawings drawings and project Specs?
c97174ee-4b5b-5b48-bd5a-a99661a89f04 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | Request Sign Off
1b2997a6-995e-5bd7-8b59-0e3c80357cd5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | • Has the outer covering of the subsurface drain been covered in a geotextile surround if specified?
6e7bfb64-29f5-5d6f-971e-07e85eeea309 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | • Has material been placed in <300mm layers and compacted with minimal disturbance to pipe, geotextile and trench walls?
506fdc8d-ce66-5be9-88f8-d8ef1ee81c5d |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | Request Sign Off
f146e191-11b1-5b79-a754-4de6c86c906f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | • Have access points installed at intervals of between 100m and 150 m?
f05eae4b-8320-5412-ade7-17f9e554a037 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 7) ITP-007 - Subsurface Drainage Works | SYM-PURL-SSD-6A-2 (6A - ACO DRAIN) | 2.0 Subsurface drainage materials and installation | • Has the pipe been flushed with water to remove any debris or blockages in the pipe and it’s working correctly with a smooth flow?
ef3c3955-c0fe-447c-a088-3d069102fa33 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works
8a22dfba-6dc6-42e3-8eb8-50e69fcb7773 |  | checklist-sectioned | work-in-progress | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A)
6adf5d76-df8e-549c-8934-cbe1bc345d6c |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 1.0 General Details
239eed54-246f-5cbe-ae69-45e365e45e02 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 1.0 General Details | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379.
b0826a34-e90f-523d-9f5b-948512ee1aab |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 1.0 General Details | Request Sign Off
800d2d23-ac0e-5d99-abad-6b43c8a27f1d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 1.0 General Details | • Is the work area clearly pegged out for line and level?
d9ee63da-98fe-5e0a-a6c9-66d8c964c69d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 1.0 General Details | • Are the drawings, complete & current?
add24590-a1bb-5108-a3ab-45ad097566e7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
a83fb1bc-1fb8-5afa-8ec3-3a76fb24b39e |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 1.0 General Details | Request Sign Off
4c844d19-46d9-54f5-985a-bca07f6a5e40 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element
d8232038-128a-5074-b3a2-502853b9722e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements.
cdffaf63-941d-56e7-8cff-2216163625df |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | • Formwork has been installed correctly and sufficiently braced.
5ce90bba-eae5-54b3-9308-e002d638c8f6 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | Request Sign Off
8b2ce23a-2428-506d-ade0-47badd58fc30 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
e0d7c2bf-0ea2-5a92-8826-3a6fa1488205 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | Request Sign Off
8cd80bce-8ed2-5c0e-b93e-0a2e0abd0742 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | • Has steel reinforcement been placed correctly with adequate cover?
e0ea710b-9705-5d5e-91d4-9281e4c4e881 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | Request Sign Off
929e7806-77aa-5160-8499-24adade5616f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C
97ac80ca-cd6f-5cda-b4e4-3b2456bddd67 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | Request Sign Off
bdfdddaa-aff4-5711-8cfa-dcee913900b5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | • Was Curing agent applies as per project specifications
20082e03-e197-5cfe-a798-67267da6b726 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | Request Sign Off
7f2232ab-b778-5cfa-b06a-6ce138142539 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
12c389d2-0a4f-5f52-ab7e-dd351cb84658 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 8) Insitu Concrete Elements Works | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | 2.0 Insitu concrete Element | Request Sign Off
c1247e40-1991-4778-b556-e64fe628da62 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 9) Tactiles Works
d4ad5690-5173-45d6-8038-d3aac1a6864d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 10) ITP-010 - Street Furniture Works
b2f08d68-b53e-432e-aaf6-e4de4c6e30f9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 11) ITP-011 - Landscaping Works
cfc3171e-1967-4c3e-8c1f-a692eb8f002c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 12) ITP-012 - Stratavault Works
53572e8a-ee63-4372-a00b-47fab9314954 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 13) ITP-013- Walls and footings Works
d846ce88-6689-4985-b588-8b3263b870da |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works
cee2a63a-378c-4067-867d-ac61dcc009a0 |  | folder-normal | pass |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST)
e80b6646-67bf-471e-aa6d-d3fa1d0b1921 |  | checklist-sectioned | pass | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing
1f03e0ea-bd29-522a-a03e-368bf6db76bc |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 1.0 General Details
8d59e38d-3dde-5505-ae85-22c2b72d2b9b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 1.0 General Details | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379.
2ea7e6b3-ff7e-57bc-813f-9df1c5ece5ef |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 1.0 General Details | Request Sign Off
b58c6a90-b4aa-55a2-88f8-50d776e42fbd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 1.0 General Details | • Is the work area clearly pegged out for line and level?
b270fcc6-e3bf-560f-8d9c-ae9ed9e37fbc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 1.0 General Details | • Are the drawings, complete & current?
2958acd0-b731-5faa-a21c-308baa024c3c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
992572c8-7850-51b7-bbb2-58be78e794a6 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 1.0 General Details | Request Sign Off
f74ac544-f2da-5c9e-9339-a173c2a71ab9 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element
71056dd4-3476-5376-a392-54964d63a72b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements.
0bafde94-3095-52c3-9cae-c5be0568d9ce |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | • Formwork has been installed correctly and sufficiently braced.
5ff237a3-0793-56b0-99e1-8f3f1a2a8717 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | Request Sign Off
52b6aa4d-66a0-5997-819f-0b296a7b7e2b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
88497f8d-3be6-5bf5-9d5d-df764911d937 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | Request Sign Off
07812268-2de3-5df5-9a29-d85f56aa43f4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | • Has steel reinforcement been placed correctly with adequate cover?
7483c8d5-40a7-577c-8518-07125ea53c0d |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | Request Sign Off
585cf191-96a8-5f03-913d-84fc782e5804 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C
2f5dd85d-2aec-5297-bf9e-9839960d62f0 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | Request Sign Off
8bf9202d-cab1-571f-a99e-4f962b8c87a8 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | • Was Curing agent applies as per project specifications
2e9fba30-a8f1-5780-8de7-cfb112d2100f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | Request Sign Off
748a1b73-0fc4-54f0-b783-2929476c53c3 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
6f24f1e1-1bd1-5917-af61-40c8742f47e9 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (WEST) | Bus Shelter In-situ Footing | 2.0 Insitu concrete Element | Request Sign Off
fee6dc3f-a18e-4da9-867c-67c7845277ab |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST)
3ddb47bb-ddc0-41e5-a62d-37e05e03e2e0 |  | checklist-sectioned | work-in-progress | SYM-ITP-008 - Insitu Concrete Elements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing
15ba41b1-98bf-5f67-b125-3c404e0d1df4 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 1.0 General Details
b2a4f20f-762d-534e-a7ed-cdee5d55e646 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 1.0 General Details | • Is Mix design approved prior to placemen and material properties meet project specification, AS 3600, AS 1379.
a3ed9ad7-6c27-5500-91eb-e81d9072d2dc |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 1.0 General Details | Request Sign Off
b68ea908-d208-51a5-ae24-a498af7e2789 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 1.0 General Details | • Is the work area clearly pegged out for line and level?
c6c7c731-40c5-5550-9e14-9d87dce426cb |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 1.0 General Details | • Are the drawings, complete & current?
f161ad30-41bb-5594-9520-04249b303531 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 1.0 General Details | • Were all identified underground services marked and potholed to confirm location and depth and no machine excavation within 1m of underground services.
f2059595-549c-5181-bc66-8631eb74a8ce |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 1.0 General Details | Request Sign Off
645dbe46-3cd4-5c41-ace8-5a1064ebadeb |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element
87af25bf-8747-5fa0-a521-7294734bec6a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | • Is the fill and base of the foundation compacted to achieve at least 98% and achieving Geotechnical strength as per the design requirements.
5b0116d8-7070-5ed6-9449-66419b02d99e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | • Formwork has been installed correctly and sufficiently braced.
39d2228d-dfe6-5da6-80c4-799789c41412 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | Request Sign Off
b8b30978-2d8a-5f51-ae2f-00b0afdc54ee |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | • Tolerance - As per specifications and Australian Standard and minimum cover for steel reinforcement is 40mm.
02277991-784a-5016-90d4-b279e1528f48 |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | Request Sign Off
a6c2f039-bfbf-5032-a42e-94778771af57 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | • Has steel reinforcement been placed correctly with adequate cover?
48063584-3e3d-5f38-94e0-6d546d78f2cd |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | Request Sign Off
2125cf21-546c-5f74-aeba-2a66ca246da5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | • Has concrete been transported, handled and placed to prevent segregation, loss or leakage of materials and air temp within 5 to 35 degrees C
f054b66c-f664-598b-a184-9ee0dd5c0dd0 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | Request Sign Off
32264454-1a88-5777-bcd1-09a13780b726 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | • Was Curing agent applies as per project specifications
e2c88f26-7964-5852-aaad-74e3ef4e2225 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | Request Sign Off
19b4fc7b-6bdd-5f6e-904e-7a661ec5c48b |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | • Were topsoil placed and compacted on layers not exceeding 150mm in thickness and not exceeding 300mm in width not earlier than 3 days after concrete pour?
5a315791-211e-5791-bbc6-e9916ef44101 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 14) ITP-014 - Bus Shelter Works | SYM-PURL-BUS-6A-1 - OVE SOLAR NON AD (EAST) | In-Situ Bus Shelter Footing | 2.0 Insitu concrete Element | Request Sign Off
55401eae-d2aa-4706-b28f-63a310dc5f42 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 15) ITP-015 - Heritage Works Works
b2fbd74f-8a4a-48ab-a338-351876c3432c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 16) ITP-016 - GPT Works
4256129c-f96b-4cf3-b7d1-5cf9c783e239 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works
b6048378-6582-487a-abc0-75ec173dc4a0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A
6c207855-d98e-42d9-b767-888d49910b2f |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS)
ebc28596-e30c-40a1-b7e4-bf94de15470b |  | checklist-sectioned | work-in-progress | SYM-ITP-017 - Traffic Signals (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A)
09df6405-2ccd-5b5c-9500-994e94d31b39 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries
4c341e81-ab4c-5055-84ff-749581b7cfdd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
1328fa0d-2a71-5cf4-877c-51ea7ca93a93 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
445e9025-03c8-544c-a161-fd1de6d2c329 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation
b840a70c-1e83-5942-902c-323cc8d5a4e4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has signalised crossing been constructed in accordance with the IFC Drawings?
dfcfeed8-c81f-5012-8bf6-eb900a81fe35 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
06b48cc8-9d09-52b4-a449-1639b7d86f55 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has Signalised crossing passed all commissioning and testing?
01ea3fd8-bdb9-55b8-96b6-bfea405de098 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
63fcfa5c-d306-5dc3-92ac-7ee203f8a762 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • DOT inspection & approval provided?
89855555-02a4-5ff8-800c-e1b10209326b |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
e9f0c98d-52ed-5ef6-9c3b-c5674861dc11 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check
61aafcef-7495-502f-933e-b66cce58fd19 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed.
48e4992b-e07d-55c7-8def-599843f6b3e9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-1 (6A.1 - LEICESTER/GRATTON INTERSECTION CONDUITS) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
f5cdd7b9-b06f-4063-a5b5-9ab34bb35cb0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD)
eec7fd60-526a-46f5-9dcb-dc37a6d6db34 |  | checklist-sectioned | work-in-progress | SYM-ITP-017 - Traffic Signals (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A)
62bae777-f38d-56a0-a786-39b60b884ea7 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries
9c99e829-fcfa-5f84-8684-2c2f6eb6220f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
d30726dc-66fc-522a-b51e-2c2e90b6654b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
6f9acdb9-8e3b-5215-916f-7550e30cd6de |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation
3c438cf1-7e0b-5f98-9e83-23a7bce3bdcd |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has signalised crossing been constructed in accordance with the IFC Drawings?
286369e5-2111-5f6e-86b1-204064cd661b |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
aeab6bf1-e233-5ea8-9068-1c771ff9783d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has Signalised crossing passed all commissioning and testing?
ae8cb032-aca6-5d99-b243-87652168cca6 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
55ff1628-a84b-5f82-b41b-35d6f476c95f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • DOT inspection & approval provided?
666b1b74-100d-5a4e-8791-8a0d42ee485f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
a1bee130-4426-563c-a449-c53be2a6d18f |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check
ebbd7f5d-70b7-5f31-a7a6-39f04bf2c281 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed.
c6b2bcd1-020d-57c0-9261-fb4353761305 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-2 (6A - 2b.1, TRAFFIC CONTROLLER, DISTRIBUTION BOARD) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
625a0cab-2160-4e94-adfc-bfd93dc91580 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2)
67df812f-621e-4ca5-9437-010756f9d4cf |  | checklist-sectioned | work-in-progress | SYM-ITP-017 - Traffic Signals (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A)
554153c5-5324-5688-bd2b-bef6200c86f9 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries
8a676def-5e55-5605-9dfe-1dfed51a2123 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
2e42e5c7-fd14-514b-bdbb-38b5dea1a25f |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
12dd616d-a5b3-52f7-8f28-d41e2eb7dcf7 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation
86378893-2bcb-59fb-8bac-3fc1a36def0b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has signalised crossing been constructed in accordance with the IFC Drawings?
d23321f5-bddb-53ac-83f8-5c0d9c38634f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
b9c4f2fb-c0f7-5f44-bbec-72fbbce78243 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has Signalised crossing passed all commissioning and testing?
e0a481ea-f4ab-54a9-b63f-86df10963b37 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
5febd144-f6e3-5c63-8dcd-abadc9920325 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • DOT inspection & approval provided?
96c79cda-080b-518a-8c5c-ae2bbf1a837c |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
3d0507d9-5da0-517e-aff5-160922e38c35 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check
cda5e417-c660-5dee-b9ae-312f63ae5824 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed.
7787d4b4-0b50-5c9a-b5fa-450808796f0a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-3 (6A - 2b.2) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
636d60db-9aba-48ec-b68c-d6b4c74baeef |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT)
5e9273e6-16dd-4c63-ad35-2cd611c1978c |  | checklist-sectioned | work-in-progress | SYM-ITP-017 - Traffic Signals (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A)
5603f0a0-fe92-524f-a90e-4d04c1830961 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries
15560c08-5a27-5af7-ab74-2256e78f102a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
7cb6010a-7527-5652-85c7-598f0fec4661 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
4332ed7a-fec3-544c-8664-ab4eed9347e6 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation
78558c24-f5f0-58d9-bade-e7c8d5b6de34 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has signalised crossing been constructed in accordance with the IFC Drawings?
c897db81-41be-5f3c-ac38-cb14020c8599 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
ec7f047b-507d-50cc-bc66-c4c5c0d6ae79 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has Signalised crossing passed all commissioning and testing?
4d7bc916-2fc7-528b-8bc8-e9cd95ea7e62 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
577361c4-9590-5c8c-bea0-794b1b6ffe74 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • DOT inspection & approval provided?
ebaa07b5-d210-5724-8c4d-05329c157f2a |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
40081ea4-064b-5fb5-8a3b-9f75650c48bd |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check
fa952a93-f404-5872-a088-1bb14a93ea5d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed.
266e9e17-bf06-51a4-bfd5-02494f3c8269 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 17) ITP-017 - Traffic Signals Works | Zone 6A | SYM-PURL-TRS-6A-4 (6A - 2x100, 1x63, VR PIT, POS PIT, P5 PIT) | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
fe39ff2e-22b2-4c91-8aab-dc3dee35d428 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works
7c8fd6b7-8dd8-47b6-8060-9f8ace03a5ba |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A
fb3e6db1-d68e-434b-82e2-a0a613b5c678 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS)
5fc54d1e-233d-4e66-9082-9ffde8b6a4e3 |  | checklist-sectioned | work-in-progress | SYM-ITP-018 - Public Lighting (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A)
5e7334ab-fdaf-5132-acdb-1ba6b3988279 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries
8d080914-7fa4-5d6b-8b8d-b2450181e32e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
75c640a4-b32d-58f0-8a6e-0f3c450709ae |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
ae207434-5f14-5360-a5e9-f427aee9e6aa |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation
14edcb22-a7d8-55a9-9a78-abad6aabe916 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting been constructed in accordance with the IFC Drawings?
56a97b13-d382-525d-8e2a-49cd1a053113 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
1df7e1f3-e720-5f1a-a72c-5e9bb24cd0a0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting passed all commissioning and testing?
19d8a00a-b596-52fd-b14c-5a406055136a |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
31488d1b-81c3-51e9-bb68-7e1d23c3d6b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Powercor inspection & approval provided?
386849ad-4681-5ea9-a889-d50791b2233e |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
8f41aedf-247b-5376-8485-918362a6cf7c |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check
e836c6e3-f726-52f1-b809-3e3085908747 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed? Attach Test reports
e801f6d1-db4d-55cd-a724-6069dd58ce17 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-1 (6A - PL PITS & CONDUITS) | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
445338f7-83a7-418b-838e-b0ded3062623 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS)
617eb17c-c68f-4f72-96c0-6f06bfb18b15 |  | checklist-sectioned | work-in-progress | SYM-ITP-018 - Public Lighting (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A)
8caedfaf-7a20-557e-b3e9-503afb41ffa4 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries
d475ca3a-fe4c-585b-a85c-e41e3e7b07d4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
08da0f0b-410a-5bef-ba31-bf1d79460cca |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
e551eac7-4744-5ff3-a0ec-da897992ea84 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation
87108364-215b-5780-92f7-96cf1880fd24 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting been constructed in accordance with the IFC Drawings?
caf810b5-e4f7-5b22-b9ad-21ae28c5527f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
73bb0020-f49c-588c-88d6-fb4a4a923c31 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting passed all commissioning and testing?
1c2776b4-1e25-5131-b8e2-922bd6d6baa5 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
3aaa92a1-946d-5dbc-ba0c-5f15ebfd7a41 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Powercor inspection & approval provided?
215f5a43-9a9f-5d79-9680-5a6307017e9e |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
d0d57553-4503-53ef-bc41-d1a707e918b4 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check
fe5abe64-b724-5bd9-926b-2c776f671331 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed? Attach Test reports
4f9f1ce8-d6d6-5774-90a9-aaa37d23acc3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 18) ITP-018 - Public Lighting Works | Zone 6A | SYM-PURL-PUL-6A-2 (2xLPS) | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
5d3eac7f-5255-43f0-92d1-a1ce8cbb16ca |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 19) ITP-019 - Cladding Works
be84db89-d873-4aef-a43d-b088d8df55e0 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works
611a20f1-53cb-4568-befe-6b53aa3427e1 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving
d71d3577-66da-44e9-8677-8a705a7415e7 |  | checklist-sectioned | work-in-progress | SYM-ITP-020 - Paving (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB)
63e36ab3-3698-5d34-895e-dfaebe3b2bfc |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 1.0 Preliminaries
94ad97d1-6203-5516-a075-3c0b0edde123 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 1.0 Preliminaries | • Are the drawings, complete & current?
63027fc4-b838-56dd-954f-05cf71dc8620 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 2.0 Pre-Construction Activities
75a368f3-6da1-50de-8b72-2a2649636125 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 2.0 Pre-Construction Activities | • Have pavers been set-out as per current drawings?
4a886833-a4e9-55b2-9818-a126e0a40557 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 2.0 Pre-Construction Activities | • Is the concrete slab free of any deposits or rubbish, projections/voids?
5d9d0254-2fb5-5fbb-999b-45ffe8ff1c91 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction
ad333da1-a81b-53aa-9874-3483944b671e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | • Has mortar been placed using type/method described in specification?
c5e8efa6-d918-58e2-b12c-fed283219157 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | Request Sign Off
834e2bc9-21d9-58e0-93ac-b14cd07d10ad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | • Where required, have been pavers been cut as described in specification?
f36e7584-4bad-512c-b287-0c07db08a2df |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | Request Sign Off
47ab3d1f-c9d3-53ed-b3fc-db7d4e65828d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | • Have pavers been laid as described in specification, considering specified tolerances?
c4a0ca25-95cd-5313-ad4f-2e5d96b58eea |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | Request Sign Off
30abff11-ddc7-5933-889b-fb6a527d510c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | • Have joints been sealed as described in specification?
93d184bd-7691-5abb-ad0b-7b0426038052 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | Request Sign Off
eac73a37-daa3-5062-a467-eb75bf443088 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-1 (6A - BLUESTONE KERB) | 3.0 Construction | Attach subcontractor ITP
369a3c05-85e4-43ca-be6f-9cdadbd97763 |  | checklist-sectioned | not-started | SYM-ITP-020 - Paving (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS)
df85d5ba-d30d-5ee8-aaf4-9133c45262d7 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 1.0 Preliminaries
461ade54-bb02-5dd5-a03a-1a175fe39c1e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 1.0 Preliminaries | • Are the drawings, complete & current?
21253596-9142-5a6f-869a-71f24b7d98e8 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 2.0 Pre-Construction Activities
a4753d76-be57-5715-b178-b47a1dd2bce3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 2.0 Pre-Construction Activities | • Have pavers been set-out as per current drawings?
8ccf2917-f5c0-5528-b120-107935580d39 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 2.0 Pre-Construction Activities | • Is the concrete slab free of any deposits or rubbish, projections/voids?
a1d1773d-b5fd-5262-977c-6d7d902d51ad |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction
1b376681-bfee-5dfe-9706-9c05c45fc570 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | • Has mortar been placed using type/method described in specification?
bbd5d26e-ae93-5c11-a444-4708f6bea706 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | Request Sign Off
23ff5e05-f551-5557-ac1f-e9e64beab9d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | • Where required, have been pavers been cut as described in specification?
89421915-9e2d-591c-8a65-e27cbbea9339 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | Request Sign Off
c888f87f-2eba-502b-87de-11e0c45414af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | • Have pavers been laid as described in specification, considering specified tolerances?
8b8c6c16-ab08-5c73-890a-93c25b8106c1 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | Request Sign Off
22024ee1-dc71-58db-9b93-258ad5ef6c20 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | • Have joints been sealed as described in specification?
08d71977-ab5e-51f7-872a-0a4339a23704 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | Request Sign Off
e116e0a6-fcc9-5dd5-a6fe-ed3fac1a0e2e |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 20) ITP-020 - Paving Works | Bluestone Kerbs and Paving | SYM-PURL-PAV-6A-2 (6A - BLUESTONE PAVERS) | 3.0 Construction | Attach subcontractor ITP
c9210cb4-8e56-4cda-aacf-0bd92e875187 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 21) ITP-021 - Precast Concrete
cffbe099-2d74-4725-ba62-7686108d9be5 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 22) ITP-022 - Linemarking Works
80f3cf91-9e77-46ec-b76c-397f21e7ac6a |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 23) ITP-023 - Signage Works
6b8a7d8e-dfe6-4fbd-a433-17f81f550f1b |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 24) ITP-024 - Handrails & Balustrades Works
0abf8e4b-e717-4f21-b836-d4963c87c7f9 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 25) ITP-025 - Drinking Fountain Works
261ef261-a30a-4be4-ac63-e634c2d932b7 |  | folder-normal | not-started |  | step | TRUE | FALSE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil
e9272f36-0c7b-4632-9617-5a7f1c5cd9b5 |  | checklist-sectioned | not-started | SYM-ITP-026 - Structural Soil (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH)
156c57f4-eb94-5d6e-a908-96b9b7aaede9 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts
d040c74e-66b9-5866-bf46-8e941663b64d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | • Are the drawings, complete & current?
7c697260-22dd-5885-90be-a664f0475ef0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | • Have all relevant samples been provided to CYP and approved?
38991828-4641-5f49-95bf-fe27ca892ccd |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | Request Sign Off
cba99185-dbb1-5c60-bbc6-97a84514916f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | • Prepare the excavation for the Structural Soil (Setout) as per latest IFC drawings specified dimensions
7fe9c8db-eb0a-5078-b8de-10f3bf2ef172 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | Request Sign Off
c7bcd367-ea62-5cb3-bb4f-9d8610d3df10 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | • Were all identified underground services marked and potholed to confirm location and depth.
8e080f72-e78e-5e1c-a70f-b080876f2947 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | Request Sign Off
70c5bd83-0677-5b3c-ab35-c394dec7eca5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 1.0 Excavation and Setouts | • Is the work area clearly pegged out for line and level?
94e7c4b0-5a0d-5a14-aea7-5d2ed5b25993 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 2.0 Construction Activities
154ef78a-b7b2-5d46-8761-ac5f1db8d9ad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 2.0 Construction Activities | • Are all pipes extended for the structural Soil install?
46dceba4-fad8-5f4c-9d28-25011dd3efc5 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 2.0 Construction Activities | Request Sign Off
b04fef3a-71ea-5566-9cb7-daca8a2bde04 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 2.0 Construction Activities | • Granular layer installed as per drawings?
86ff654b-aee0-5218-885e-10aa00d0b0be |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 2.0 Construction Activities | Request Sign Off
f947a54c-ca88-5a02-80df-00befa3627b9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 2.0 Construction Activities | • Structural Soil fill completed as per specified levels and quantities.
8d225ff5-910f-5b17-bae0-5d559120c46d |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Zone 6A | 26) Structural soil | SYM-PURL-SSL-6A-1 (6A - STRUCTURAL SOIL TRENCH) | 2.0 Construction Activities | Request Sign Off
475fe39c-ba67-433e-bfec-78b7021a8db3 |  | checklist-flat | not-started | Bluestone Wastage Record | checklist-flat | FALSE | FALSE | Construction | STAGE 2.1 | Bluestone Wastage Record
918ffe32-8bd5-54a9-9627-53a275f47541 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Bluestone Wastage Record | Bluestone Wastage Record
47bf594e-ce64-505b-b0e0-6bc603533693 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Bluestone Wastage Record | Sign-Offs Click to Attach Signature(s) below
386f2b12-d744-5a22-9913-6a7a9fd7c35d |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 2.1 | Bluestone Wastage Record | REQUEST SIGN OFF
e136990f-ac23-4e4f-a9bd-041e9b0208e9 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1
dc4c4fa9-8bde-4b91-ba50-14478b305b70 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D
0b16a16c-92ec-4dc0-8b65-36ffbb040cfa |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 1) ITP-001 - Subgrade Works
618775c9-4d92-4fca-9288-0ffe078a5d97 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 2) ITP-002 - Flexible Pavement Works
e5134e34-f4dc-419b-9369-26867bd2509e |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 3) ITP-003 - Asphalt & Sealing Works
df442483-5b7a-47f1-a46d-9b1bfeab1544 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 4) ITP-004 - Concrete Pavements Works
d3a39602-707d-40e3-9c84-7540d1c998c0 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 5) ITP-005 - Kerb and Channel Works
d73347c3-9df4-49e6-a41b-88c0467a08be |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 6) ITP-006 - Stormwater Works
725bc87c-fe79-465a-b871-912086c731f4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 7) ITP-007 - Subsurface Drainage Works
87c07553-8d7f-4f0f-a80b-15a4186ad30d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 8) Insitu Concrete Elements Works
ed745794-d15b-4802-b509-c849a3924c3d |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 9) Tactiles Works
b7e14814-02eb-4dab-bff9-9501588b574c |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 10) ITP-010 - Street Furniture Works
cd262260-c944-44fd-a224-6c866fcc5fe1 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 11) ITP-011 - Landscaping Works
3c3bf504-34dd-4142-b4a3-fd36828490fa |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 12) ITP-012 - Stratavault Works
9a604406-79b5-47ae-8349-f818589cb5a6 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 13) ITP-013- Walls and footings Works
8ee4b295-809b-4769-bbd5-67b94184a263 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 14) ITP-014 - Bus Shelter Works
edfe12cb-5d51-4c1d-8a8e-25e40bea61d2 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 15) ITP-015 - Heritage Works Works
4a008867-6e0b-4912-a451-0b881d4b00a4 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 16) ITP-016 - GPT Works
877202ac-7edc-4a4d-b63f-f43f458fa2ac |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 17) ITP-017 - Traffic Signals Works
335ef5af-b73b-4b6e-b396-50c5e2d78621 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 18) ITP-018 - Public Lighting Works
6d8909dc-2e96-4d6c-a642-a5c8ae25c3d2 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 19) ITP-019 - Cladding Works
36981fa4-260c-4a74-bcab-6620691c51fd |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 20) ITP-020 - Paving Works
7f45a4ee-1f6b-42b1-bbba-d6661ecaedc2 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 21) ITP-021 - Precast Concrete
95ff0518-9e11-46b6-9e61-a34dfa963431 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 22) ITP-022 - Linemarking Works
b9ae12f0-3dc2-4adb-860c-dd9c9db94670 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 23) ITP-023 - Signage Works
5b3cafef-0454-463f-bf8d-821effc50352 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 24) ITP-024 - Handrails & Balustrades Works
912fbcf5-bc6a-467b-9426-8eb8180a63b5 |  | folder-normal | no-status-not-started |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1D | 25) ITP-025 - Drinking Fountain Works
fd60414d-4923-47ac-aef6-1763953e99b6 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1G
e3384469-47eb-431e-9ee6-dbd5e2ad724d |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY)
6e06607e-6506-4bf0-a0e4-cee80ad28a64 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN
bd0027ee-bb3c-4dd3-b75c-1d1b55a3bff2 |  | checklist-sectioned | pass | SYM-ITP-001 - Subgrade Preparation (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A)
5e9b7dd9-dc7d-5d96-ae41-7d04f5e70f05 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries
234bfa81-16b0-54be-ae0b-813613996087 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | • What is the lot size?
7aff0be4-f47a-5b66-833a-4e86ee3e384a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | • Has the work area been set out for line and level?
638c9176-4c83-58b3-bc04-0235be5aca98 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
6a731ee2-d421-5cd6-a6d3-811faf8909c1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | • Has the material being excavated been inspected with category agreed upon by Superintendent?
91f19645-dd47-524c-a24e-3a9eea57d4f5 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
edcd1b2a-8265-5676-bca8-2b2ad67776db |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | • Has the material to be used been approved by CYP D&C JV?
3998b48f-a785-574a-ad05-8f5bd31357f4 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
463c2ab7-d0fc-5649-9fc8-a53c5663a277 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
e6bdc26f-f16f-5443-a4f7-63535f72b05e |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
3fc8dee7-c809-5289-a0ac-153752ef0050 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
610ccd0e-24d3-5801-95e3-365237eacb0b |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut
64b7343d-2d35-5373-8ffd-a32712bb83e1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • Has the cut surface been trimmed to an even surface free from lose material?
b56488b2-5ea7-54f7-a8a6-2c8e5cae5fe4 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | Request Sign Off
49fcecdf-3392-547b-99aa-2b4a0a307325 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action. Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
b63044b8-d67d-5a8f-96dc-e216cdac124c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
5a254195-0d99-5780-aa37-075a453bfca7 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | Request Sign Off
7661033f-38b2-5e57-b8b4-38732c3eebbc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • Compaction Scale B, CBR and Swell Testing per lot (3 tests per lot). Has the subgrade been adequately compacted achieving a mean value density ratio of 98% Standard?
d68c68a7-eb05-56e9-a594-f6d49595acca |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | Request Sign Off
3099865d-dfef-58aa-b60a-44e36cf5bf78 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • Does the layer withstand test rolling without visible deformation or springing?
d01d27ec-b5ea-5f97-80a2-b80545d30900 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | Request Sign Off
bea8eaca-db33-5621-8bd6-273d7da9c373 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • What quantity of soft, wet or unstable material is present?
76349da3-5798-5c65-87c2-4cac2262bcbe |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • Has rectification process been submitted to the Superintendent for review?
654b1933-f34e-50d4-b395-d35a56412705 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | Request Sign Off
3f9b1e9d-4893-5979-83ac-1ad3d14f756f |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
17060ba7-eeee-505f-a92b-016ff19500a8 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 2.0 Bulk earthworks - cut | Request Sign Off
ef33a911-634d-5fe8-8bcd-fd6779ab8b68 |  | checkpoint-group | not-applicable |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill
bc1f2221-d5c9-5baf-a208-dcdc22be0b86 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
5ed93cb7-552e-50cf-9aef-e33d62fa6f39 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | Request Sign Off
cf01ec12-ed86-50cd-a3cd-b689b51d43df |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • What quantity of soft, wet or unstable material is present?
59d8d56c-896e-5401-8582-302d7c72e3ed |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Has rectification process been submitted to the Superintendent for review?
d4533362-b722-5301-a376-42caf25fb2fc |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | Request Sign Off
d5a42971-0989-5e88-b4d1-208e6bcc6ae2 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
afb18388-4545-522e-bf2a-06501940a2d8 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Has fill been placed in maximum 200mm compacted layer thickness?
c7d96dfd-302f-5b60-9002-b772dcbd8dc7 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | Request Sign Off
2a8b562b-2dc6-59b5-8589-ee9153af9ae4 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction?
aaf2099e-fd60-5d7d-bf50-aeb1d3cd7fc9 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Compaction Scale B (6 tests per lot) Has the layer been adequately compacted achieving a mean value density ratio of 98% Standard?
8f410cf8-e932-59b6-9f8f-8ebae1039229 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | Request Sign Off
da424a00-5cff-5f85-a099-6b19844a1240 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041? If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested
4d152687-d023-51ce-8b22-095f19061008 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | Request Sign Off
908440fd-39a2-5271-aded-2803196aef45 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Does the layer withstand test rolling without visible deformation or springing?
c07698d3-e3c1-51f1-9620-737fd0d0486a |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | Request Sign Off
984db92f-b5f3-5e91-8842-b943b23574c9 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • What quantity of soft, wet or unstable material is present?
4ee3e5ee-0f8a-5c81-a66e-9d6ef4f36a12 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | • Has rectification process been submitted to the Superintendent for review?
3d4edaa7-afb6-5469-bc72-4330659cc809 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 3.0 Bulk earthworks - fill | Request Sign Off
a22bdfcd-4c73-5b0a-9d85-2a17b7aae98f |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check
d593d970-3273-5df1-b718-2a2b57859d90 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
ca4fcd73-3288-5f4b-9534-cd3c0254e600 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | Request Sign Off
f74f64fc-c9ec-5e1c-a707-13526b8bdc83 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements? Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm
6cbeff4d-f951-5572-a115-3ba73f9828cd |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | Request Sign Off
2e12f50a-c54e-5b0a-bb9b-837bfbcbae6c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | • All Test reports received and reviewed.
9f8e6b1d-a97c-5990-b902-f6c0e7188265 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | Request Sign Off
d01290a5-16d8-5371-9e6e-c3bf2f8bd245 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
da92e6d8-7f39-5b29-ade6-54315f78a215 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-SUB-1G-1 (Subgrade Preparation Rev A) | 4.0 Conformance check | Request Sign Off
7f54461c-16a6-4731-8631-6bade2d3e3da |  | checklist-sectioned | work-in-progress | SYM-ITP-002 - Flexible Pavements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A)
0a2a1858-168e-5585-bb90-b87dae2bfe0b |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries
b5948c1f-b56d-50d1-8c60-99bd622ee57c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • Has the work area been set out for line and level?
ccc94278-71a3-5b83-8e56-c7fe4207ab81 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • Has the previous layer passed acceptance criteria?
bbadd9ea-28ba-55c1-9f1e-95433f3feebd |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
9d891a2c-4cfd-5086-8fdd-72f54212c632 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • Is the correct material being used?
7f50110c-0ea2-57ea-ac5c-0418589ad908 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
4524dc61-d4a5-584b-b5c5-e3ea7d708dc4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • What is the lot size?
f9bae9a1-514d-5715-9a08-e423c266022d |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction
ec0923c4-c43b-5bfc-adfc-418962e70c82 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Is the pavement intended to be Lower Subbase or Upper Subbase?
c2614220-f7ca-5a8b-b0a2-af762729a24b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
53ffa4fc-f8a4-521b-9e2e-7eb8966ee14c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Place and compact layers so that the surface finish is smooth and uniform.
fe4bfabe-c055-57af-a687-b9a290d28e41 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
79784edf-1d24-518a-afa1-bce2eb3cc745 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
3a594af9-ae21-50a3-936c-084a62494dc9 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Area shall withstand test rolling without visible deformation or springing.
380f856c-e4f0-54f7-9408-7276690a87eb |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
835e56d2-e50f-5fee-ab28-747b2c2b2c69 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • What quantity of soft, wet or unstable material is present?
41295d26-2e92-55c8-97fd-948267a72481 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Has rectification process been submitted to VicRoads for Review?
ddf35a32-fc3d-5a78-b646-bf1b56f20d36 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
020a348d-6849-513d-9fc0-4481a0f48322 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
2b35bba9-2306-56a9-81d8-fc719a89b834 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
fb94cdbf-966a-5d2a-b5a1-3583e86587c8 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 3.0 Testing
417596d5-0180-5d58-a3d4-76bb87042ee7 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 3.0 Testing | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
967181ae-200d-5516-afe0-c4556be869ba |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 3.0 Testing | Request Sign Off
d9e7ac34-d5dc-5744-a633-d8de42dbe775 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 3.0 Testing | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
f2e028e4-45a9-5a74-8c80-721f0e52a4b0 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 3.0 Testing | Request Sign Off
a0f128d2-ab2e-5fe5-ac0d-6c67477395f0 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 4.0 Completion
2c114cb6-d096-512d-8845-1642b463f607 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 4.0 Completion | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
5584e83e-5d49-5af8-967f-5661a5c0f852 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 4.0 Completion | Request Sign Off
ba321dd8-1dc0-57e4-ad41-cc72fa75c6fb |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 5.0 Work Lot Close Out
861efc03-1cfc-5697-aad7-52aa3881afb4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 5.0 Work Lot Close Out | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
86ab9e4e-2ad3-585f-975e-5f825360c697 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-1 (Flexible Pavement Preparation Rev A) | 5.0 Work Lot Close Out | • All Product Non-Conformance(s) recorded and closed (if applicable)
f6445741-d261-480b-9e99-2f90e15ecdf3 |  | checklist-sectioned | work-in-progress | SYM-ITP-002 - Flexible Pavements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A)
81b50eac-8668-5134-a51e-b002391fc50f |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries
5a9bb8eb-f143-58dc-aab5-7817706dfae4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • Has the work area been set out for line and level?
24108fa9-959c-54ec-a425-6ba77a9ecc83 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • Has the previous layer passed acceptance criteria?
cbed93e3-d7d4-554d-b5fc-58b4209fa03f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
e81ceffd-871e-5922-897f-54732c81e4e9 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • Is the correct material being used?
a57de4e2-c854-5182-aa10-541d97a74375 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | Request Sign Off
a4c5aaf5-e4cf-58ce-8aeb-06dd6db433a3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 1.0 Preliminaries | • What is the lot size?
8ec5ef97-2945-557a-ab27-9f3dea9067e7 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction
f7ea840f-25e0-56fb-9ab1-a0c8bb272c5a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Is the pavement intended to be Lower Subbase or Upper Subbase?
5f8ca38c-9166-56be-820d-6826470aef9b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
609aca65-0e6e-51f1-abff-05f8a2314410 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Place and compact layers so that the surface finish is smooth and uniform.
84457b3f-775a-56be-945f-6b3eaa2136fc |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
84f691b5-0ed0-5328-b9fa-370e857fef21 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
4369c314-78e8-515c-867e-f6dfa5c14dd1 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Area shall withstand test rolling without visible deformation or springing.
245dff3a-5760-5300-aae8-598cae2582a7 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
9a57cef7-30e8-5823-9b6f-99e7b076626c |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • What quantity of soft, wet or unstable material is present?
0cd24839-940a-5d12-8a75-77d479bdf94e |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Has rectification process been submitted to VicRoads for Review?
77064a55-eddf-5059-8158-4795c6615861 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
6dece771-dcb5-5419-b729-0dd77316ee81 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
77d14be8-d35f-542c-a28d-c5a0201c94e2 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 2.0 Pavement Construction | Request Sign Off
7159d01d-d086-595d-a201-4cb5c09ef565 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 3.0 Testing
20597ef2-d628-51c3-ac8e-078c8cfa10db |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 3.0 Testing | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
caa94dd4-f4be-569a-9d8e-71aa3eb68651 |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 3.0 Testing | Request Sign Off
4abefc4b-fde0-5ed4-bd01-8072a6c82dd2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 3.0 Testing | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
71227a29-9357-569f-b75f-73efb6536b15 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 3.0 Testing | Request Sign Off
0cbfbc05-6777-5af1-8752-b22a283e3002 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 4.0 Completion
9ca7abdf-2806-5c6a-8206-4a0769606b7c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 4.0 Completion | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
ce35890d-7297-596b-ad40-b7b0e81476f5 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 4.0 Completion | Request Sign Off
f85cccae-6642-5e86-8aaa-70648d061b09 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 5.0 Work Lot Close Out
98e8d673-c51d-592d-8f67-dc66bd86a193 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 5.0 Work Lot Close Out | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
fe5c5525-04fc-5d2a-af4d-317933307c76 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-PURL-PFLX-1G-2 (Flexible Pavement Preparation Rev A) | 5.0 Work Lot Close Out | • All Product Non-Conformance(s) recorded and closed (if applicable)
1774dfea-9bec-4118-80fd-d61092da6424 |  | checklist-sectioned | pass | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course
13dca17c-b253-59bc-8602-fcf7896bf106 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities
82b039a6-878f-5fac-bc6a-c23a25b01e49 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | • What is the lot size?
83696324-8b46-5220-8458-d35ae81eaf11 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | • Is the asphalt mix design considered “General” and does it conform with VicRoads Section 407? Has mix design been approved by CYP D&C JV?
01d3636e-3129-5f5c-863f-87b1bd3dbf9e |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | Request Sign Off
5e5df357-abff-5f7c-b2e0-b746f4670b17 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | • Has the previous layer passed acceptance criteria?
cafa67ff-8025-5d6e-bbff-731fd6141e87 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | Request Sign Off
90ccc2dc-3d4e-52d4-9dd6-55e8cb318905 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | • For intermediate and base courses surface to be above 5 degrees Celsius. For wearing course installation, surface to be greater then 10 degrees Celsius. Has the above criteria been met?
addc9cbd-237a-5b97-a9c6-97fdc626bf1d |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | Request Sign Off
7802e8b9-36c8-562b-b2b9-bfe208ce4544 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 1.0 Pre-start activities | • Have the existing pits been raised/lowered to meet the surface level of Asphalt?
33c78cc4-252c-58fa-b8c7-8bc1146184df |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation
98b1330a-9042-5637-9719-e638ce75b75c |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from CYP D&C JV.
5d9a95d7-0bc5-584b-9f22-0dfce5d31c7b |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
5aabc0bd-e1a2-5981-9d5f-e9f9739aea78 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | • All transverse joints shall be offset from layer to layer by at least 2 m.
3db386fe-fc33-564c-9812-0ddcf02a91aa |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
8ee821d5-93a7-5e47-ae84-4984ca1a8e6a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | • At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
c8713810-6893-514f-9309-d2a7dd314ee4 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
1ed680c0-fca1-5038-b60a-a0fe02d43b16 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | • Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified. Asphalt shall be uniformly compacted Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
30d071c7-9f0b-5197-b4fa-7ce00d9774cf |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
ab5f35d0-7e69-5fc4-b299-c7aeb481b4f1 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 3.0 Completion and Compliance
cacc214b-d0d6-54a9-a3f6-d35167b46415 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 3.0 Completion and Compliance | • Thickness < 50 mm: 94.0% Characteristic Density Ratio
9892530d-44e1-5c66-b663-cbf9f3a2fc55 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 3.0 Completion and Compliance | Request Sign Off
d3886edc-4700-5b5b-bf3d-011d82282921 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 3.0 Completion and Compliance | • The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements (mean +/- 5mm, standard deviation 8mm)
74d675c1-4d02-5357-bbdd-de7a2e1cec55 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 3.0 Completion and Compliance | Request Sign Off
896433b3-9714-5652-949f-3c1c2052060b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Base Course | 3.0 Completion and Compliance | • Surface finish - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
56138106-40d7-4dc8-8c09-beafca51c408 |  | checklist-sectioned | pass | SYM-ITP-003 - Asphalt Placement 1 (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course
21d84058-42e9-5d89-bcfe-f280be2f27a2 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities
da433721-8002-5336-bdf2-33d37c1c069b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | • What is the lot size?
f1f23782-09c5-5519-8392-c7e8886e715d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | • Is the asphalt mix design considered “General” and does it conform with VicRoads Section 407? Has mix design been approved by CYP D&C JV?
2feeaaeb-dca5-5122-9345-21528791f049 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | Request Sign Off
324fed60-860b-5a91-bcc8-66f8542b5c76 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | • Has the previous layer passed acceptance criteria?
b1c985c4-2925-52c2-ae54-262542dea05c |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | Request Sign Off
3b7834d6-7fe5-5ff1-831f-969802874022 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | • For intermediate and base courses surface to be above 5 degrees Celsius. For wearing course installation, surface to be greater then 10 degrees Celsius. Has the above criteria been met?
b7625fca-d45e-58c2-a71d-a58f293b00ae |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | Request Sign Off
bfbfb1b7-d9cb-535a-9f0c-b66e94ea6a42 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 1.0 Pre-start activities | • Have the existing pits been raised/lowered to meet the surface level of Asphalt?
98d4efff-edf2-5683-8276-4e95a59c617d |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation
6b28ef7a-a1c6-56e2-beb3-881a95ee7dd2 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | • The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from CYP D&C JV.
28ab635b-fb18-5d51-9eb2-81cbcd8244a5 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
4878bb73-5376-538f-9b2a-adf087cf3fe3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | • All transverse joints shall be offset from layer to layer by at least 2 m.
09903696-c347-5dc2-93bd-31e917ce193f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
c3e4c6c4-ada6-5669-bc9d-9761ccc58dc3 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | • At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
52820015-5822-5e9d-b673-f4cbd8ea79c4 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
6d713385-4912-5bc9-b11c-36a6b493e284 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | • Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings or specified. Asphalt shall be uniformly compacted Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
ea53340a-4054-5f6e-88e4-f8746b857c1f |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 2.0 Hot Mix Asphalt Installation | Request Sign Off
8941dcf3-eecc-5beb-b3cf-8a9c9f3d04a7 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 3.0 Completion and Compliance
fda77e1e-7249-54fa-9f7f-a71a3ef09be6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 3.0 Completion and Compliance | • Thickness < 50 mm: 94.0% Characteristic Density Ratio
c6b950c8-e7c2-5b4b-896b-95440692a6bc |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 3.0 Completion and Compliance | Request Sign Off
4a8aa372-e753-5301-8b39-acc1c7f72338 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 3.0 Completion and Compliance | • The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements (mean +/- 5mm, standard deviation 8mm)
87ca281c-a772-53f3-bb3d-a1442615e1c3 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 3.0 Completion and Compliance | Request Sign Off
e71f15d6-777d-51e1-abbd-de77d388e235 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #1 (AMBO ENTRY) | 1G - FP4 - NEW MEDIAN | SYM-ITP-003 - Asphalt Placement 1 (Rev A) - Intermediate Course | 3.0 Completion and Compliance | • Surface finish - Uniform in appearance, free of dragged areas, cracks, open textured patches, and roller marks.
aa8bad0d-7b3d-47e9-975b-05389b16d480 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1
7a1c2e70-56e4-409f-aadc-4e6a8fac82d0 |  | checklist-sectioned | work-in-progress | SYM-ITP-018 - Public Lighting (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A)
c91f2192-f001-53f5-a32f-c10becde1553 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries
f36fe6bf-7de0-5ea1-adbb-d0fca24f2dcc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
637fa54c-05e2-559a-b291-f79c5c6d1853 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
f9ed5205-9a85-581d-b01f-1459de636f80 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation
5a595068-6bc2-5eb4-98e7-484ac662203a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting been constructed in accordance with the IFC Drawings?
e739ff94-fdd7-566e-b2e9-e5f532410cd9 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
8ebeae83-448f-56b8-9f1a-61ffecdc4e1e |  | checkpoint-status | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting passed all commissioning and testing?
dfcb90a6-3351-58db-8269-86c99ff4327b |  | holdpoint | work-in-progress |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
bd8489b4-9f2d-52c5-a6ba-6f33acdbd091 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Powercor inspection & approval provided?
42edf62d-c888-526f-8a54-fcb6c16e588f |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
2f1c6cbf-f0c6-5a96-a58a-dc0f30436465 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check
108a7f4c-324f-5305-83cb-1eb21ec99633 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed? Attach Test reports
4d8788b5-4842-596b-9dc5-125c191fd097 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-1 | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
d54c8095-920a-43a9-824a-5e2b52ff3d3b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1
e9bbddd9-2e48-43d8-b5cb-b88ecad90201 |  | checklist-sectioned | work-in-progress | SYM-ITP-017 - Traffic Signals (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A)
30787e5b-2fbb-5fc3-99ce-f7e7f26f2ee6 |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries
bea80976-df61-518e-a0ef-014ab54d4bc6 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
ca5bad98-0a70-5476-aaa0-7aaefd087b10 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
6478373f-2f82-5c4c-b579-64fb6bd52a4a |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation
6c4438b9-3fa2-5a40-9d6b-5a853d1ee4b4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has signalised crossing been constructed in accordance with the IFC Drawings?
a6182efe-b6ee-5984-a1f0-331303765ce2 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
e9f7f29e-d066-5ffb-8dd3-672a5711e791 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • Has Signalised crossing passed all commissioning and testing?
e47d0c98-7cc5-59ce-8ef1-1b151c1ccc32 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
d39fd9aa-a230-5ffb-92a5-693d60f046f2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | • DOT inspection & approval provided?
d1217cdf-de89-5f87-9a4a-e11f90d1598c |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 2.0 Traffic Signals Installation | Request Sign Off
224542de-e9c4-59ee-b1ca-9de50dcb3618 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check
15466e85-279e-5788-829d-c6114eef61fe |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed.
69cba27e-c5e3-558d-b507-3701c62d7cea |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-TRS-1G-1 | SYM-ITP-017 - Traffic Signals (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
9595537c-35a4-4070-a052-0ce5c7f8e91b |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2
c7c57edb-677e-4614-bcaf-e6efc129921f |  | checklist-sectioned | work-in-progress | SYM-ITP-018 - Public Lighting (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A)
79c6bbc4-517f-58c2-9bd1-563df5bb5b6a |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries
4f43934a-f5e4-574d-a244-81ae7b9c49cc |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the lot been defined and marked up on lot map?
e7130c7e-44a4-5fd7-bb82-ae1a85593cd4 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 1.0 Preliminaries | • Has the work area been set out as per IFC drawings?
19376ddc-9059-54af-bef1-03d6167dc9ef |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation
011e708e-540c-5014-ac09-aeba2078c73d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting been constructed in accordance with the IFC Drawings?
0b76bfa9-ea77-5dc8-bfbf-1c0ddce642ae |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
75587003-2164-5ab9-baef-b6bd497661d4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Has the public lighting passed all commissioning and testing?
b3b2750e-f3bb-544d-a8de-c5f524154cec |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
4d8ad9e5-ba78-56ba-b801-f1ff23decf69 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | • Powercor inspection & approval provided?
c63cebe8-7513-5048-9527-b98bec39c8fe |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 2.0 Public lighting Installation | Request Sign Off
b3dbd087-7ae9-55de-b3f9-35f244e48fe7 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check
e599a6c4-4c19-56ac-9477-6138d9b5e969 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Test reports and as builts received and reviewed? Attach Test reports
fd72fef4-f216-5d2d-aa11-e666cbc60aa6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | SYM-PURL-PUL-1G-2 | SYM-ITP-018 - Public Lighting (Rev A) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
676f73c3-c69b-43b5-aba7-84b2a73face3 |  | folder-normal | work-in-progress |  | step | TRUE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2
4451d96b-7110-45b9-8d70-f8259d630131 |  | checklist-sectioned | work-in-progress | SYM-ITP-001 - Subgrade Preparation (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade))
56f4e6aa-96d8-51c6-afbf-996493cabbca |  | checkpoint-group | pass |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries
c5849181-02f0-54a5-afdd-fc4456f4aa4b |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | • What is the lot size?
4da89c9c-5c6c-5806-b09b-164c9c07d1e5 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | • Has the work area been set out for line and level?
4f70f2be-e1b6-5c10-ac66-27aedc658219 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | Request Sign Off
c0662919-f99d-59b9-87b0-6b70407be708 |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | • Has the material being excavated been inspected with category agreed upon by Superintendent?
d9805608-40d8-5bd7-8863-3f120e1fbb0b |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | Request Sign Off
7d0c7b4d-d1d4-5345-b31b-180fc2eac121 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | • Has the material to be used been approved by CYP D&C JV?
39ed2dca-a69f-58f6-9d9b-58f43a9ecca5 |  | holdpoint | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | Request Sign Off
e55be30d-4c35-56d7-bb9f-4727f84a91e1 |  | checkpoint-status | not-applicable |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | • Where necessary, have batters been rounded and catch drains constructed to allow for potential surface runoff during the course of excavation?
a85e2eaf-e3d0-5185-b966-67bb636a304d |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | • 1A / 1B/ 1C/ 1D / 1E / 1F / 1G / 2A / 2B / 2C / 2D / 2E / 2F / 2G / 3A / 3B / 3C / 4A / 4B / 4C / 5A / 5B / 5D / 6A / 6B
ac023432-b2eb-5ad5-bc96-19dc48c555b2 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 1.0 Preliminaries | Request Sign Off
76662db0-517f-5ff7-ae3a-62ee88d95c78 |  | checkpoint-group | work-in-progress |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut
df22ff8c-0a8d-522f-b14c-90f8d983da4a |  | checkpoint-status | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • Has the cut surface been trimmed to an even surface free from lose material?
ae8316fb-5062-5e03-a6e4-b89e0f72cb93 |  | holdpoint | pass |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | Request Sign Off
f5316f40-b0d4-5df2-a0ce-df7e28634f71 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • If groundwater or seepage is encountered, notify the Superintendent and create a course of proposed action. Submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
f7de6b67-8a24-5401-b914-60391122a05d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • The in-situ material shall be ripped to a minimum depth of 150 mm, loosened and broken down to a maximum particle size of 50 mm. Any rocks or boulders larger than 50 mm shall be removed and any resulting depression shall be backfilled with approved material and such backfilling together with the loosened material shall be reworked and compacted as specified to the Cut Floor Level in preparation for test rolling.
0a95308b-4507-5312-944f-c80e27a0b5a8 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | Request Sign Off
b20d964e-66b7-5faf-8d3b-c9e0f775ae1a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • Compaction Scale B, CBR and Swell Testing per lot (3 tests per lot). Has the subgrade been adequately compacted achieving a mean value density ratio of 98% Standard?
08c2d860-ea71-5f13-9539-68e5dc85d890 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | Request Sign Off
7b3e66c0-cf32-5dff-a67f-c5f9a9f65d9a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • Does the layer withstand test rolling without visible deformation or springing?
312458a2-12aa-56c1-88be-9deed27023a6 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | Request Sign Off
6979f1a2-9690-5e72-aa04-ed6604dd98c7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • What quantity of soft, wet or unstable material is present?
272cd7a5-7cf7-54e9-a948-a30c38d29a5a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • Has rectification process been submitted to the Superintendent for review?
288d99c2-3e09-5909-8a40-129e2cd5cc43 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | Request Sign Off
a3cee588-ad8d-5639-a054-fc752ae7403f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | • Visual inspection to confirm that surface is a smooth, hard, tightly bound surface, free from depressions capable of holding water. Material within 150 mm of subgrade shall be maintained such that its moisture content is not less than 70% of optimum moisture content prior to the placement of any pavement layer.
4382f96b-659a-5eb0-9a1e-61377f64d573 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 2.0 Bulk earthworks - cut | Request Sign Off
8c7e8211-104c-5a0b-8932-71c3babba6dc |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill
d284568c-3a9c-5fd4-8598-4d6b502dd9a3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Does the stripped surface to be filled withstand test rolling without visible deformation or springing?
5ccca2ec-7837-5351-bf26-50ddaea6ffd0 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | Request Sign Off
4f27cf6f-2697-54f1-a0cc-4a1d9a5498f7 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • What quantity of soft, wet or unstable material is present?
17e2a5ec-d4c4-51a9-9470-b1d957125a41 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Has rectification process been submitted to the Superintendent for review?
b0c29160-62a8-543b-986a-6830de2155b3 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | Request Sign Off
48ee2c55-9020-526e-bae9-bd90793a8449 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Has adequate water been added to the stripped surface to ensure adhesion to the next layer?
405b2bcd-9eaf-5bc7-bccc-6fe2ea2fbb89 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Has fill been placed in maximum 200mm compacted layer thickness?
994c45ec-df08-58a1-82f1-200b7f9ad3ea |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | Request Sign Off
9e17f7a6-0c77-52eb-8a5c-4a9c57217ae8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Has the material maintained at optimum moisture content (>80%), with additional water being added if required during compaction?
fa81fdb1-4101-5f71-a8d7-cdb925398f77 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Compaction Scale B (6 tests per lot) Has the layer been adequately compacted achieving a mean value density ratio of 98% Standard?
9fe45918-030c-5162-9d34-d23658dbd66b |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | Request Sign Off
f3158d8e-3236-5289-b26a-00501afb5cd9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Has the material properties testing (CBR / Swell / Grading / PI / LL / Permeability) been undertaken for the first lot of material placement and satisfies the VicRoads requirements as per Table 204.041? If the first lot of each fill satisfies the specified post compaction requirements, every second lot of like material and work will be tested
8164b686-7af4-54db-805d-fd8fc57eeadb |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | Request Sign Off
e8de4118-fb85-50a0-9209-3479306a9dec |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Does the layer withstand test rolling without visible deformation or springing?
f48960c8-0aeb-5c07-bd13-310658b4cc0e |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | Request Sign Off
6c12686b-f841-5ce4-a79d-ed8806e7f271 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • What quantity of soft, wet or unstable material is present?
b2534759-326b-532f-bbd0-5df5e139536b |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | • Has rectification process been submitted to the Superintendent for review?
79a4434c-0c21-5b77-8d2c-c4bfbc039e0e |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 3.0 Bulk earthworks - fill | Request Sign Off
196390f4-5d17-5610-8b25-6e04a313a0a6 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check
0a7ca155-19ff-5dee-9661-048bccb180b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | • Has the pavement been constructed at the correct width and alignment as detailed in the construction drawings?
60e01ff9-27c3-5979-8590-be5179627310 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | Request Sign Off
678c494e-0efc-59d0-8b32-9bc317c600f9 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | • Has the prepared subgrade been surveyed in accordance with and verifying specified requirements? Mean Range: +5mm to -25mm Standard Deviation: Maximum 15mm
2b7f472b-c817-540c-ba5e-ed58ca94095a |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | Request Sign Off
3a22201f-7c31-5c1e-aac8-4dcfaa61d3f4 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | • All Test reports received and reviewed.
b2ff1280-89db-543b-9213-a5698d6c29a1 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | Request Sign Off
61f83e68-a654-5660-afb4-cb4f264c8971 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | • All Product Non-Conformance(s) recorded and closed (if applicable)
1e986765-73ce-5748-aea9-07fa7151a67a |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-SUB-1G-2 (1G - FP4 - #2 (Subgrade)) | 4.0 Conformance check | Request Sign Off
d509a7e1-a52f-4fb5-ba61-aaded410a0ca |  | checklist-sectioned | not-started | SYM-ITP-002 - Flexible Pavements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase))
512665ca-385c-5d01-9573-7126c2dd4087 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 1.0 Preliminaries
e79d028f-4d29-57ef-8a7b-7267a8451266 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 1.0 Preliminaries | • Has the work area been set out for line and level?
14ccfb98-d8e0-5d38-b6ae-32fe05b28713 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 1.0 Preliminaries | • Has the previous layer passed acceptance criteria?
180b0fe8-ea8e-574b-8688-bf00b8ba36c4 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 1.0 Preliminaries | Request Sign Off
ce3b969b-98d6-521d-b7b0-a16695307802 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 1.0 Preliminaries | • Is the correct material being used?
0f903c3e-9285-56d7-bf9e-767f0f572fb1 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 1.0 Preliminaries | Request Sign Off
714d17a0-baf3-5326-9c06-14054c33aeb8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 1.0 Preliminaries | • What is the lot size?
8a4eaff0-e4cb-5619-bf6f-8635dda9d8ec |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction
f3ed2e19-fd90-5367-b98b-e1b2a6ffbfc5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • Is the pavement intended to be Lower Subbase or Upper Subbase?
77c77003-8a49-527e-85e4-b66c82069da5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
e16b4190-991a-5598-8879-e814a78c7ab6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • Place and compact layers so that the surface finish is smooth and uniform.
658a598f-3b72-5e30-8a69-00361680f40a |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | Request Sign Off
a215fa74-558f-57c9-b62f-64dbeb7595b6 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
dc81bc55-c3d9-5e09-bcda-f48be29f45bc |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • Area shall withstand test rolling without visible deformation or springing.
535021d1-28e0-544c-99c7-df9cc395b9c1 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | Request Sign Off
b231f26c-507d-53ef-b34b-e6f72e87df92 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • What quantity of soft, wet or unstable material is present?
dbb41298-5cf1-5ce5-9576-6c4c65f2bf37 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • Has rectification process been submitted to VicRoads for Review?
22df82da-70b9-5512-9535-1a358adc11a3 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | Request Sign Off
db72c6e5-1039-59ae-863e-d47a66d06b0d |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
a126f8b7-0a3e-59a7-b053-0a987909b796 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 2.0 Pavement Construction | Request Sign Off
bb86a213-f594-5ce9-be71-91548aab00f5 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 3.0 Testing
aa88dbe8-b918-5ef5-bf98-acf38b0f4a2c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 3.0 Testing | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
c4e2d6a4-b2f5-5a25-9597-dd67923e65fc |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 3.0 Testing | Request Sign Off
4bb11c5b-c6bb-5a6a-9c00-7a24a3a413af |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 3.0 Testing | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
04341e19-03a5-59d0-883e-26d183c30a7f |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 3.0 Testing | Request Sign Off
5e682c5b-1b31-5df8-bba9-c9388cad5d33 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 4.0 Completion
3b260cae-299b-5175-a614-92a886f5c517 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 4.0 Completion | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
69561d5a-c9a2-52e5-b493-ac66916f4dc6 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 4.0 Completion | Request Sign Off
1a59e60b-7ce8-53b4-ba44-9058c6901df7 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 5.0 Work Lot Close Out
43649d2f-1cf3-5fc8-9a72-2e8a64204789 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 5.0 Work Lot Close Out | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
05729dd8-6071-559d-83b4-b2567e5d6aad |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.1 (1G - FP4 - #2 (Lower-Subbase)) | 5.0 Work Lot Close Out | • All Product Non-Conformance(s) recorded and closed (if applicable)
12cc851f-488a-46a6-8bf8-ef7afd42c58c |  | checklist-sectioned | not-started | SYM-ITP-002 - Flexible Pavements (Rev A) | checklist | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase))
fd6345af-f326-5022-b969-e5e220ea1abd |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 1.0 Preliminaries
5d19b127-50e4-5f3b-bec4-d1ba95746830 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 1.0 Preliminaries | • Has the work area been set out for line and level?
ae1b62f4-2eeb-50d4-933c-e2949dc3d9f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 1.0 Preliminaries | • Has the previous layer passed acceptance criteria?
ae7efd21-2666-559a-9fe1-752087c60b2f |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 1.0 Preliminaries | Request Sign Off
5b58b6d1-dba8-5182-8ba5-5ec04a8efe87 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 1.0 Preliminaries | • Is the correct material being used?
668f4e93-a7bc-5202-b680-2e5ea01f9e8f |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 1.0 Preliminaries | Request Sign Off
e353d46d-7112-546a-b5fa-2e4c47a337b0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 1.0 Preliminaries | • What is the lot size?
4e80a79e-eeb8-5228-8625-2387f8612233 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction
bb70b7c9-b767-56b9-bce6-d66eb0c51bae |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • Is the pavement intended to be Lower Subbase or Upper Subbase?
011c1954-4326-5110-b8b1-85196e9192d2 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • Transverse - Offset by not less than 2 m to any underlying pavement layers.
32443c38-f7ca-53ca-9afb-a827c8b73ee0 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • Place and compact layers so that the surface finish is smooth and uniform.
d269eab5-d33c-585d-ba36-68cbbb7b66ec |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | Request Sign Off
1552ce6a-7cc4-5a92-811d-7c56cbb182f5 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • Has the material maintained at optimum moisture content (>85%), with additional water being added if required during compaction?
a94e073b-f687-50a0-928c-ba03bc3e79d3 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • Area shall withstand test rolling without visible deformation or springing.
90b075ac-988d-50e6-a390-66f67694c80a |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | Request Sign Off
827d6d44-dc5c-5942-b011-7d9ce679be9f |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • What quantity of soft, wet or unstable material is present?
3023846e-9251-5a9c-81e2-90744ebaf0a8 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • Has rectification process been submitted to VicRoads for Review?
19011b78-dedd-5e05-b35b-bb620b28961b |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | Request Sign Off
c9b61fab-6ca4-5a7e-803b-05a3b7c12b2c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | • Surface of each compacted layer in good order/condition & free from contamination until the subsequent pavement work is to commence.
690a794b-e086-50c5-b8af-4a4d9fde42f6 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 2.0 Pavement Construction | Request Sign Off
91da36ec-3e86-51e3-ab7b-c4f551973aed |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 3.0 Testing
e7e2ec61-c37d-5bd1-91d1-33cf11007645 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 3.0 Testing | • Characteristic Density Ratio % (six tests per lot): Not less than 98.0% Modified (Scale A)
d91100ba-49a7-5e2f-8023-71d6f1de01d2 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 3.0 Testing | Request Sign Off
6b7ea196-4864-577d-8cf8-4125c99e845c |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 3.0 Testing | • Test every lot for acceptance until three consecutive lot of like material and/or work have passed the requirements.
cebee324-6f7f-5a3d-b3a1-4a9549214b41 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 3.0 Testing | Request Sign Off
a9bfb8dc-dcc0-5235-a03c-51018d5c32d4 |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 4.0 Completion
7b89e7de-0107-5e83-a48a-2ebc15cc2f46 |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 4.0 Completion | • Surface after completion shall be smooth and uniform, free of segmented areas and conforming to grade, thickness and cross-section shown on the drawings.
209ba354-9cf8-5b4a-90d4-6ba9c6663499 |  | holdpoint | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 4.0 Completion | Request Sign Off
cfc6c828-c254-5e45-9053-b7633ead350e |  | checkpoint-group | not-started |  |  | FALSE | FALSE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 5.0 Work Lot Close Out
d1e745c8-e917-583b-b0f2-d2da5ca16d8a |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 5.0 Work Lot Close Out | • All Test reports received and Reviewed as per Requirements for Testing and Acceptance of Surface Level Measurement, Compaction and Post-compaction Gradings and PIs (Clauses 304.06, 304.08, 304.10 and 304.11)
2a1d6744-e7f7-5624-baf3-25a8bf0616fa |  | checkpoint-status | not-started |  |  | TRUE | TRUE | Construction | STAGE 1 | ZONE 1G | 1G - FP4 #2 | SYM-PURL-PFLX-1G-2.2 (1G - FP4 - #2 (Subbase)) | 5.0 Work Lot Close Out | • All Product Non-Conformance(s) recorded and closed (if applicable)
b498ce7f-0b67-4885-a2da-cac1948301ef |  | folder-normal | pass |  | step | TRUE | FALSE | References
08cfd0a7-af68-445a-a871-85d37564017d |  | folder-normal | pass |  | step | TRUE | FALSE | References | PAPER BASED ITPS
29bb81c4-c093-42f0-b8d7-78a5c15de281 |  | checklist-flat | pass | Document Upload Checklist | checklist-flat | FALSE | FALSE | References | PAPER BASED ITPS | Document Upload Checklist
72f57667-d4d5-5c1c-9953-b7018348010e |  | checkpoint-status | pass |  |  | TRUE | TRUE | References | PAPER BASED ITPS | Document Upload Checklist | Document uploaded below
8282ca41-e903-44da-86ff-db2a9f951241 |  | folder-normal | pass |  | step | TRUE | FALSE | References | VICROADS SPECIFICATIONS AND DRAWINGS
86b21a0b-3edb-4a12-8775-d7941c9e6f1d |  | checklist-flat | pass | Document Upload Checklist | checklist-flat | FALSE | FALSE | References | VICROADS SPECIFICATIONS AND DRAWINGS | Specs
8bdd51f1-d212-5146-998a-e209346edbfe |  | checkpoint-status | pass |  |  | TRUE | TRUE | References | VICROADS SPECIFICATIONS AND DRAWINGS | Specs | Document uploaded below
c5d0d756-73c2-451e-a844-526c3fc9d787 |  | checklist-flat | pass | Document Upload Checklist | checklist-flat | FALSE | FALSE | References | VICROADS SPECIFICATIONS AND DRAWINGS | Drawings
aeea1d03-1e5e-547a-9d1a-b2e13fad7f6a |  | checkpoint-status | pass |  |  | TRUE | TRUE | References | VICROADS SPECIFICATIONS AND DRAWINGS | Drawings | Document uploaded below
9340e3f0-f659-4394-b318-22af3e6a841e |  | folder-normal | pass |  | step | TRUE | FALSE | References | CITY OF MELBOURNE SPECIFICATIONS AND DRAWINGS
e1bd75af-4914-4105-8445-eb04228b796a |  | checklist-flat | pass | Document Upload Checklist | checklist-flat | FALSE | FALSE | References | CITY OF MELBOURNE SPECIFICATIONS AND DRAWINGS | Specs
45013012-efb1-5a6b-bd2e-9c71ee66c69c |  | checkpoint-status | pass |  |  | TRUE | TRUE | References | CITY OF MELBOURNE SPECIFICATIONS AND DRAWINGS | Specs | Document uploaded below