## Breakdown
PROJECT BREAKDOWN
Waterproofing Concepts - Riccarton Park (Kevin Hickman)
Project Build QA
Stage 5 - B03
|  |  | Pre-populate | ST - S - Epoxy
|  |  | Pre-populate | TPO - Viking Roof membrane system

## Checklist
checklist-flat | ST - S - Epoxy
checkpoint | Applicators
text | Area:
checkpoint | Surface and preparation completed
checkpoint | Method of preparing joints or cracks
checkpoint | Hypalon tape used, type and strength
checkpoint | Sikadur 31 number of units and last 6 digits of batch number (Attach confirmation Photo)
checkpoint | Weather and Temperature
text | Weather conditions and temperature in Celsius
checkpoint | Surface temperature
text | Surface temperature in Celsius
checkpoint | Sarnafil Roof
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
type | name | values
checklist | TPO - Viking Roof membrane system
Section | Roof Membrane
checkpoint | Correct drawing revision referenced and attached
text | Drawing number(s) & Revisions
checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
bool | Plywood substrate checked and accurate
checkpoint | Moisture check to substrate before Enviroclad to be installed / checked and accurate/ documentation, photos attached
checkpoint | Hatches checked and accurate (2-4 Photos attached)
checkpoint | Area left clean and tidy
checkpoint | No Damages to membrane (cuts & holes)
checkpoint | Work completed, reviewed and approved
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Section | Internal Gutter
checkpoint | Correct drawing revision referenced and attached
text | Drawing number(s) & Revisions
checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
checkpoint | Gutters checked and accurate (2-4 Photos attached)
checkpoint | Screw heads and ply joints all flush (2-4 Photos attached)
checkpoint | Correct fall (2-4 Photos attached)
checkpoint | Membrane checked, Lapped and accurate (2-4 Photos attached)
checkpoint | No bubbles or bulges (2-4 Photos attached)
checkpoint | All joints sealed and accurate (2-4 Photos attached)
checkpoint | Water test done and results attached
checkpoint | Area left clean and tidy
checkpoint | Work completed, reviewed and approved
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS