## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Waterproofing Footing Base - GPL-QSE-ITP-WPF (Rev 00)
section | Prior to Works Commencing
checkpoint | Work area and surfaces clean and clear ready to commence work
checkpoint | Jackhammer pile concrete to finish 50mm above blinding slab level, ensure flat surface with vertical edge at perimeter for waterproofing
checkpoint | Confirm Structural Engineer acceptance of waterproofing detail
checkpoint | Confirm Waterproofing products to be used, confirm Waterproofing Third Party Engineer signoff of products suitability
checkpoint | Confirm all concrete defects have been actioned and surface inspected/accepted by Subcontractor, Waterproofing Third Party Engineer, and product manufacturer
section | During Works
checkpoint | Confirm product used is as per design
label | Refer Product Specification, Architectural Waterproofing drawing, and Waterproofing IFC Design Compliance Report
checkpoint | Apply the membrane so the adhesive surface is facing the concrete footing, ensure joints are installed to product specification
checkpoint | Apply waterstop plug to vertical edge of piles, ensure no gaps
checkpoint | Apply waterproof membrane to top of pile, covering reinforcement bar and turning up reinforcement bar by over 30mm
checkpoint | Ensure all edges and overlaps are properly sealed and protected
checkpoint | After Concrete Footing Pour: Lap over membrane from base and complete wall membrane termination detail
label | Refer Product Specification, Architectural Waterproofing drawing, and Waterproofing IFC Design Compliance Report
section | After Works
checkpoint | Confirm inspection and testing of joints by Waterproofing Third Party Engineer
label | If failure occurs, rectify issue and retest
checkpoint | Apply dimple board protection to membrane prior to back-filling
checkpoint | Confirm back-filling material and complete as per Structural Engineer detail
checkpoint | Attach subcontractor ITP
section | Sign Off
checkpoint | Orwell Sign Off
label | Authorised By: DL
label | Issue Date: 07.08.2025
holdpoint | Request Sign Off