## Table 1
Inspection and Test Plan
Project: |  | Korimako Avenue Stormwater Main Renewal |  |  |  | R0: 10/06/25 | Role | Person(s) Responsible
Job nr |  | 25049 |  |  |  |  | Project Engineer | Norbert Jacsek
Location: |  | Korimako Avenue Otatara, Invercargill |  |  |  |  | Operations Manager | Bryan Duggan
Action |  | Witness | W | WCL | Wilson Contractors (2003) Ltd | Activity by | Contract Manager | Hamish Lindsay
|  | Hold Point | H | ICC | Invercargill City Council |  | ICC Engineers Representative | Tom Andersen
|  | Monitor | M | Lab | Independent testing agent |  | ICC Engineer | Rob Hayes
Print, sign and date
No | Contract Spec # | Inspection / Test Point | ACTION (W, M, H) | Activity by | Conformance Criteria (What's Required) | Quantity | Frequency / When? | Inspection / Test Method | Records / evidence, WCL form | Standard | Wilson | ICC
Contract
1 | D1.3 | Site Management Plan (QEHS, SSST, KSA) | H | WCL | Ensure Quality, Environment, Health & Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times. | — | Prior to commencement | Submission (NTE) | Sign This ITP LN-01, FM-83, FM-69 | ICC STANDARD SPECIFICATIONS | YES | YES
2 | D1.18 | TMP | H | WCL | traffic management plan to be submitted and approved by Road Controlling Authority | — | Prior to commencement | Sumission (NTE) | Sign This ITP TMP | Code of practice for temporary traffic management (CoPTTM) | YES | YES
3 | D1.4 | Works Access Permit | H | WCL | TMP and Corridor Access Request to be sumbitted on myWorksites | — | Prior to commencement | Document | Sign This ITP WAP | — | YES | YES
4 | D1.14 | Client start-up meeting | H | ICC, WCL | — | — | Prior to commencement | Document | Sign This ITP MoM | ICC STANDARD SPECIFICATIONS | YES | YES
Production
5 | D2.4.2 | Bedding material | W | Lab | Material to comply with contract specification | 280 m3 | Prior to commencement | Lab report | Grading Results | ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2 | YES | YES
6 | D1.29.3 | Sub Base Aggregate AP65 | W | Lab | Materials to comply with contract specification | 90 m3 | Prior to commencement | Lab report | MDD and Grading Results | ICC STANDARD SPECIFICATIONS | YES | YES
7 | D1.29.4 | Crushed Basecource Aggregate M/4 AP40 | W | Lab | Materials to comply with contract specification | 22 m3 | Prior to commencement | Lab report | MDD and Grading Results | ICC STANDARD SPECIFICATIONS NZTA M/4 | YES | YES
Pre Construction
8 | D1.5 | Pre-work site inspection | H | WCL | Video or photos near the construction zone to determine their pre construction condition. (landowners property) | — | Prior to commencement | Inspection Document | Sign This ITP Video Photo | ICC STANDARD SPECIFICATIONS | YES | YES
9 | D1.18 | Temporary traffic management | H | WCL | Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer. | — | Prior to commencement | Visual inspection Document | Sign This ITP On-site record | ICC STANDARD SPECIFICATIONS CoPTTM | YES | YES
10 | D2.7.1 | Set out | W | ICC, WCL | Mark out of alignment for mains and laterals | — | Prior to commencement | Surface marking | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
11 | D1.8 | Protection and identification of other Services | H | WCL, asset owners | Mark out on site of all services. Services to be potholed for as per Wilsons company policy | — | Prior to commencement | Surface marking Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS Wilson's prior to excavate policy | YES | YES
12 | D1.11 D9.5 | Notification to residents and businesses | M | WCL | Letter drop / business visits | — | Prior to commencement (min. two working days prior to water shutoff or access restriction) | Document delivered | Sign This ITP Notification letter | ICC STANDARD SPECIFICATIONS | YES | YES
Stormwater main
13 | C1.4 D2.4.1 | Pipe material (main) | M | WCL, ICC | DN450 RC JR Class 4 ICC to inspect pipe deliveries as required | 360 m | 1 / delivery | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS AS/NZS 4058:2007 | YES | YES
14 | D4.3.1 | Pipe material (lateral) | M | WCL, ICC | DN100 uPVC SN6 RRJ | 32 m | 1 / delivery | Visual inspection | Sign This ITP | AS/NZS 1260:2017 | YES | YES
15 | D4.3.1 | Pipe material (sump lead) | M | WCL, ICC | DN150 uPVC SN8 RRJ DN225 uPVC SN8 RRJ | 45 m 35 m | 1 / delivery | Visual inspection | Sign This ITP | AS/NZS 1260:2017 | YES | YES
16 | D2.7.2 | Excavation | M | WCL | The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed. | 472 m | continuous | Visual inspection Levelling | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
17 | D13.4.3 | Subgrade inspection | M | WCL, ICC | To determine if improvements are required | 472 m | Prior to placement of bedding | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
18 | D2.4.2 | Free draining material | M | WCL | pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed | 0 - 360 m | Continous, in accordance with observed groundwater conditions | Secific approval should be given by the Engineer | NTE, NTC | ICC STANDARD SPECIFICATIONS | YES | YES
19 | D2.7.3 | Pipe installation (main) | M | WCL | +/- 30mm (horizontal) +/- 5mm (vertical) | 360 m | Continous (pipe laser) 1/20 m (independent optical level) | Using calibrated pipe laser Optical levelling | Sign this ITP leveling record | ICC STANDARD SPECIFICATIONS | YES | YES
20 | D4.4 | Pipe installation (lateral) | M | WCL | grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 manhole: gritted manhole finisher Connection at boundary: slip coupler/plumbqwik | 3 (to 600 mh) 7 (to main) 1 (to 1050 mh) | Continous | Measurement Document | Sign this ITP Detailed Drainage Connection Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
21 | D4.4 | Pipe installation (sump lead) | M | WCL | grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 mh / yard sump: gritted manhole starter / finisher | 3 (to 600 MH) 3 (to main) | continous | Measurement Visual inspection | Sign This ITP | — | YES | YES
22 | D2.7.6 | Bedding (main) | M | WCL | lb (depth below): min 150 mm lc (width beside): min 300 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | 360 m | continuous | Measurement Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES
23 | D2.7.6 | Bedding (lateral) | M | WCL | lb (depth below): min 75 mm lc (width beside): min 100 mm lo (depth above): min 100 mm compacted layers not exceeding ⅓ of the pipe OD | 32 m | continuous | Measurement Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES
24 | D2.7.6 | Bedding (sump lead) | M | WCL | lb (depth below): min 100 mm lc (width beside): min 150 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | 80 m | continuous | Measurements Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES
25 | D18 Fig. D12 | Manhole (D1050) | M | WCL | 1050mm The sump shall be at least 300 mm from the underside of the lowest invert level. neck depth ≤ 315 mm in-situ concrete packing | 7 | 1 / manhole | Measurement Levelling Document | Sign this ITP Manhole Inspection Sheet | NZS 3109:1997 | YES | YES
26 | D18 | Manhole (D600) | M | WCL | CIRCULAR SUMP+INTERNAL BASE 600.900.100MM 600 mm cover Class D connection to the main: D225 uPVC | 3 | 1 / manhole | Measurement Levelling Document | Sign this ITP Manhole Inspection Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
27 | D18 | Yard sumps | M | WCL | Flat top concrete sump box 450x450x1200 Cast Iron sump grate + frame 450x450 D150 sump lead | 5 (1 existing is to be reconnected) | 1 / yard sump | Measurement Levelling Document | Sign this ITP Manhole Inspection Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
28 | D15 | Service covers | W | WCL, ICC | HN-HO-72 d600 mm, 450x450 mm Cover levels to be adjusted to existing ground levels | 7 grated 600 3 solid 600 5 grated 450x450 | before surface reinstatement, landscaping | Visual inspection Measurement | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
29 | D2.9.3 | CCTV Inspection and Cleaning | H | WCL | to confirm that the lines are free from debris and have no defects | 360 m (main) | prior to the final surface reinstatement | CCTV inspection | Sign this ITP CCTV survey | New Zealand Pipe Inspection Manual AS/NZS 2566:2 | YES | YES
30 | — | Removal of existing pipelines and manholes | W | WCL | DN150 EW Excavation may include the removal of existing redundant mains located within the trench extents. | max 360 m + 10 manholes | during main installation (parts of Southern Korimako alignment) | Visual inspection | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
31 | D2.10 | Abandonement of existing pipelines by filling | — | WCL | DN150 EW Filling material and methodology for execution shall be approved by the Engineer. Ensure there are no active connections to the main | 15 m3 | following new main installation (Northern Korimako alignment) | Visual inspection Document | Sign this ITP Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES
32 | D2.7.7 | Backfilling and compaction (existing, excavated material in berm) | M | WCL | All backfill material layers shall be placed and compacted in layers with appropriately sized mechanical compaction equipment to achieve uniform compaction for the full depth. This shall be in compacted layers not exceeding 200mm depth | 240 m | continuous | NDM testing: not required Clegg testing: not required | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
Surface reinstatement
33 | D13 | Landscaping | W | WCL | The final surface in the berm area is to be re-graded, with new sump manholes and yard sumps established as the low points. | 240 m | following new main and lateral installation | Visual inspection Levelling | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES
34 | D13.7 | Grass seeding | W | WCL | approved seed mixture, 35 g/m2 | 240 m | following landscaping between the months of September - April | Visual inspection | Sign this ITP Blending docket | ICC STANDARD SPECIFICATIONS | YES | YES
35 | D2.7.7 | Subbase (AP65) compaction | H | WCL | Carriageway: 0.3 - 1.5 m deep: min 35 CIV > 1.5 m deep : min 25 CIV | Culvert + ch 240 - 329 ch 87, 139, 220, 224, 253, 295 | During installation, every 200 mm layers at 5 m intervals for all trenches in carriageway above main and connections | Clegg test | Sign This ITP Clegg Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
36 | D2.11.5 | Subbase (AP65) compaction | H | WCL / Lab ICC | 95% compaction rate It is not required to complete NDM testing on connections. | Culvert + ch 240 - 329 = 95 m | At pipe laying commencement and reconfirmed at 120m intervals for open trench every 200 mm layers | NDM test (direct transmission) | Sign This ITP NDM Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
37 | D2.7 | Basecourse (AP40) compaction | H | WCL / Lab ICC | 98% compaction rate It is not required to complete NDM testing on connections | Culvert + ch 240 - 329 = 95 m | 1 / 20 m of trench including one test at the start and end of the trench | NDM test | Sign This ITP NDM Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES
38 | D2.8.3 | Trench reinstatement - marking out saw cutting | H | ICC | Engineers rep to mark out saw cutting required (overcuts) | 6 m: Marama 79 m: Kori | Prior to sealing | Visual inspection, measurements (1 m rule) | Sign This ITP | ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors | YES | YES
39 | D2.7.7.2 | Basecourse (AP40) geometry | H | WCL, ICC | -5 mm +15 mm h = 45-65 mm (carriageways) h = 25-45 mm (footpath) | Culvert + ch 240 - 319 = 85 m +5 cross | Prior to sealing | Visual inspection String line / straight edge inspection | Sign This ITP Pre seal inspection record (FM-114) | ICC STANDARD SPECIFICATIONS NZTA B/2 | YES | YES
40 | D11.4.3 | Membrane Seal | H | WCL, ICC | Residual bitumen application rate ≥ 1.5 l/m2 | Culvert + ch 240 - 319 = 85 m | Prior to asphalting | Visual inspection | Sign This ITP, Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES
41 | D12.5 | Asphalt paving geometry | H | WCL, ICC | 5 mm from a 3 m straight edge laid longitudinally 5 mm from a 1 m straight edge laid transversely | 85 m | 1 / finished surface | Post seal surface inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES
42 | D2.8.3 D12.3.1 | Asphalt paving material | W | WCL, ICC | DG10 (carriageways) | 13 t | — | Document | Sign This ITP Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES
43 | — | Road markings | W | WCL, ICC | Reinstatement of the existing markings | — | 1 / finished surface | Post seal surface inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | N/A | N/A
Completion
44 | D17 | As-built information | H | WCL | Encountered Services Record Sheet Detailed Water Connection Sheet As-built drawings as per D17 | — | Following/during completion of works | Document | Sign This ITP DWCS, ESRS, As-built | ICC STANDARD SPECIFICATIONS | YES | YES
45 | — | Site walkover | H | WCL, ICC | Snag list to be compiled, and completed | — | At Completion | Review | Sign This ITP SNAG List | — | YES | YES
Wilsons Engineer Wilsons Contract Manager ICC Engineers Representative Signed By : Norbert Jacsek Accepted By : Hamish Lindsay Accepted By : Tom Andersen Signature: Signature: Signature: