## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-282-Civil-PSSD-Traffic Signal Installation
ITP Description: |  | Traffic Signal Installation
Project: |  | Progress Street
Discipline (e.g. CIV/STR/RAIL: |  | Civil
Revision Number: |  | 0
Revision Date: |  | 2025-05-14
ITP created by: |  | Romualdo Magpantay
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP to be used at Progress Street Project Only
Inspection & Test Plan - Traffic Signal Installation
|  |  | Document Title: ITP-282-Civil -PSSD-Traffic Signal Installation | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-05-14
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | VicRoads Specification | VicRoads Section 730 October 2013 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Australian Standard - Methods of testing soils for engineering purposes | AS3000 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Vic Roads Site Plan | L1-CHE-SPE-178 - Clause 5.10.1. Australian Standard - AS1289 | Scope of works, equipment requirements and placement of equipment shall be as shown on the VicRoads Site Plan | Review Document | Prior to works commencement | IP | SE/PE | This ITP Signed Off : Attach: VicRoads Site Plan
2.2 | Subcontractor Prequalification | Section 730.01c | All works associated with the installation and commissioning or remodel of trafic signals shall be undertaken only by contractors that are pre-qualifed at the STS level under the VicRoads contractor pre-qualification scheme. | Review Document | Prior to works commencement | IP | SE/PE | This ITP Signed Off Attach Subcontractor Prequalification Certificate
2.3 | Material Fabrication and Supply - Traffic Signal Hardware | Section 730.05 | The fabrication and supply of all components for tratraffic signal works shall conform to all relevant VR Specs and Aus Standards. To comply with: VR 'TCS' series specs, VR 'TC' series specs, AS1742, AS/NZS3000 and Victorian Service and Installation Rules Team Binder Material Approval No. | Review Document | Prior to works commencement | IP | SE/PE | : Issue to TB and Attach Material Certifiate
2.4 | Equipment to be supplied by VicRoads | Section 730.06 | VicRoads will supply or arrange for the supply of the following items: (a) the tra昀케c signal controller and associated vehicle detector units (b) communication devices, such as Dial-IP modems (c) ‘DUSC’ units. Contractor to provide VR a list of materials at least 20no. working days before delivery is required. | Review Document | Once | IP | SE/PE | This ITP Signed Off
2.5 | Equipment to be supplied by the Contractor | Section 730.07 | Contractor shall be responsible for the supply of all equipment, items and peripherals required for the completion of the works Where applicable, all equipment proposed for use shall hold current VicRoads ‘Type Approval’ certi昀椀cation or Product Acceptance. Refer to Item 2.3. All equipment, materials and 昀椀ttings supplied by the Contractor are to be new. Contractor to ensure equipment used is compactible with all equipment TB Material Approval No. | Review Document | Once | IP | SE/PE | : Issue to TB and Attach Material Certifiate
2.6 | Concrete Mix | Section 730.12 a) | Concrete shall comply with AS1379. Concrete grade to be as per relevant Vic Road Standard Drawings. TB Material Approval No. | Review Document | Prior to commencement | IP | SE/PE | This ITP Signed Off Issue to TB and Attach Material Certifcate
2.7 | Material Fabrication and Supply - Electrical components | Section 730.14 | : All electrical works, conduits, Fittings, materials and installations shall comply with the requirements of AS/ NZS 3000 Wiring Rules for all traffic signal related works | Review Document | Prior to commencement | IP | SE/PE | This ITP Signed Off Issue to TB and Attach Material Certifcate
3 | Pre-Construction /Pre Installation Activities
3.1 | Pre-Installation Meeting | Section 730.08 (b) | The Contractor shall mark the position of pedestals, poles, controller bases, pits and conduits in accordance with the drawings, in the presence of and with the approval of the Nominated Authority, Vic Roads, service authority and others as appropriate. On satisfactory completion of the pre-installation meeting, the Superintendent will issue to the Contractor a copy of the PreInstallation Report. The Contractor shall not commence installation of the trafficc signal pedestals, poles, controller bases or pits until the Pre-Installation Report has been approved. | Record | Prior to works commencing | HP | PE, NA and VR Representative | This ITP Signed Off Attach Pre-Installation Report
3.2 | Service Proving prior to commence of new works | Section 730.09 (a) | The Contractor shall be responsible for locating and proving all underground and overhead services. Any consultation with, and authorisation required from, other authorities under relevant utility regulations and codes shall be the responsibility of the Contractor. | Review | Prior to commencement of fworks | IP | SE/PE/SPE | This ITP Signed Off
3.3 | Survey Set-Out | IFC Drawings Works Agreement Section 730.11 | Survey to mark out works as per IFC Drawing. As per Item 3.1 VR to inspect the set out of Pits and Conduits for Traffic Signals prior to commencement of works. No part of the signal hardware is to be closer than 500 mm behind the face of the nearest kerb line, or closest vehicle path if no kerb is present. The minimum clearance of 5.5 m shall be achieved between the lowest part of a lantern installed on an outreach and the roadwa directly beneath it. | :Visual | Each item | HP | Surveyor, SE, VR | This ITP Signed Off
3.4 | Material Inspection | Design Drawings Section 730.05 | Supplied items are: To correct spec, class, size and quantity Defect free, safely and securely stored | Record | Per delivery | IP | SE/PE/SPE | This ITP Signed Off
4 | Traffic Signal Civil Works
4.1 | Conduit Installation | Section 730.09 Section 733 TP-CIV Conduit and Pit (Roads) | All electrical conduit installation works for traffic signals must be carried out by, or under the direct supervision of, a VicRoads pre-qualified traffic signal Contractor and in accordance with the requirements of Energy Safe Victoria. All communication conduit installation works are to be carried out under the ‘on site’ supervision of a licensed cabler | Review Documents | Prior to commencement of works | IP | SE/PE/SPE | This ITP Signed Off Attach Subcontractor Prequal Documentation
4.2 | Pit Installation | Section 730.09 TP-CIV Conduit and Pit (Roads) | All cable pit installation works for traffic signals must be carried out by, or under the direct supervision of a VicRoads pre-qualified traffic signal Contractor and in accordance with the requirements of Energy Safe Victoria. | Visual | Prior to commencement of works | IP | SE/PE/SPE | This ITP Signed Off Attach Subcontractor Prequal Documentation
4.3 | Foundations | Section 730.11 | : Foundations shall be constructed in accordance with the drawings and as approved at the Pre-Installation Meeting. Foundations and footings shall be as speci昀椀ed in the VicRoads Standard Drawings for the speci昀椀c item of equipment they are to support, as listed in Table 730.111. The standard foundation for an MA, JUMA and JUP shall be a bored pile. | Visual | Prior to commencement of works | IP | SE/PE/SPE | This ITP Signed Off
4.4 | Inspection of civil works | Section 730.11 | All conduit, pit and foundation works shall be inspected by the Nominated Authority and Vic Roads prior to the Contractor covering the works | Visual | Per lot | HP | SE, NA and Vic Roads Representative | This ITP Signed Off
4.5 | Concrete Placement | Section 730.12 b AS1012 AS1379 ITP-CIV Bored Pile | Where concrete is placed in a bore hole, it shall be compacted with immersion type, high frequency vibrators. Concrete shall be placed through a tremie tube, shall not be dropped from a height greater than 2 m and shall be guided away from reinforcement | Visual | Per lot | IP | SE/PE/SPE | This ITP Signed Off Attach Concrete Dockets , Attach Bored Pile ITP
4.6 | Concrete Testing | 730.12 c) & d) | All grade 32MPa concrete shall be sampled and tested in accordance with AS 1012 and AS 1379. 1no. cylinder to be tested at 7 day and 2no. Clynders to be tested at 28 days. | Review Documents | Per lot | IP | SE/PE/SPE | This ITP Signed Off Attach Concrete Test Report
5 | Traffic Signal Hardware
5.1 | Standing of Pedestals and Poles | Section 730.13 a) SD TC-1201 Design Drawings | Pedestals and poles shall be installed in accordance with the design drawings and relevant specifcations. Pedestals shall not be stood within 48 hours of casting of foundations. Poles shall not be stood within 7 days of casting of foundation. | Visual | Per Item | IP | SE/Surveyor | This ITP Signed Off Attach: Survey Conformance Report
5.2 | Lantern Requirements | Section 730.13 b) | All trraffic signal lanterns shall be LED type, excluding minor remodels where QH lanterns are permitted. A mix of LED and QH lanterns is not permitted. | Visual | Per Item | IP | SE/Surveyor | This ITP Signed Off
5.3 | Lantern Installation - Mounting | Section 730.13 c) SD TC-1115 | Lanterns shall be mounted vertically using straps securely Fixed to mounting brackets. Upper mounting brackets shall be orientated in accordance with TC-1115. | Visual | Per Item | IP | SE/Site Supervisor | This ITP Signed Off
5.4 | Lantern Installation - Cabling | Section 730.13 c) (vi, vii, viii and ix) SD TC-1119 | External cables and conduits shall be 昀椀xed to pedestals, poles or supports with the desired length as per the relevant standards. Cable connections to lanterns shall be made with continuous lengths of cable; no joins shall be allowed. | Visual | Per Item | IP | SE/Site Supervisor | This ITP Signed Off
5.5 | Lantern Installation - Mounting Height and Alignment | REFERENCE: Section 730.13 (d)&(e) SD TC-1112 SD TC-1116 | Mounting heights for 2A and 2B pedestals are to be as per SD TC-1116. Lanterns on the outreach of a MA or JUMA shall be mounted in accordance with SD TC-1112. Vehicle lanterns shall be aligned to provide optimum visibility for approaching tra昀케c, and aimed at a distance before the stop line for the following Primary - 240m Secondary - 150m Tertiary - 5m | Visual | Per Item | IP | SE/Site Supervisor | This ITP Signed Off
5.6 | Lantern Installation - Target Boards and Visors | REFERENCE: Section 730.131 (f) SD TC-1119 SD TC-1127 | ACCEPTANCE CRITERIA: All target boards shall be metal and fitted in accordance with SD TC-1119. Visors for LED lanterns shall be fittedas per the below and Table 730.132: MA/JUMA - Visor Type 1 - Both Sides Cutaway L/H Primary - Visor Type 1 - Both Sides Cutaway R/H Primary - Visor Type 1 - Both Sides Cutaway Secondary/Tertiary - Visor Type 3 Short Pedestrian/Bicycle - Visor Type 4 | Visual | Per Item | IP | SE/Site Supervisor | This ITP Signed Off
5.7 | Installation of Pedestrian Push Buttons and Audio Tactile Devices | SREFERENCE: Section 730.131 (g), (h) SD TC-1116 | ACCEPTANCE CRITERIA: assemblies shall be mounted clear of any access openings and such that the centre of the button is 1.0 m above FSL, as shown on SD TC-1116. The face of the button shall be at right angles to the direction of the associated walk lines. the tactile arrow indicator shall be orientated to indicate the walk direction. If required, audio tactile units of the type nominated shall be mounted as shown on SD TC-1116. | Visual | Per Item | IP | SE/Site Supervisor | This ITP Signed Off
5.8 | Non-Commissioned Lanterns | REFERENCE: Section 730.131 (l) SD TC 1131 | The faces of all installed but not yet operating lanterns shall be covered, specificsally 'NOT IN USE' signage on vehicle lanterns that have not been switched on. | Visual | Per Item | IP | SE/Site Supervisor | This ITP Signed Off
5.9 | Hardware Inspection | REFERENCE: 730.131 | All installed hardware shall be inspected prior to works proceeding by the Nominated Authority. | Visual | Per Item | HP* | SE & NA | This ITP Signed Off
6 | Post-construction / Post-installation Activities
6.1 | As built survey |  | Survey activities carried out to validate correct construction of signs, components and posts as per IFC Drawings Attach: Survey Conformance Data/Report | Document Review | Per lot | IP | SE | This ITP Signed Off
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed Off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /