## Sheet1
1 | D1.3 | Site Management Plan (QEHS, SSST, KSA) | H | WCL | Ensure Quality, Environment, Health CHAR(AMP) Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times. | — | Prior to commencement | Submission (NTE) | Sign This ITP LN-01, FM-83, FM-69 | ICC STANDARD SPECIFICATIONS | YES | YES | 1 - D1.3 | Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA) | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - Ensure Quality, Environment, Health CHAR(AMP) Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times. | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Submission (NTE) | Records / evidence, WCL form - Sign This ITP LN-01, FM-83, FM-69 | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | 1 - D1.3
2 | D1.18 | TMP | H | WCL | traffic management plan to be submitted and approved by Road Controlling Authority | — | Prior to commencement | Sumission (NTE) | Sign This ITP TMP | Code of practice for temporary traffic management (CoPTTM) | YES | YES | 2 - D1.18 | Inspection / Test Point - TMP | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - traffic management plan to be submitted and approved by Road Controlling Authority | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Sumission (NTE) | Records / evidence, WCL form - Sign This ITP TMP | Standard - Code of practice for temporary traffic management (CoPTTM) | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Point - Site Management Plan (QEHS, SSST, KSA)
3 | D1.4 | Works Access Permit | H | WCL | TMP and Corridor Access Request to be sumbitted on myWorksites | — | Prior to commencement | Document | Sign This ITP WAP | — | YES | YES | 3 - D1.4 | Inspection / Test Point - Works Access Permit | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - TMP and Corridor Access Request to be sumbitted on myWorksites | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Document | Records / evidence, WCL form - Sign This ITP WAP | Standard - — | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | ACTION (W, M, H) - H
4 | D1.14 | Client start-up meeting | H | ICC, WCL | — | — | Prior to commencement | Document | Sign This ITP MoM | ICC STANDARD SPECIFICATIONS | YES | YES | 4 - D1.14 | Inspection / Test Point - Client start-up meeting | ACTION (W, M, H) - H | Activity by - ICC, WCL | Conformance Criteria (What's Required) - — | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Document | Records / evidence, WCL form - Sign This ITP MoM | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Activity by - WCL
5 | D2.4.2 | Bedding material | W | Lab | Material to comply with contract specification | 280 m3 | Prior to commencement | Lab report | Grading Results | ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2 | YES | YES | 5 - D2.4.2 | Inspection / Test Point - Bedding material | ACTION (W, M, H) - W | Activity by - Lab | Conformance Criteria (What's Required) - Material to comply with contract specification | Quantity - 280 m3 | Frequency / When? - Prior to commencement | Inspection / Test Method - Lab report | Records / evidence, WCL form - Grading Results | Standard - ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Conformance Criteria (What's Required) - Ensure Quality, Environment, Health CHAR(AMP) Safety Management Systems Plan Site Specific Safety Plan and Key Step Analysis are approved. Living document to be adjusted and updated as required. A copy of QEHS plan, SSSP and KSA to be on site at all times.
6 | D1.29.3 | Sub Base Aggregate AP65 | W | Lab | Materials to comply with contract specification | 90 m3 | Prior to commencement | Lab report | MDD and Grading Results | ICC STANDARD SPECIFICATIONS | YES | YES | 6 - D1.29.3 | Inspection / Test Point - Sub Base Aggregate AP65 | ACTION (W, M, H) - W | Activity by - Lab | Conformance Criteria (What's Required) - Materials to comply with contract specification | Quantity - 90 m3 | Frequency / When? - Prior to commencement | Inspection / Test Method - Lab report | Records / evidence, WCL form - MDD and Grading Results | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Quantity - —
7 | D1.29.4 | Crushed Basecource Aggregate M/4 AP40 | W | Lab | Materials to comply with contract specification | 22 m3 | Prior to commencement | Lab report | MDD and Grading Results | ICC STANDARD SPECIFICATIONS NZTA M/4 | YES | YES | 7 - D1.29.4 | Inspection / Test Point - Crushed Basecource Aggregate M/4 AP40 | ACTION (W, M, H) - W | Activity by - Lab | Conformance Criteria (What's Required) - Materials to comply with contract specification | Quantity - 22 m3 | Frequency / When? - Prior to commencement | Inspection / Test Method - Lab report | Records / evidence, WCL form - MDD and Grading Results | Standard - ICC STANDARD SPECIFICATIONS NZTA M/4 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Frequency / When? - Prior to commencement
8 | D1.5 | Pre-work site inspection | H | WCL | Video or photos near the construction zone to determine their pre construction condition. (landowners property) | — | Prior to commencement | Inspection Document | Sign This ITP Video Photo | ICC STANDARD SPECIFICATIONS | YES | YES | 8 - D1.5 | Inspection / Test Point - Pre-work site inspection | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - Video or photos near the construction zone to determine their pre construction condition. (landowners property) | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Inspection Document | Records / evidence, WCL form - Sign This ITP Video Photo | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Method - Submission (NTE)
9 | D1.18 | Temporary traffic management | H | WCL | Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer. | — | Prior to commencement | Visual inspection Document | Sign This ITP On-site record | ICC STANDARD SPECIFICATIONS CoPTTM | YES | YES | 9 - D1.18 | Inspection / Test Point - Temporary traffic management | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer. | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Visual inspection Document | Records / evidence, WCL form - Sign This ITP On-site record | Standard - ICC STANDARD SPECIFICATIONS CoPTTM | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Records / evidence, WCL form - Sign This ITP LN-01, FM-83, FM-69
10 | D2.7.1 | Set out | W | ICC, WCL | Mark out of alignment for mains and laterals | — | Prior to commencement | Surface marking | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 10 - D2.7.1 | Inspection / Test Point - Set out | ACTION (W, M, H) - W | Activity by - ICC, WCL | Conformance Criteria (What's Required) - Mark out of alignment for mains and laterals | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Surface marking | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Standard - ICC STANDARD SPECIFICATIONS
11 | D1.8 | Protection and identification of other Services | H | WCL, asset owners | Mark out on site of all services. Services to be potholed for as per Wilsons company policy | — | Prior to commencement | Surface marking Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS Wilson's prior to excavate policy | YES | YES | 11 - D1.8 | Inspection / Test Point - Protection and identification of other Services | ACTION (W, M, H) - H | Activity by - WCL, asset owners | Conformance Criteria (What's Required) - Mark out on site of all services. Services to be potholed for as per Wilsons company policy | Quantity - — | Frequency / When? - Prior to commencement | Inspection / Test Method - Surface marking Visual inspection | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS Wilson's prior to excavate policy | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Print, sign and date: Wilson - YES
12 | D1.11 D9.5 | Notification to residents and businesses | M | WCL | Letter drop / business visits | — | Prior to commencement (min. two working days prior to water shutoff or access restriction) | Document delivered | Sign This ITP Notification letter | ICC STANDARD SPECIFICATIONS | YES | YES | 12 - D1.11 D9.5 | Inspection / Test Point - Notification to residents and businesses | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - Letter drop / business visits | Quantity - — | Frequency / When? - Prior to commencement (min. two working days prior to water shutoff or access restriction) | Inspection / Test Method - Document delivered | Records / evidence, WCL form - Sign This ITP Notification letter | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Print, sign and date: ICC - YES
13 | C1.4 D2.4.1 | Pipe material (main) | M | WCL, ICC | DN450 RC JR Class 4 ICC to inspect pipe deliveries as required | 360 m | 1 / delivery | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS AS/NZS 4058:2007 | YES | YES | 13 - C1.4 D2.4.1 | Inspection / Test Point - Pipe material (main) | ACTION (W, M, H) - M | Activity by - WCL, ICC | Conformance Criteria (What's Required) - DN450 RC JR Class 4 ICC to inspect pipe deliveries as required | Quantity - 360 m | Frequency / When? - 1 / delivery | Inspection / Test Method - Visual inspection | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS AS/NZS 4058:2007 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | 2 - D1.18
14 | D4.3.1 | Pipe material (lateral) | M | WCL, ICC | DN100 uPVC SN6 RRJ | 32 m | 1 / delivery | Visual inspection | Sign This ITP | AS/NZS 1260:2017 | YES | YES | 14 - D4.3.1 | Inspection / Test Point - Pipe material (lateral) | ACTION (W, M, H) - M | Activity by - WCL, ICC | Conformance Criteria (What's Required) - DN100 uPVC SN6 RRJ | Quantity - 32 m | Frequency / When? - 1 / delivery | Inspection / Test Method - Visual inspection | Records / evidence, WCL form - Sign This ITP | Standard - AS/NZS 1260:2017 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Point - TMP
15 | D4.3.1 | Pipe material (sump lead) | M | WCL, ICC | DN150 uPVC SN8 RRJ DN225 uPVC SN8 RRJ | 45 m 35 m | 1 / delivery | Visual inspection | Sign This ITP | AS/NZS 1260:2017 | YES | YES | 15 - D4.3.1 | Inspection / Test Point - Pipe material (sump lead) | ACTION (W, M, H) - M | Activity by - WCL, ICC | Conformance Criteria (What's Required) - DN150 uPVC SN8 RRJ DN225 uPVC SN8 RRJ | Quantity - 45 m 35 m | Frequency / When? - 1 / delivery | Inspection / Test Method - Visual inspection | Records / evidence, WCL form - Sign This ITP | Standard - AS/NZS 1260:2017 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | ACTION (W, M, H) - H
16 | D2.7.2 | Excavation | M | WCL | The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed. | 472 m | continuous | Visual inspection Levelling | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 16 - D2.7.2 | Inspection / Test Point - Excavation | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed. | Quantity - 472 m | Frequency / When? - continuous | Inspection / Test Method - Visual inspection Levelling | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Activity by - WCL
17 | D13.4.3 | Subgrade inspection | M | WCL, ICC | To determine if improvements are required | 472 m | Prior to placement of bedding | Visual inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 17 - D13.4.3 | Inspection / Test Point - Subgrade inspection | ACTION (W, M, H) - M | Activity by - WCL, ICC | Conformance Criteria (What's Required) - To determine if improvements are required | Quantity - 472 m | Frequency / When? - Prior to placement of bedding | Inspection / Test Method - Visual inspection | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Conformance Criteria (What's Required) - traffic management plan to be submitted and approved by Road Controlling Authority
18 | D2.4.2 | Free draining material | M | WCL | pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed | 0 - 360 m | Continous, in accordance with observed groundwater conditions | Secific approval should be given by the Engineer | NTE, NTC | ICC STANDARD SPECIFICATIONS | YES | YES | 18 - D2.4.2 | Inspection / Test Point - Free draining material | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed | Quantity - 0 - 360 m | Frequency / When? - Continous, in accordance with observed groundwater conditions | Inspection / Test Method - Secific approval should be given by the Engineer | Records / evidence, WCL form - NTE, NTC | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Quantity - —
19 | D2.7.3 | Pipe installation (main) | M | WCL | +/- 30mm (horizontal) +/- 5mm (vertical) | 360 m | Continous (pipe laser) 1/20 m (independent optical level) | Using calibrated pipe laser Optical levelling | Sign this ITP leveling record | ICC STANDARD SPECIFICATIONS | YES | YES | 19 - D2.7.3 | Inspection / Test Point - Pipe installation (main) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - +/- 30mm (horizontal) +/- 5mm (vertical) | Quantity - 360 m | Frequency / When? - Continous (pipe laser) 1/20 m (independent optical level) | Inspection / Test Method - Using calibrated pipe laser Optical levelling | Records / evidence, WCL form - Sign this ITP leveling record | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Frequency / When? - Prior to commencement
20 | D4.4 | Pipe installation (lateral) | M | WCL | grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 manhole: gritted manhole finisher Connection at boundary: slip coupler/plumbqwik | 3 (to 600 mh) 7 (to main) 1 (to 1050 mh) | Continous | Measurement Document | Sign this ITP Detailed Drainage Connection Sheet | ICC STANDARD SPECIFICATIONS | YES | YES | 20 - D4.4 | Inspection / Test Point - Pipe installation (lateral) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 manhole: gritted manhole finisher Connection at boundary: slip coupler/plumbqwik | Quantity - 3 (to 600 mh) 7 (to main) 1 (to 1050 mh) | Frequency / When? - Continous | Inspection / Test Method - Measurement Document | Records / evidence, WCL form - Sign this ITP Detailed Drainage Connection Sheet | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Method - Sumission (NTE)
21 | D4.4 | Pipe installation (sump lead) | M | WCL | grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 mh / yard sump: gritted manhole starter / finisher | 3 (to 600 MH) 3 (to main) | continous | Measurement Visual inspection | Sign This ITP | — | YES | YES | 21 - D4.4 | Inspection / Test Point - Pipe installation (sump lead) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 mh / yard sump: gritted manhole starter / finisher | Quantity - 3 (to 600 MH) 3 (to main) | Frequency / When? - continous | Inspection / Test Method - Measurement Visual inspection | Records / evidence, WCL form - Sign This ITP | Standard - — | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Records / evidence, WCL form - Sign This ITP TMP
22 | D2.7.6 | Bedding (main) | M | WCL | lb (depth below): min 150 mm lc (width beside): min 300 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | 360 m | continuous | Measurement Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES | 22 - D2.7.6 | Inspection / Test Point - Bedding (main) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - lb (depth below): min 150 mm lc (width beside): min 300 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | Quantity - 360 m | Frequency / When? - continuous | Inspection / Test Method - Measurement Levelling | Records / evidence, WCL form - Sign this ITP | Standard - AS/NZS 2566 table 4.2. | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Standard - Code of practice for temporary traffic management (CoPTTM)
23 | D2.7.6 | Bedding (lateral) | M | WCL | lb (depth below): min 75 mm lc (width beside): min 100 mm lo (depth above): min 100 mm compacted layers not exceeding ⅓ of the pipe OD | 32 m | continuous | Measurement Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES | 23 - D2.7.6 | Inspection / Test Point - Bedding (lateral) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - lb (depth below): min 75 mm lc (width beside): min 100 mm lo (depth above): min 100 mm compacted layers not exceeding ⅓ of the pipe OD | Quantity - 32 m | Frequency / When? - continuous | Inspection / Test Method - Measurement Levelling | Records / evidence, WCL form - Sign this ITP | Standard - AS/NZS 2566 table 4.2. | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Print, sign and date: Wilson - YES
24 | D2.7.6 | Bedding (sump lead) | M | WCL | lb (depth below): min 100 mm lc (width beside): min 150 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | 80 m | continuous | Measurements Levelling | Sign this ITP | AS/NZS 2566 table 4.2. | YES | YES | 24 - D2.7.6 | Inspection / Test Point - Bedding (sump lead) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - lb (depth below): min 100 mm lc (width beside): min 150 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD | Quantity - 80 m | Frequency / When? - continuous | Inspection / Test Method - Measurements Levelling | Records / evidence, WCL form - Sign this ITP | Standard - AS/NZS 2566 table 4.2. | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Print, sign and date: ICC - YES
25 | D18 Fig. D12 | Manhole (D1050) | M | WCL | 1050mm The sump shall be at least 300 mm from the underside of the lowest invert level. neck depth ≤ 315 mm in-situ concrete packing | 7 | 1 / manhole | Measurement Levelling Document | Sign this ITP Manhole Inspection Sheet | NZS 3109:1997 | YES | YES | 25 - D18 Fig. D12 | Inspection / Test Point - Manhole (D1050) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - 1050mm The sump shall be at least 300 mm from the underside of the lowest invert level. neck depth ≤ 315 mm in-situ concrete packing | Quantity - 7 | Frequency / When? - 1 / manhole | Inspection / Test Method - Measurement Levelling Document | Records / evidence, WCL form - Sign this ITP Manhole Inspection Sheet | Standard - NZS 3109:1997 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | 3 - D1.4
26 | D18 | Manhole (D600) | M | WCL | CIRCULAR SUMP+INTERNAL BASE 600.900.100MM 600 mm cover Class D connection to the main: D225 uPVC | 3 | 1 / manhole | Measurement Levelling Document | Sign this ITP Manhole Inspection Sheet | ICC STANDARD SPECIFICATIONS | YES | YES | 26 - D18 | Inspection / Test Point - Manhole (D600) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - CIRCULAR SUMP+INTERNAL BASE 600.900.100MM 600 mm cover Class D connection to the main: D225 uPVC | Quantity - 3 | Frequency / When? - 1 / manhole | Inspection / Test Method - Measurement Levelling Document | Records / evidence, WCL form - Sign this ITP Manhole Inspection Sheet | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Point - Works Access Permit
27 | D18 | Yard sumps | M | WCL | Flat top concrete sump box 450x450x1200 Cast Iron sump grate + frame 450x450 D150 sump lead | 5 (1 existing is to be reconnected) | 1 / yard sump | Measurement Levelling Document | Sign this ITP Manhole Inspection Sheet | ICC STANDARD SPECIFICATIONS | YES | YES | 27 - D18 | Inspection / Test Point - Yard sumps | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - Flat top concrete sump box 450x450x1200 Cast Iron sump grate + frame 450x450 D150 sump lead | Quantity - 5 (1 existing is to be reconnected) | Frequency / When? - 1 / yard sump | Inspection / Test Method - Measurement Levelling Document | Records / evidence, WCL form - Sign this ITP Manhole Inspection Sheet | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | ACTION (W, M, H) - H
28 | D15 | Service covers | W | WCL, ICC | HN-HO-72 d600 mm, 450x450 mm Cover levels to be adjusted to existing ground levels | 7 grated 600 3 solid 600 5 grated 450x450 | before surface reinstatement, landscaping | Visual inspection Measurement | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 28 - D15 | Inspection / Test Point - Service covers | ACTION (W, M, H) - W | Activity by - WCL, ICC | Conformance Criteria (What's Required) - HN-HO-72 d600 mm, 450x450 mm Cover levels to be adjusted to existing ground levels | Quantity - 7 grated 600 3 solid 600 5 grated 450x450 | Frequency / When? - before surface reinstatement, landscaping | Inspection / Test Method - Visual inspection Measurement | Records / evidence, WCL form - Sign this ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Activity by - WCL
29 | D2.9.3 | CCTV Inspection and Cleaning | H | WCL | to confirm that the lines are free from debris and have no defects | 360 m (main) | prior to the final surface reinstatement | CCTV inspection | Sign this ITP CCTV survey | New Zealand Pipe Inspection Manual AS/NZS 2566:2 | YES | YES | 29 - D2.9.3 | Inspection / Test Point - CCTV Inspection and Cleaning | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - to confirm that the lines are free from debris and have no defects | Quantity - 360 m (main) | Frequency / When? - prior to the final surface reinstatement | Inspection / Test Method - CCTV inspection | Records / evidence, WCL form - Sign this ITP CCTV survey | Standard - New Zealand Pipe Inspection Manual AS/NZS 2566:2 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Conformance Criteria (What's Required) - TMP and Corridor Access Request to be sumbitted on myWorksites
30 | — | Removal of existing pipelines and manholes | W | WCL | DN150 EW Excavation may include the removal of existing redundant mains located within the trench extents. | max 360 m + 10 manholes | during main installation (parts of Southern Korimako alignment) | Visual inspection | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 30 - — | Inspection / Test Point - Removal of existing pipelines and manholes | ACTION (W, M, H) - W | Activity by - WCL | Conformance Criteria (What's Required) - DN150 EW Excavation may include the removal of existing redundant mains located within the trench extents. | Quantity - max 360 m + 10 manholes | Frequency / When? - during main installation (parts of Southern Korimako alignment) | Inspection / Test Method - Visual inspection | Records / evidence, WCL form - Sign this ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Quantity - —
31 | D2.10 | Abandonement of existing pipelines by filling | — | WCL | DN150 EW Filling material and methodology for execution shall be approved by the Engineer. Ensure there are no active connections to the main | 15 m3 | following new main installation (Northern Korimako alignment) | Visual inspection Document | Sign this ITP Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES | 31 - D2.10 | Inspection / Test Point - Abandonement of existing pipelines by filling | ACTION (W, M, H) - — | Activity by - WCL | Conformance Criteria (What's Required) - DN150 EW Filling material and methodology for execution shall be approved by the Engineer. Ensure there are no active connections to the main | Quantity - 15 m3 | Frequency / When? - following new main installation (Northern Korimako alignment) | Inspection / Test Method - Visual inspection Document | Records / evidence, WCL form - Sign this ITP Delivery docket | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Frequency / When? - Prior to commencement
32 | D2.7.7 | Backfilling and compaction (existing, excavated material in berm) | M | WCL | All backfill material layers shall be placed and compacted in layers with appropriately sized mechanical compaction equipment to achieve uniform compaction for the full depth. This shall be in compacted layers not exceeding 200mm depth | 240 m | continuous | NDM testing: not required Clegg testing: not required | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 32 - D2.7.7 | Inspection / Test Point - Backfilling and compaction (existing, excavated material in berm) | ACTION (W, M, H) - M | Activity by - WCL | Conformance Criteria (What's Required) - All backfill material layers shall be placed and compacted in layers with appropriately sized mechanical compaction equipment to achieve uniform compaction for the full depth. This shall be in compacted layers not exceeding 200mm depth | Quantity - 240 m | Frequency / When? - continuous | Inspection / Test Method - NDM testing: not required Clegg testing: not required | Records / evidence, WCL form - Sign this ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Method - Document
33 | D13 | Landscaping | W | WCL | The final surface in the berm area is to be re-graded, with new sump manholes and yard sumps established as the low points. | 240 m | following new main and lateral installation | Visual inspection Levelling | Sign this ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 33 - D13 | Inspection / Test Point - Landscaping | ACTION (W, M, H) - W | Activity by - WCL | Conformance Criteria (What's Required) - The final surface in the berm area is to be re-graded, with new sump manholes and yard sumps established as the low points. | Quantity - 240 m | Frequency / When? - following new main and lateral installation | Inspection / Test Method - Visual inspection Levelling | Records / evidence, WCL form - Sign this ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Records / evidence, WCL form - Sign This ITP WAP
34 | D13.7 | Grass seeding | W | WCL | approved seed mixture, 35 g/m2 | 240 m | following landscaping between the months of September - April | Visual inspection | Sign this ITP Blending docket | ICC STANDARD SPECIFICATIONS | YES | YES | 34 - D13.7 | Inspection / Test Point - Grass seeding | ACTION (W, M, H) - W | Activity by - WCL | Conformance Criteria (What's Required) - approved seed mixture, 35 g/m2 | Quantity - 240 m | Frequency / When? - following landscaping between the months of September - April | Inspection / Test Method - Visual inspection | Records / evidence, WCL form - Sign this ITP Blending docket | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Standard - —
35 | D2.7.7 | Subbase (AP65) compaction | H | WCL | Carriageway: 0.3 - 1.5 m deep: min 35 CIV > 1.5 m deep : min 25 CIV | Culvert + ch 240 - 329 ch 87, 139, 220, 224, 253, 295 | During installation, every 200 mm layers at 5 m intervals for all trenches in carriageway above main and connections | Clegg test | Sign This ITP Clegg Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES | 35 - D2.7.7 | Inspection / Test Point - Subbase (AP65) compaction | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - Carriageway: 0.3 - 1.5 m deep: min 35 CIV > 1.5 m deep : min 25 CIV | Quantity - Culvert + ch 240 - 329 ch 87, 139, 220, 224, 253, 295 | Frequency / When? - During installation, every 200 mm layers at 5 m intervals for all trenches in carriageway above main and connections | Inspection / Test Method - Clegg test | Records / evidence, WCL form - Sign This ITP Clegg Test Result Sheet | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Print, sign and date: Wilson - YES
36 | D2.11.5 | Subbase (AP65) compaction | H | WCL / Lab ICC | 95% compaction rate It is not required to complete NDM testing on connections. | Culvert + ch 240 - 329 = 95 m | At pipe laying commencement and reconfirmed at 120m intervals for open trench every 200 mm layers | NDM test (direct transmission) | Sign This ITP NDM Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES | 36 - D2.11.5 | Inspection / Test Point - Subbase (AP65) compaction | ACTION (W, M, H) - H | Activity by - WCL / Lab ICC | Conformance Criteria (What's Required) - 95% compaction rate It is not required to complete NDM testing on connections. | Quantity - Culvert + ch 240 - 329 = 95 m | Frequency / When? - At pipe laying commencement and reconfirmed at 120m intervals for open trench every 200 mm layers | Inspection / Test Method - NDM test (direct transmission) | Records / evidence, WCL form - Sign This ITP NDM Test Result Sheet | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Print, sign and date: ICC - YES
37 | D2.7 | Basecourse (AP40) compaction | H | WCL / Lab ICC | 98% compaction rate It is not required to complete NDM testing on connections | Culvert + ch 240 - 329 = 95 m | 1 / 20 m of trench including one test at the start and end of the trench | NDM test | Sign This ITP NDM Test Result Sheet | ICC STANDARD SPECIFICATIONS | YES | YES | 37 - D2.7 | Inspection / Test Point - Basecourse (AP40) compaction | ACTION (W, M, H) - H | Activity by - WCL / Lab ICC | Conformance Criteria (What's Required) - 98% compaction rate It is not required to complete NDM testing on connections | Quantity - Culvert + ch 240 - 329 = 95 m | Frequency / When? - 1 / 20 m of trench including one test at the start and end of the trench | Inspection / Test Method - NDM test | Records / evidence, WCL form - Sign This ITP NDM Test Result Sheet | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | 4 - D1.14
38 | D2.8.3 | Trench reinstatement - marking out saw cutting | H | ICC | Engineers rep to mark out saw cutting required (overcuts) | 6 m: Marama 79 m: Kori | Prior to sealing | Visual inspection, measurements (1 m rule) | Sign This ITP | ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors | YES | YES | 38 - D2.8.3 | Inspection / Test Point - Trench reinstatement - marking out saw cutting | ACTION (W, M, H) - H | Activity by - ICC | Conformance Criteria (What's Required) - Engineers rep to mark out saw cutting required (overcuts) | Quantity - 6 m: Marama 79 m: Kori | Frequency / When? - Prior to sealing | Inspection / Test Method - Visual inspection, measurements (1 m rule) | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Point - Client start-up meeting
39 | D2.7.7.2 | Basecourse (AP40) geometry | H | WCL, ICC | -5 mm +15 mm h = 45-65 mm (carriageways) h = 25-45 mm (footpath) | Culvert + ch 240 - 319 = 85 m +5 cross | Prior to sealing | Visual inspection String line / straight edge inspection | Sign This ITP Pre seal inspection record (FM-114) | ICC STANDARD SPECIFICATIONS NZTA B/2 | YES | YES | 39 - D2.7.7.2 | Inspection / Test Point - Basecourse (AP40) geometry | ACTION (W, M, H) - H | Activity by - WCL, ICC | Conformance Criteria (What's Required) - -5 mm +15 mm h = 45-65 mm (carriageways) h = 25-45 mm (footpath) | Quantity - Culvert + ch 240 - 319 = 85 m +5 cross | Frequency / When? - Prior to sealing | Inspection / Test Method - Visual inspection String line / straight edge inspection | Records / evidence, WCL form - Sign This ITP Pre seal inspection record (FM-114) | Standard - ICC STANDARD SPECIFICATIONS NZTA B/2 | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | ACTION (W, M, H) - H
40 | D11.4.3 | Membrane Seal | H | WCL, ICC | Residual bitumen application rate ≥ 1.5 l/m2 | Culvert + ch 240 - 319 = 85 m | Prior to asphalting | Visual inspection | Sign This ITP, Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES | 40 - D11.4.3 | Inspection / Test Point - Membrane Seal | ACTION (W, M, H) - H | Activity by - WCL, ICC | Conformance Criteria (What's Required) - Residual bitumen application rate ≥ 1.5 l/m2 | Quantity - Culvert + ch 240 - 319 = 85 m | Frequency / When? - Prior to asphalting | Inspection / Test Method - Visual inspection | Records / evidence, WCL form - Sign This ITP, Delivery docket | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Activity by - ICC, WCL
41 | D12.5 | Asphalt paving geometry | H | WCL, ICC | 5 mm from a 3 m straight edge laid longitudinally 5 mm from a 1 m straight edge laid transversely | 85 m | 1 / finished surface | Post seal surface inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | YES | YES | 41 - D12.5 | Inspection / Test Point - Asphalt paving geometry | ACTION (W, M, H) - H | Activity by - WCL, ICC | Conformance Criteria (What's Required) - 5 mm from a 3 m straight edge laid longitudinally 5 mm from a 1 m straight edge laid transversely | Quantity - 85 m | Frequency / When? - 1 / finished surface | Inspection / Test Method - Post seal surface inspection | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Conformance Criteria (What's Required) - —
42 | D2.8.3 D12.3.1 | Asphalt paving material | W | WCL, ICC | DG10 (carriageways) | 13 t | — | Document | Sign This ITP Delivery docket | ICC STANDARD SPECIFICATIONS | YES | YES | 42 - D2.8.3 D12.3.1 | Inspection / Test Point - Asphalt paving material | ACTION (W, M, H) - W | Activity by - WCL, ICC | Conformance Criteria (What's Required) - DG10 (carriageways) | Quantity - 13 t | Frequency / When? - — | Inspection / Test Method - Document | Records / evidence, WCL form - Sign This ITP Delivery docket | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Quantity - —
43 | — | Road markings | W | WCL, ICC | Reinstatement of the existing markings | — | 1 / finished surface | Post seal surface inspection | Sign This ITP | ICC STANDARD SPECIFICATIONS | N/A | N/A | 43 - — | Inspection / Test Point - Road markings | ACTION (W, M, H) - W | Activity by - WCL, ICC | Conformance Criteria (What's Required) - Reinstatement of the existing markings | Quantity - — | Frequency / When? - 1 / finished surface | Inspection / Test Method - Post seal surface inspection | Records / evidence, WCL form - Sign This ITP | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - N/A | Print, sign and date: ICC - N/A | Frequency / When? - Prior to commencement
44 | D17 | As-built information | H | WCL | Encountered Services Record Sheet Detailed Water Connection Sheet As-built drawings as per D17 | — | Following/during completion of works | Document | Sign This ITP DWCS, ESRS, As-built | ICC STANDARD SPECIFICATIONS | YES | YES | 44 - D17 | Inspection / Test Point - As-built information | ACTION (W, M, H) - H | Activity by - WCL | Conformance Criteria (What's Required) - Encountered Services Record Sheet Detailed Water Connection Sheet As-built drawings as per D17 | Quantity - — | Frequency / When? - Following/during completion of works | Inspection / Test Method - Document | Records / evidence, WCL form - Sign This ITP DWCS, ESRS, As-built | Standard - ICC STANDARD SPECIFICATIONS | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Inspection / Test Method - Document
45 | — | Site walkover | H | WCL, ICC | Snag list to be compiled, and completed | — | At Completion | Review | Sign This ITP SNAG List | — | YES | YES | 45 - — | Inspection / Test Point - Site walkover | ACTION (W, M, H) - H | Activity by - WCL, ICC | Conformance Criteria (What's Required) - Snag list to be compiled, and completed | Quantity - — | Frequency / When? - At Completion | Inspection / Test Method - Review | Records / evidence, WCL form - Sign This ITP SNAG List | Standard - — | Print, sign and date: Wilson - YES | Print, sign and date: ICC - YES | Records / evidence, WCL form - Sign This ITP MoM
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
5 - D2.4.2
Inspection / Test Point - Bedding material
ACTION (W, M, H) - W
Activity by - Lab
Conformance Criteria (What's Required) - Material to comply with contract specification
Quantity - 280 m3
Frequency / When? - Prior to commencement
Inspection / Test Method - Lab report
Records / evidence, WCL form - Grading Results
Standard - ICC STANDARD SPECIFICATIONS G3 of AS/NZS 2566.2
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
6 - D1.29.3
Inspection / Test Point - Sub Base Aggregate AP65
ACTION (W, M, H) - W
Activity by - Lab
Conformance Criteria (What's Required) - Materials to comply with contract specification
Quantity - 90 m3
Frequency / When? - Prior to commencement
Inspection / Test Method - Lab report
Records / evidence, WCL form - MDD and Grading Results
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
7 - D1.29.4
Inspection / Test Point - Crushed Basecource Aggregate M/4 AP40
ACTION (W, M, H) - W
Activity by - Lab
Conformance Criteria (What's Required) - Materials to comply with contract specification
Quantity - 22 m3
Frequency / When? - Prior to commencement
Inspection / Test Method - Lab report
Records / evidence, WCL form - MDD and Grading Results
Standard - ICC STANDARD SPECIFICATIONS NZTA M/4
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
8 - D1.5
Inspection / Test Point - Pre-work site inspection
ACTION (W, M, H) - H
Activity by - WCL
Conformance Criteria (What's Required) - Video or photos near the construction zone to determine their pre construction condition. (landowners property)
Quantity - —
Frequency / When? - Prior to commencement
Inspection / Test Method - Inspection Document
Records / evidence, WCL form - Sign This ITP Video Photo
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
9 - D1.18
Inspection / Test Point - Temporary traffic management
ACTION (W, M, H) - H
Activity by - WCL
Conformance Criteria (What's Required) - Signs set up as per TMP, with a copy on site with STMS. TMP monitored for practicality. If changes are required these are to be agreed upon with the engineer.
Quantity - —
Frequency / When? - Prior to commencement
Inspection / Test Method - Visual inspection Document
Records / evidence, WCL form - Sign This ITP On-site record
Standard - ICC STANDARD SPECIFICATIONS CoPTTM
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
10 - D2.7.1
Inspection / Test Point - Set out
ACTION (W, M, H) - W
Activity by - ICC, WCL
Conformance Criteria (What's Required) - Mark out of alignment for mains and laterals
Quantity - —
Frequency / When? - Prior to commencement
Inspection / Test Method - Surface marking
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
11 - D1.8
Inspection / Test Point - Protection and identification of other Services
ACTION (W, M, H) - H
Activity by - WCL, asset owners
Conformance Criteria (What's Required) - Mark out on site of all services. Services to be potholed for as per Wilsons company policy
Quantity - —
Frequency / When? - Prior to commencement
Inspection / Test Method - Surface marking Visual inspection
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS Wilson's prior to excavate policy
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
12 - D1.11 D9.5
Inspection / Test Point - Notification to residents and businesses
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - Letter drop / business visits
Quantity - —
Frequency / When? - Prior to commencement (min. two working days prior to water shutoff or access restriction)
Inspection / Test Method - Document delivered
Records / evidence, WCL form - Sign This ITP Notification letter
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
13 - C1.4 D2.4.1
Inspection / Test Point - Pipe material (main)
ACTION (W, M, H) - M
Activity by - WCL, ICC
Conformance Criteria (What's Required) - DN450 RC JR Class 4 ICC to inspect pipe deliveries as required
Quantity - 360 m
Frequency / When? - 1 / delivery
Inspection / Test Method - Visual inspection
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS AS/NZS 4058:2007
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
14 - D4.3.1
Inspection / Test Point - Pipe material (lateral)
ACTION (W, M, H) - M
Activity by - WCL, ICC
Conformance Criteria (What's Required) - DN100 uPVC SN6 RRJ
Quantity - 32 m
Frequency / When? - 1 / delivery
Inspection / Test Method - Visual inspection
Records / evidence, WCL form - Sign This ITP
Standard - AS/NZS 1260:2017
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
15 - D4.3.1
Inspection / Test Point - Pipe material (sump lead)
ACTION (W, M, H) - M
Activity by - WCL, ICC
Conformance Criteria (What's Required) - DN150 uPVC SN8 RRJ DN225 uPVC SN8 RRJ
Quantity - 45 m 35 m
Frequency / When? - 1 / delivery
Inspection / Test Method - Visual inspection
Records / evidence, WCL form - Sign This ITP
Standard - AS/NZS 1260:2017
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
16 - D2.7.2
Inspection / Test Point - Excavation
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - The finished excavation surface shall be a smooth consistent surface at the appropriate grade. No tolerance on the excavation base level that reduces the depth of the bedding will be allowed.
Quantity - 472 m
Frequency / When? - continuous
Inspection / Test Method - Visual inspection Levelling
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
17 - D13.4.3
Inspection / Test Point - Subgrade inspection
ACTION (W, M, H) - M
Activity by - WCL, ICC
Conformance Criteria (What's Required) - To determine if improvements are required
Quantity - 472 m
Frequency / When? - Prior to placement of bedding
Inspection / Test Method - Visual inspection
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
18 - D2.4.2
Inspection / Test Point - Free draining material
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - pea gravel wrapped in a suitable geotextile up to 100 mm over the trench bed
Quantity - 0 - 360 m
Frequency / When? - Continous, in accordance with observed groundwater conditions
Inspection / Test Method - Secific approval should be given by the Engineer
Records / evidence, WCL form - NTE, NTC
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
19 - D2.7.3
Inspection / Test Point - Pipe installation (main)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - +/- 30mm (horizontal) +/- 5mm (vertical)
Quantity - 360 m
Frequency / When? - Continous (pipe laser) 1/20 m (independent optical level)
Inspection / Test Method - Using calibrated pipe laser Optical levelling
Records / evidence, WCL form - Sign this ITP leveling record
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
20 - D4.4
Inspection / Test Point - Pipe installation (lateral)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 manhole: gritted manhole finisher Connection at boundary: slip coupler/plumbqwik
Quantity - 3 (to 600 mh) 7 (to main) 1 (to 1050 mh)
Frequency / When? - Continous
Inspection / Test Method - Measurement Document
Records / evidence, WCL form - Sign this ITP Detailed Drainage Connection Sheet
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
21 - D4.4
Inspection / Test Point - Pipe installation (sump lead)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - grade: min 1.00 % Connection to the main: 90° saddle Connection to D600 mh / yard sump: gritted manhole starter / finisher
Quantity - 3 (to 600 MH) 3 (to main)
Frequency / When? - continous
Inspection / Test Method - Measurement Visual inspection
Records / evidence, WCL form - Sign This ITP
Standard - —
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
22 - D2.7.6
Inspection / Test Point - Bedding (main)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - lb (depth below): min 150 mm lc (width beside): min 300 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD
Quantity - 360 m
Frequency / When? - continuous
Inspection / Test Method - Measurement Levelling
Records / evidence, WCL form - Sign this ITP
Standard - AS/NZS 2566 table 4.2.
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
23 - D2.7.6
Inspection / Test Point - Bedding (lateral)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - lb (depth below): min 75 mm lc (width beside): min 100 mm lo (depth above): min 100 mm compacted layers not exceeding ⅓ of the pipe OD
Quantity - 32 m
Frequency / When? - continuous
Inspection / Test Method - Measurement Levelling
Records / evidence, WCL form - Sign this ITP
Standard - AS/NZS 2566 table 4.2.
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
24 - D2.7.6
Inspection / Test Point - Bedding (sump lead)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - lb (depth below): min 100 mm lc (width beside): min 150 mm lo (depth above): min 150 mm compacted layers not exceeding ⅓ of the pipe OD
Quantity - 80 m
Frequency / When? - continuous
Inspection / Test Method - Measurements Levelling
Records / evidence, WCL form - Sign this ITP
Standard - AS/NZS 2566 table 4.2.
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
25 - D18 Fig. D12
Inspection / Test Point - Manhole (D1050)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - 1050mm The sump shall be at least 300 mm from the underside of the lowest invert level. neck depth ≤ 315 mm in-situ concrete packing
Quantity - 7
Frequency / When? - 1 / manhole
Inspection / Test Method - Measurement Levelling Document
Records / evidence, WCL form - Sign this ITP Manhole Inspection Sheet
Standard - NZS 3109:1997
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
26 - D18
Inspection / Test Point - Manhole (D600)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - CIRCULAR SUMP+INTERNAL BASE 600.900.100MM 600 mm cover Class D connection to the main: D225 uPVC
Quantity - 3
Frequency / When? - 1 / manhole
Inspection / Test Method - Measurement Levelling Document
Records / evidence, WCL form - Sign this ITP Manhole Inspection Sheet
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
27 - D18
Inspection / Test Point - Yard sumps
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - Flat top concrete sump box 450x450x1200 Cast Iron sump grate + frame 450x450 D150 sump lead
Quantity - 5 (1 existing is to be reconnected)
Frequency / When? - 1 / yard sump
Inspection / Test Method - Measurement Levelling Document
Records / evidence, WCL form - Sign this ITP Manhole Inspection Sheet
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
28 - D15
Inspection / Test Point - Service covers
ACTION (W, M, H) - W
Activity by - WCL, ICC
Conformance Criteria (What's Required) - HN-HO-72 d600 mm, 450x450 mm Cover levels to be adjusted to existing ground levels
Quantity - 7 grated 600 3 solid 600 5 grated 450x450
Frequency / When? - before surface reinstatement, landscaping
Inspection / Test Method - Visual inspection Measurement
Records / evidence, WCL form - Sign this ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
29 - D2.9.3
Inspection / Test Point - CCTV Inspection and Cleaning
ACTION (W, M, H) - H
Activity by - WCL
Conformance Criteria (What's Required) - to confirm that the lines are free from debris and have no defects
Quantity - 360 m (main)
Frequency / When? - prior to the final surface reinstatement
Inspection / Test Method - CCTV inspection
Records / evidence, WCL form - Sign this ITP CCTV survey
Standard - New Zealand Pipe Inspection Manual AS/NZS 2566:2
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
30 - —
Inspection / Test Point - Removal of existing pipelines and manholes
ACTION (W, M, H) - W
Activity by - WCL
Conformance Criteria (What's Required) - DN150 EW Excavation may include the removal of existing redundant mains located within the trench extents.
Quantity - max 360 m + 10 manholes
Frequency / When? - during main installation (parts of Southern Korimako alignment)
Inspection / Test Method - Visual inspection
Records / evidence, WCL form - Sign this ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
31 - D2.10
Inspection / Test Point - Abandonement of existing pipelines by filling
ACTION (W, M, H) - —
Activity by - WCL
Conformance Criteria (What's Required) - DN150 EW Filling material and methodology for execution shall be approved by the Engineer. Ensure there are no active connections to the main
Quantity - 15 m3
Frequency / When? - following new main installation (Northern Korimako alignment)
Inspection / Test Method - Visual inspection Document
Records / evidence, WCL form - Sign this ITP Delivery docket
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
32 - D2.7.7
Inspection / Test Point - Backfilling and compaction (existing, excavated material in berm)
ACTION (W, M, H) - M
Activity by - WCL
Conformance Criteria (What's Required) - All backfill material layers shall be placed and compacted in layers with appropriately sized mechanical compaction equipment to achieve uniform compaction for the full depth. This shall be in compacted layers not exceeding 200mm depth
Quantity - 240 m
Frequency / When? - continuous
Inspection / Test Method - NDM testing: not required Clegg testing: not required
Records / evidence, WCL form - Sign this ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
33 - D13
Inspection / Test Point - Landscaping
ACTION (W, M, H) - W
Activity by - WCL
Conformance Criteria (What's Required) - The final surface in the berm area is to be re-graded, with new sump manholes and yard sumps established as the low points.
Quantity - 240 m
Frequency / When? - following new main and lateral installation
Inspection / Test Method - Visual inspection Levelling
Records / evidence, WCL form - Sign this ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
34 - D13.7
Inspection / Test Point - Grass seeding
ACTION (W, M, H) - W
Activity by - WCL
Conformance Criteria (What's Required) - approved seed mixture, 35 g/m2
Quantity - 240 m
Frequency / When? - following landscaping between the months of September - April
Inspection / Test Method - Visual inspection
Records / evidence, WCL form - Sign this ITP Blending docket
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
35 - D2.7.7
Inspection / Test Point - Subbase (AP65) compaction
ACTION (W, M, H) - H
Activity by - WCL
Conformance Criteria (What's Required) - Carriageway: 0.3 - 1.5 m deep: min 35 CIV > 1.5 m deep : min 25 CIV
Quantity - Culvert + ch 240 - 329 ch 87, 139, 220, 224, 253, 295
Frequency / When? - During installation, every 200 mm layers at 5 m intervals for all trenches in carriageway above main and connections
Inspection / Test Method - Clegg test
Records / evidence, WCL form - Sign This ITP Clegg Test Result Sheet
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
36 - D2.11.5
Inspection / Test Point - Subbase (AP65) compaction
ACTION (W, M, H) - H
Activity by - WCL / Lab ICC
Conformance Criteria (What's Required) - 95% compaction rate It is not required to complete NDM testing on connections.
Quantity - Culvert + ch 240 - 329 = 95 m
Frequency / When? - At pipe laying commencement and reconfirmed at 120m intervals for open trench every 200 mm layers
Inspection / Test Method - NDM test (direct transmission)
Records / evidence, WCL form - Sign This ITP NDM Test Result Sheet
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
37 - D2.7
Inspection / Test Point - Basecourse (AP40) compaction
ACTION (W, M, H) - H
Activity by - WCL / Lab ICC
Conformance Criteria (What's Required) - 98% compaction rate It is not required to complete NDM testing on connections
Quantity - Culvert + ch 240 - 329 = 95 m
Frequency / When? - 1 / 20 m of trench including one test at the start and end of the trench
Inspection / Test Method - NDM test
Records / evidence, WCL form - Sign This ITP NDM Test Result Sheet
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
38 - D2.8.3
Inspection / Test Point - Trench reinstatement - marking out saw cutting
ACTION (W, M, H) - H
Activity by - ICC
Conformance Criteria (What's Required) - Engineers rep to mark out saw cutting required (overcuts)
Quantity - 6 m: Marama 79 m: Kori
Frequency / When? - Prior to sealing
Inspection / Test Method - Visual inspection, measurements (1 m rule)
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS National Code of Practise for Utility Operators' Access to Transport Corridors
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
39 - D2.7.7.2
Inspection / Test Point - Basecourse (AP40) geometry
ACTION (W, M, H) - H
Activity by - WCL, ICC
Conformance Criteria (What's Required) - -5 mm +15 mm h = 45-65 mm (carriageways) h = 25-45 mm (footpath)
Quantity - Culvert + ch 240 - 319 = 85 m +5 cross
Frequency / When? - Prior to sealing
Inspection / Test Method - Visual inspection String line / straight edge inspection
Records / evidence, WCL form - Sign This ITP Pre seal inspection record (FM-114)
Standard - ICC STANDARD SPECIFICATIONS NZTA B/2
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
40 - D11.4.3
Inspection / Test Point - Membrane Seal
ACTION (W, M, H) - H
Activity by - WCL, ICC
Conformance Criteria (What's Required) - Residual bitumen application rate ≥ 1.5 l/m2
Quantity - Culvert + ch 240 - 319 = 85 m
Frequency / When? - Prior to asphalting
Inspection / Test Method - Visual inspection
Records / evidence, WCL form - Sign This ITP, Delivery docket
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
41 - D12.5
Inspection / Test Point - Asphalt paving geometry
ACTION (W, M, H) - H
Activity by - WCL, ICC
Conformance Criteria (What's Required) - 5 mm from a 3 m straight edge laid longitudinally 5 mm from a 1 m straight edge laid transversely
Quantity - 85 m
Frequency / When? - 1 / finished surface
Inspection / Test Method - Post seal surface inspection
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
42 - D2.8.3 D12.3.1
Inspection / Test Point - Asphalt paving material
ACTION (W, M, H) - W
Activity by - WCL, ICC
Conformance Criteria (What's Required) - DG10 (carriageways)
Quantity - 13 t
Frequency / When? - —
Inspection / Test Method - Document
Records / evidence, WCL form - Sign This ITP Delivery docket
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
43 - —
Inspection / Test Point - Road markings
ACTION (W, M, H) - W
Activity by - WCL, ICC
Conformance Criteria (What's Required) - Reinstatement of the existing markings
Quantity - —
Frequency / When? - 1 / finished surface
Inspection / Test Method - Post seal surface inspection
Records / evidence, WCL form - Sign This ITP
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - N/A
Print, sign and date: ICC - N/A
44 - D17
Inspection / Test Point - As-built information
ACTION (W, M, H) - H
Activity by - WCL
Conformance Criteria (What's Required) - Encountered Services Record Sheet Detailed Water Connection Sheet As-built drawings as per D17
Quantity - —
Frequency / When? - Following/during completion of works
Inspection / Test Method - Document
Records / evidence, WCL form - Sign This ITP DWCS, ESRS, As-built
Standard - ICC STANDARD SPECIFICATIONS
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES
45 - —
Inspection / Test Point - Site walkover
ACTION (W, M, H) - H
Activity by - WCL, ICC
Conformance Criteria (What's Required) - Snag list to be compiled, and completed
Quantity - —
Frequency / When? - At Completion
Inspection / Test Method - Review
Records / evidence, WCL form - Sign This ITP SNAG List
Standard - —
Print, sign and date: Wilson - YES
Print, sign and date: ICC - YES