## Master List Templates
Id | Type | Name | Values | Prompting Name
54f46eed-b187-41ed-8185-97eab2d362a5 | checklist | 001 - 2.1 - Submission of Mix design Details | itp | Mix Design Details -
86d2ef28-cf5c-4811-ba89-0a31a7a44ba8 | section | Material & Production of Ashpalt
b95e6d82-4133-471a-8e7d-b692808a8950 | checkpoint | 2.1 Submission of nominated mix design details
fbb69301-ca4d-5f52-b3a8-c67a6b4b59c9 | note | 2.1 of 1680-CHK-R116-001
2053d61e-cd35-5302-bd39-b97f9d9733bc | note | FREQUENCY: Each mix and 7 days prior to placement
b3de8e71-1f98-5c40-a097-b00bcb5ab7ee | note | ACCEPTANCE CRITERIA:
50481df0-0f62-53f1-b1f3-d31223501f44 | note | -Documents as detailed in Clause 2.3.3
80134f2e-259c-5986-a0f7-defd2d3f09ce | note | REFERENCE DOCUMENTS:
6a041ccb-2a76-5afa-84e2-a68406007474 | note | R116, Cl 2.3.5
a991ff44-4fdb-5580-b73e-b0f88d82ecfe | note | *HP
13ea4576-2cb1-5889-b94b-8cdfd1eae9e4 | note | RESPONSIBILITY: Contractor
51320d10-5ae4-4893-a847-e2e3e4a2946a | signoff | HOLDPOINT
0a2745d3-6e5d-46d3-b463-97f51d842800 | checklist | 1680-ITP-R116-001 - Heavy Duty Dense Graded Asphalt | itp | 1680-ITP-R116-001 - Heavy Duty Dense Graded Asphalt
822f7072-9b84-44d4-ae96-33b3082cc57b | section | Material & Production of Ashpalt
ed58d427-c27f-4155-ab7b-33a25d53745d | checkpoint | 2.3 - Production tolerance
b87ddf71-c53b-5bb7-b994-8f26ffae9e67 | note | FREQUENCY: Per Lot
3aff5e24-372e-5364-9afb-096d7278da58 | note | ACCEPTANCE CRITERIA: The actual combined particle size distribution & actual binder content may vary from their nominated values within the limits shown in Table R116.8
cf854048-5b34-53b6-a7f3-86e583978837 | note | TABLE 1
712685e2-07b3-5790-8264-9e0516bf492b | note | tolerance ¦¦ Value
ffbafb7e-0430-51b6-933b-88e9922d509c | note | 1 ¦¦ 8.7 as per detail
f3a4093e-9c84-5b4d-ba52-286a5045b7d0 | note | 2 ¦¦ > 2
8b580401-9aca-5d86-93c3-c6b62610f2e2 | note | 3 ¦¦ ABC
cc366e36-b39e-5bd9-ada8-cf45e3ddf0e7 | note | 4 ¦¦ >10220
2b7b1527-ea49-56d8-9166-84dbba9d3de7 | note | 5 ¦¦ a
7046c80e-5982-5a2a-90d0-e919502ace31 | note | 6 ¦¦ 8
41a19693-d7cd-5a0a-9154-5da900934b98 | note | 7 ¦¦ and below
e147a021-64a2-578e-9523-d64ed7469e32 | note | REFERENCE DOCUMENTS: R116, C6 2.4.2
8b66a001-f14c-503c-a71a-2f163e9776c4 | note | INSPECTION/TEST METHOD: Hold point
add2c30a-278f-59f5-93cf-bc9c89250e77 | note | CONFORMANCE RECORD: ITC
bb760e9f-c791-5f2b-a88c-0ab8075713a7 | note | HP*
cdbbcbf9-7cac-4a0e-9842-ab3a2d0a8c7c | signoff | Accepted
5a9ad40d-863e-4062-90ef-0586b090f67e | checkpoint | 2.4 - Storage and handling (Production)
3338b132-43d6-515d-b9af-335ffecf537c | note | FREQUENCY: Per Lot
6615cf8a-f3a5-5354-a344-e201160610a0 | note | ACCEPTANCE CRITERIA: Binder: Heating and storage must comply with the temperature and time limits set out in Advisory Note 7 published by AAPA:
468f6d05-42ef-53c3-8e7c-b1f2c10f0104 | note | Asphalt: which does not contain RAP material may be retained in hot storage silos for a period not exceeding 24 hours
5d8aef0f-f8c7-548f-813a-beaff6eed2b5 | note | INSPECTION/TEST METHOD: Inspection
e05a0fab-94b6-51fd-aaf6-60c2b25dcbde | note | CONFORMANCE RECORD: ITC
4c9eb2d2-981b-5cc7-b231-567fa673b8f2 | note | HP*
9cc55764-b192-414a-98ef-eedb1abd669e | signoff | Accepted
6125cfb2-199e-4f56-8afc-ebed12e960de | checkpoint | 2.5 - Manufacturing Temperates
017742f1-0101-55ab-87c2-8eb92c6ec080 | note | FREQUENCY: Per Lot
a5715664-315f-5639-91ff-6753086a68ae | note | ACCEPTANCE CRITERIA: The temperature of asphalt must not at any time exceed 175*
c8c2a477-21a9-527e-b2ce-32a443f15450 | note | INSPECTION/TEST METHOD: Inspection
99698b91-0642-4674-9ead-8a24af3f1a1a | signoff | Accepted
23489750-24a0-450e-b4d8-070847178128 | checkpoint | 2.6 - Transport of asphalt
86d8a5a3-0790-5aec-b857-7b49be5d269f | note | FREQUENCY: Per Lot
16adabc3-de36-5ec7-8da8-3d507836ddb0 | note | ACCEPTANCE CRITERIA: -Transport of asphalt in accordance with AS2150
9c23e01e-cee9-5db7-917a-92f637fdf708 | note | INSPECTION/TEST METHOD: Inspection
64a954f4-9c5b-41a9-b5b6-fb55b4eeea13 | signoff | Accepted
a7ca21f3-c7b6-4f0a-bba6-3686600c9f01 | section | Placement of Asphalt
20c1d84e-20cd-4665-8b27-f53a8d0e88e7 | checkpoint | 3.1 - Surface preparation
8e026286-ddf7-59b3-a28c-74e3f3e89f25 | note | FREQUENCY: Prior to excavation of toe
e14742c3-dec9-5f64-bd0e-b92eae750e32 | note | ACCEPTANCE CRITERIA: Prepare the suface in accordance with AS
fddb486e-d67d-5c00-99b3-822c51403e2a | note | CONFORMANCE RECORD: ITC
ab371c71-1588-52ef-8c59-2945002c81ad | note | INSPECTION/TEST METHOD: Site inspection
7c828207-25e3-52cd-bde2-f4b6894d495e | note | IP
80bf72e3-a9a8-58cd-923e-9cf2756a942f | date | Date Completed:
80fefcc8-ce2d-4487-a0df-15613caf420c | signoff | Accepted
e006a9a2-85ae-488e-81cf-a469a5993a96 | checkpoint | 3.2 - Protection of Road and Services Fixtures
367a404d-7eff-5e2b-9668-b4bf6fd01afb | note | FREQUENCY: Prior to commencement
4e4a64bb-c193-55ce-a929-1592f56dc130 | note | ACCEPTANCE CRITERIA: Trees for removal marked out and approved for removal
d13c320e-c092-5fba-a7c9-e5c96eb32f94 | note | CONFORMANCE RECORD: ITC
b72e461d-6eea-539a-b84c-e30c07574226 | note | INSPECTION/TEST METHOD: Site Inspection Permit
d11cb3bc-5ae7-5679-bc23-d8ac7aaa5c6f | note | HP
41daddb3-27ac-5f48-87eb-65d7f65458c1 | date | Date Completed:
f57d44dd-5721-40df-ae04-d8e7a77f6e15 | signoff | Accepted
fafd826a-5b18-4627-ae6a-e1314c3c8272 | checkpoint | 3.3 - Existing surface condition
0ccc9272-6936-5663-940c-f99747339d7f | note | FREQUENCY: xxx
f96e8575-c1c5-5ef2-82b4-e423178ae82a | note | ACCEPTANCE CRITERIA: yyy
036a565a-3015-5880-8b74-7cd8d2acb3c3 | note | REFERENCE DOCUMENTS: zzzz
b2c592e2-583d-5897-b038-40701b3289b1 | note | INSPECTION/TEST METHOD: aaaa
71c91742-fa37-51bf-a2fe-cf0133cc46dd | note | CONFORMANCE RECORD: bbbb
6b12ebf0-f46b-5c69-a694-d521fb2261dd | note | IP
6cad3ed0-896b-59e6-a9a4-f2329f670628 | date | Date Completed:
6abd173d-e626-4a86-af3a-1067790d036e | checkpoint | 3.4 - Tackcoat application rate
f4ffc575-12f4-5a6e-965d-4e7225048e1b | note | FREQUENCY: xxx
a1c0858e-1969-5750-8a0e-78016a15c178 | note | ACCEPTANCE CRITERIA: yyy
0bdb9e3f-6920-564c-a5c8-a4035f601c9d | note | REFERENCE DOCUMENTS: zzzz
4e1aaf06-6ca7-5895-9635-09e471b8b16f | note | INSPECTION/TEST METHOD: aaaa
0d366441-b6a5-5cda-8656-9e0b95db7212 | note | CONFORMANCE RECORD: bbbb
274a18db-e812-51ff-b31c-b6337947af05 | note | IP
3417ad53-460e-5d9a-ac0f-420ea20972b3 | date | Date Completed:
04fca6aa-f288-4baf-af03-00d77785dc60 | signoff | HOLDPOINT
a6c3adea-1497-494d-9107-c26543cd7a60 | checkpoint | 3.5 - Tackcoat daily record
2c7d6cd9-fe1f-5ae0-9e6b-77b7c710d5ce | note | FREQUENCY: xxx
32b793d9-e4fc-5e48-a41c-1924122bc033 | note | ACCEPTANCE CRITERIA: yyy
88a92277-d25f-5924-96d6-3020cf034e4f | note | REFERENCE DOCUMENTS: zzzz
02e0bb20-ea44-552e-8158-ce44fdc7bab1 | note | INSPECTION/TEST METHOD: aaaa
85a57209-645d-5cbe-9f4a-78ef53747379 | note | CONFORMANCE RECORD: bbbb
4fbfaf30-0ddb-5b71-ad61-a344240fe3b7 | note | IP
ba2da9ad-728d-52cc-89e7-c1985db23f54 | date | Date Completed:
22f5cd54-e8fa-4384-8132-0fddc6533507 | checkpoint | 3.6 - AAAA
e22499d7-78c1-5c94-bfad-68091fcab45b | note | FREQUENCY: During the placement of the toe rock
e8345f41-f893-572a-89f2-00cdbbbffbad | note | ACCEPTANCE CRITERIA: Solid base, Maximum particle sizes 750-1000mm
51bb87e7-8916-5f1a-ac50-9825c26626a9 | note | REFERENCE DOCUMENTS: N/A
de432fa4-5caf-5aa0-b803-6833e56fa68c | note | INSPECTION/TEST METHOD: Inspection
0705f010-3be7-57c0-97ee-52764d4caeb2 | note | CONFORMANCE RECORD: ITP
58df7331-8cc5-5f64-82fb-9dbef87b210d | note | IP
bb77e2d1-c1b6-596f-87b5-ff1748086944 | date | Date Completed:
f043cd1c-e23a-4b45-8436-1e8d93230ed7 | signoff | Accepted
7228e70d-9714-4d73-9aac-74659f564120 | checkpoint | 3.7 - Temperature and weather condition
a107b479-97be-5d86-9dd7-1611f69f0f5a | note | FREQUENCY: During construction
74889dcb-ea76-5344-b9aa-16e8fddf8240 | note | ACCEPTANCE CRITERIA: Flowable grout adequately placed to fill void under downstream wingwall
a01cb800-63e9-502b-b27e-00d20c9ff24b | note | REFERENCE DOCUMENTS: Drawing
1f8cd2a3-0f8d-5718-8e70-cef30481b433 | note | INSPECTION/TEST METHOD: Inspection
194579af-5574-5387-bf9b-d44e79e538ae | note | CONFORMANCE RECORD: ITP
05294e13-55c2-501c-8328-d0c47b5bc714 | note | HP
e7afb4e8-77a8-50cb-8aa2-403009970c3f | note | RESPONSIBILITY: Client
26306419-c596-5b8d-a0db-239da4ad0a6f | date | Date Completed:
3d784d13-4d63-45b6-8cec-1f4b97b461a2 | signoff | Accepted
8ecdf3c4-8956-4ee0-8b5f-fc83548ff6db | section | Sampling and testing of placed asphalt
53a32300-ffe7-4ce6-90f7-bb19dd675e72 | checkpoint | 4.1 - Determination of insitu Air voidspreparation
f38fdd78-efe7-489b-bf51-8ba1fd5d9215 | checkpoint | 4.2 - protetion of road and sevice Fixtures
38b59b4c-f4d6-4759-b5dc-a908218c9978 | checkpoint | 4.3 - protetion of road and sevice Fixtures
4e11df68-8dd5-463a-9c59-857e1a04e3f8 | checkpoint | 4.4 - protetion of road and sevice Fixtures
4a4045b0-af51-4fed-863c-41e4e5faf5e9 | section | Conformance
c478edad-0737-4fd1-94d0-57a246f6f534 | checkpoint | 5.1 - Homogeneity
d1875727-62a7-4dbd-ba6d-6b3f43027d20 | checkpoint | 5.2 - Rectification or replacement of a nonconforming Lot
234d0903-e7cc-47f7-a170-2808147f90ce | signoff | HOLDPOINT
dd5906fa-89df-4448-9c0a-b4a326b4354b | checkpoint | 5.3 - Further production of the nominated mix
44cdf0d0-f170-4d61-8a4b-299cd04e8da2 | signoff | HOLDPOINT
ba5d0b2e-c004-4fdc-b1a7-502410553fb7 | checklist | IM-FOR-1000-001 - RFI |  | RFI#
9312ae44-ba54-433c-8e47-f3be9774d876 | section | Request for Information
a4626773-05dc-496c-8114-55a16943a7ab | checkpoint | RFI
d5068229-d273-51ed-87e4-a9ef479f20d9 | textbox | Process
baa7c427-bff7-5624-acb8-2e0206f6aca1 | textbox | ITP Reference No
d25c0d3c-3a94-5d6f-b8df-e1391d56916a | textbox | Lot Reference
11de142e-3a54-5ce0-ba06-1efded3160cf | textbox | Description
287ec80a-930a-5134-b866-37c2b3139fbf | textbox | Drawing Ref
e1e749ff-87d5-5a7d-8f5a-e44195dd0c1f | textbox | Information Requested
3e66c009-0787-58d9-a61e-1adde7a20f06 | date | Todays Date
dffd2350-4ea1-5e2c-b100-e863af31bb3f | date | Expected Reply Date
1cf44b08-8c32-5383-bfa3-02099b644721 | date | Response Received
9430b8e2-8bfc-421c-8152-24fd6cc6ec87 | signoff | Request for Information