## Table 1
Memorial Avenue Upgrade, Kellyville Job No. 1680 Client: Transport for New South Wales (TfNSW) Principal’s Authorised Person: Mark Jajou | [8 empty] | Area No. |  |  |  | 1
[9 empty] | Activity Type |  |  |  | Kerb & Gutter
INSPECTION AND TEST PLAN |  |  |  |  | KERBS AND GUTTERS – R15 Ed 4 / Rev 3 (Jul-2019) | [6 empty] | Checklist No. | [5 empty] | 1680-CHK-R15-001
Item |  | Activity | Reference |  | Acceptance Criteria |  |  |  |  | Frequency |  |  |  | Acceptance By | [5 empty] | Record / Comments
|  |  | Spec | Method | [9 empty] | DG |  |  | TfNSW | Other
|  | In work sequence | OHSR, Environment, Quality aspect Specification, standard or | [6 empty] | Inspection/testing frequency |  |  |  | See key on final page. | [5 empty] | Identify relevant records Add notes to assist.
1. PRELIMINARIES
1.1 |  | SWMS, EWMS and EPL | G22 Cl 3.4 G36 G38 |  | -Ensure SWMS & EWMS are in place, understood and signed off by all personnel involved in completing the task -Ensure EPL criteria are conformed with |  |  |  |  | Prior to commencement |  |  |  | PE |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
1.2 |  | Erosion and Sedimentation Control Plan | G38 Cl 2.1.2, 3.1.1 |  | Ensure ERSED plan has been developed and communicated to site team. |  |  |  |  | Prior to commencement |  |  |  | ENM |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
1.3 |  | Traffic Control | G10 Cl 2 |  | -Traffic control is in place. -Relevant TCP and VMP are approved |  |  |  |  | Prior to commencement |  |  |  | TM |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
1.4 |  | Construction Lot Identification, Traceability and Frequency of Testing | Q6, Cl 7.5.3 Annexure L1 Annexure L3 |  | -Set the bounds for each construction lot as per Q6 requirements -Lot Number assigned -Lot size as per specification -This lot number as an identifier on all quality records -Lot map is prepared for traceability -Frequency of testing as per Q6/L3 and specification requirements |  |  |  |  | Prior to commencement |  |  |  | PQR |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
2. MATERIALS
2.1 |  | Materials | R15 Cl 2 |  | Concrete properties and delivery, placing, compaction, finishing, curing and protection in accordance with RMS R53. |  |  |  |  | Per Lot |  |  |  | ENG SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
2.2 |  | Production of Concrete Mix HOLD POINT | R53, Cl 2.4.3 |  | Submit any one of the following: (a) The documents specified in Clause 2.4.3 items (a) and (b); or (b) Details of mix(es) selected from the RMS Register of Concrete Mixes, together with a statement certifying that the mix conforms to this Specification and is suitable for its intended use |  |  |  |  | At least 5 days prior to production |  |  |  | ENG |  |  | HP |  |  | HP Release / Refer to checklist 1680- CHK-R15-001
2.3 |  | Curing Compound | R53, Cl 2.6 |  | The curing compound must be: (a) a hydrocarbon resin compound complying with AS 3799 Class B, Type 1-D; or (b) a wax emulsion complying with AS 3799 Class A, Type 1-D. |  |  |  |  | Per Lot |  |  |  | ENG |  |  |  |  |  | CoC / Refer to checklist 1680- CHK-R15-001
3. CONSTRUCTION
3.1 |  | Construction | R15 Cl 2 |  | Do not undercut the batters of cuttings. Construct kerbs and gutters in accordance with AS 2876 modified as shown in Table R15.1. Provide a steel float finish to gutter inverts and faces of kerbs (unless otherwise in Drawings). |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.2 |  | Profiles and Dimensions | R15 Cl 2 |  | As nominated on Drawings. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.3 |  | Preparation of Supporting Layers | R15 Cl 2 |  | Compact subgrade, subbase and base layers supporting kerb and gutter to standard specified for the adjacent pavement |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.4 |  | Tolerance | R15 Cl 2 |  | Gutter and adjacent pavement gutter lip +0/-10 mm to adjoining pavement surface. |  |  |  |  | Every 10 m |  |  |  | SU |  |  |  |  |  | Survey Report / Refer to checklist 1680-CHK-R15-001
3.5 |  | Joints | R15 Cl 2 |  | Expansion: provide at all points where kerbs and gutters abut structures. Provide preformed joint filler complying with RMS 3204 within joint. Isolation: provide between pit and rigid pavement |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.6 |  | Kerb & Gutter with Flexible Pavement | R15 Cl 3 |  | Constructed in fixed forms or by extrusion or slip forming. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.7 |  | Kerb & Gutter with Rigid Pavement Constructed Adjacent to Concrete Base | R15 Cl 4 |  | Kerb & gutter alongside and tied to base placed by fixed forms or slip forming. Longitudinal joints continuous over full length without steps or offsets. Must not deviate from a 3m straight- edge by > 20mm. Joint corrugated and tied as on Drawings and as specified for the base. Kerb & gutter alongside but not tied to the base constructed in fixed forms, extrusion or slip forming. Seal longitudinal joints as on Drawings. Provide kerbs placed on top of concrete base with ties as shown on Drawings. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.8 |  | Kerb & Gutter with Rigid Pavement Placed After Concrete Base | R15 Cl 4 |  | Complete base joint sealing prior to kerb & gutter construction. For kerb & gutter alongside base, extend sealant down vertical face of transverse base joints and any underlying crack > 1mm wide. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.9 |  | Kerb & Gutter with Rigid Pavement Constructed Before Concrete Base | R15 Cl 4 |  | For kerb/gutter constructed before base and kerb and gutter lip is to be level with upper base surface: radius of lip adjacent to the base < 5mm, unless otherwise on Drawings. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.1 |  | Joints | R15 Cl 4 |  | Untied joints in base must continue across kerb & gutter in same type and on same alignment. Tied joints need not continue into kerb. Seal joints with sealant used for base joints. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.11 |  | Kerb Constructed on Top of Concrete Base | R15 Cl 4 |  | Align each joint in kerb with underlying base joint. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.12 |  | Kerb & Gutter with Rigid Pavement Placed Alongside Base Joints | R15 Cl 4 |  | Where kerb and gutter is placed alongside the base joints in the kerb and gutter must intersect at the common longitudinal joint (± 15mm). For kerb and gutter placed integrally with the base, align joints with those in base. Otherwise, align joints at an angle of 90° ± 5° to line of kerb. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.13 |  | Removal of Kerb & Gutter | R15 Cl 5 |  | Kerbs, gutters and vehicular crossings removed and excavations backfilled as per G40 Clause 2.5. Material from removed kerb & gutter will become Daracon property and must be removed and disposed off-site in accordance with the Waste Management Sub-Plan RMS G36 |  |  |  |  | Per Lot |  |  |  | ENG SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.14 |  | No Fines Concrete Under Kerb & Gutter | R15 Cl 6 |  | Place no fines concrete under kerb and gutter in accordance with RMS 3222 & geotextile comply with RMS R63 Cure no fines concrete for 7 days with polyethylene sheeting ≥ 0.125mm thick or until covered by kerb and gutter. Place kerb & gutter after 5 days of placing concrete or until no fines concrete has sufficient strength. Surface voids to remain open, do not slurry surface. |  |  |  |  | Per Lot |  |  |  | SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
3.15 |  | THSC “150mm Kerb & Gutter” | R15 Cl 7 |  | Where shown on the Drawings, construct kerb & gutter in accordance with the Hills Shire Council specification SD14. |  |  |  |  | Per Lot |  |  |  | ENG SS |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
4. CONFORMANCE
4.1 |  | Identification and Control of Non-conforming Products or Services | Q6 Cl 8.3 |  | NCR to be opened & closed prior to closing of construction Lot |  |  |  |  | After work completion |  |  |  | PQR |  |  |  |  |  | Non-Conformance Report
4.2 |  | Verification that Rectified Work Conforms HOLD POINT | Q6 Cl 8.3 |  | Verification that rectified works conform to accepted rectification method and specifications within the NCR |  |  |  |  | Prior to covering up the works |  |  |  | PQR |  |  | HP |  |  | NCR # Refer to checklist 1680-CHK-R015- 001
4.3 |  | Final Verification of Construction Lot Records | Q6 Cl 8.2.4.3 |  | To confirm that all inspections and tests have been carried out to completely verify conformity. |  |  |  |  | Prior to closing out each lot |  |  |  | PQR |  |  |  |  |  | Refer to checklist 1680-CHK-R15-001
[7 empty] | KEY | CoC |  |  | Certificate of Conformance |  |  |  |  | ENG |  |  | Engineer Responsible
[8 empty] | HP |  |  | Hold point |  |  |  |  | ENM |  |  | Environmental Manager
[8 empty] | IR |  |  | Identified Record |  |  |  |  | PE |  |  | Project Engineer
[8 empty] | S |  |  | Surveillance |  |  |  |  | PQR |  |  | Project Quality Representative
[8 empty] | T |  |  | Test |  |  |  |  | SS |  |  | Site Supervisor
[8 empty] | WP |  |  | Witness point |  |  |  |  | SA |  |  | Site Administrator
[16 empty] | SU |  |  | Surveyor
[16 empty] | TM |  |  | Traffic Manager
| Prepared by: Emma Cowdery |  |  |  |  | Authorised for Use: Andrew Rigby | [8 empty] | Date: 27/09/2021