## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | 1680 - ITP-R15.001_A01 Kerbs and Gutters | itp |  |  |  |  | 1680 - ITP-R15.001_A01 Kerbs and Gutters Rev.1
section | 1. PRELIMINARIES
checkpoint | 1.1 - SWMS, EWMS and EPL
label | REFERENCE / METHOD - G22 Cl 3.4 G36 G38
label | ACCEPTANCE CRITERIA - Ensure SWMS & EWMS are in place, understood and signed off by all personnel involved in completing the task
label | ○ Ensure EPL criteria are conformed with
label | FREQUENCY - Prior to commencement
label | ACCEPTANCE BY: DG - PE
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 1.2 - Erosion and Sedimentation Control Plan
label | REFERENCE / METHOD - G38 Cl 2.1.2, 3.1.1
label | ACCEPTANCE CRITERIA - Ensure ERSED plan has been developed and communicated to site team.
label | FREQUENCY - Prior to commencement
label | ACCEPTANCE BY: DG - ENM
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 1.3 - Traffic Control
label | REFERENCE / METHOD - G10 Cl 2
label | ACCEPTANCE CRITERIA - Traffic control is in place.
label | ○ Relevant TCP and VMP are approved
label | FREQUENCY - Prior to commencement
label | ACCEPTANCE BY: DG - TM
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 1.4 - Construction Lot Identification, Traceability and Frequency of Testing
label | REFERENCE / METHOD - Q6, Cl 7.5.3 Annexure L1 Annexure L3
label | ACCEPTANCE CRITERIA - Set the bounds for each construction lot as per Q6 requirements
label | ○ Lot Number assigned
label | ○ Lot size as per specification
label | ○ This Lot Number as an identifier on all quality records
label | ○ Lot map is prepared for traceability
label | ○ Frequency of testing as per Q6/L3 and specification requirements
label | FREQUENCY - Prior to commencement
label | ACCEPTANCE BY: DG - PQR
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
section | 2. MATERIALS
checkpoint | 2.1 - Materials
label | REFERENCE / METHOD - R15 Cl 2
label | ACCEPTANCE CRITERIA - Concrete properties and delivery, placing, compaction, finishing, curing and protection in accordance with RMS R53.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - ENG SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 2.2 - Production of Concrete Mix HOLD POINT
label | REFERENCE / METHOD - R53, Cl 2.4.3
label | ACCEPTANCE CRITERIA - Submit any one of the following:
label | (a) The documents specified in Clause 2.4.3 items (a) and (b); or
label | (b) Details of mix(es) selected from the RMS Register of Concrete Mixes, together with a statement certifying that the mix conforms to this Specification and is suitable for its intended use
label | FREQUENCY - At least 5 days prior to production
label | ACCEPTANCE BY: DG - ENG
label | ACCEPTANCE BY: TfNSW - HP
label | RECORD / COMMENTS - HP Release / Refer to checklist 1680- CHK-R15-001
holdpoint | HOLD POINT
checkpoint | 2.3 - Curing Compound
label | REFERENCE / METHOD - R53, Cl 2.6
label | ACCEPTANCE CRITERIA - The curing compound must be:
label | (a) a hydrocarbon resin compound complying with AS 3799 Class B, Type 1-D; or
label | (b) a wax emulsion complying with AS 3799 Class A, Type 1-D.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - ENG
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - CoC / Refer to checklist 1680- CHK-R15-001
section | 3. CONSTRUCTION
checkpoint | 3.1 - Construction
label | REFERENCE / METHOD - R15 Cl 2
label | ACCEPTANCE CRITERIA - Do not undercut the batters of cuttings. Construct kerbs and gutters in accordance with AS 2876 modified as shown in Table R15.1.
label | ○ Provide a steel float finish to gutter inverts and faces of kerbs (unless otherwise in Drawings).
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.2 - Profiles and Dimensions
label | REFERENCE / METHOD - R15 Cl 2
label | ACCEPTANCE CRITERIA - As nominated on Drawings.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.3 - Preparation of Supporting Layers
label | REFERENCE / METHOD - R15 Cl 2
label | ACCEPTANCE CRITERIA - Compact subgrade, subbase and base layers supporting kerb and gutter to standard specified for the adjacent pavement
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.4 - Tolerance
label | REFERENCE / METHOD - R15 Cl 2
label | ACCEPTANCE CRITERIA - Gutter and adjacent pavement gutter lip +0/-10 mm to adjoining pavement surface.
label | FREQUENCY - Every 10 m
label | ACCEPTANCE BY: DG - SU
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Survey Report / Refer to checklist 1680-CHK-R15-001
checkpoint | 3.5 - Joints
label | REFERENCE / METHOD - R15 Cl 2
label | ACCEPTANCE CRITERIA - Expansion: provide at all points where kerbs and gutters abut structures. Provide preformed joint filler complying with RMS 3204 within joint.
label | ○ Isolation: provide between pit and rigid pavement
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.6 - Kerb & Gutter with Flexible Pavement
label | REFERENCE / METHOD - R15 Cl 3
label | ACCEPTANCE CRITERIA - Constructed in fixed forms or by extrusion or slip forming.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.7 - Kerb & Gutter with Rigid Pavement Constructed Adjacent to Concrete Base
label | REFERENCE / METHOD - R15 Cl 4
label | ACCEPTANCE CRITERIA - Kerb & gutter alongside and tied to base placed by fixed forms or slip forming. Longitudinal joints continuous over full length without steps or offsets. Must not deviate from a 3m straight- edge by > 20mm. Joint corrugated and tied as on Drawings and as specified for the base.
label | ○ Kerb & gutter alongside but not tied to the base constructed in fixed forms, extrusion or slip forming. Seal longitudinal joints as on Drawings.
label | ○ Provide kerbs placed on top of concrete base with ties as shown on Drawings.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.8 - Kerb & Gutter with Rigid Pavement Placed After Concrete Base
label | REFERENCE / METHOD - R15 Cl 4
label | ACCEPTANCE CRITERIA - Complete base joint sealing prior to kerb & gutter construction.
label | ○ For kerb & gutter alongside base, extend sealant down vertical face of transverse base joints and any underlying crack > 1mm wide.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.9 - Kerb & Gutter with Rigid Pavement Constructed Before Concrete Base
label | REFERENCE / METHOD - R15 Cl 4
label | ACCEPTANCE CRITERIA - For kerb/gutter constructed before base and kerb and gutter lip is to be level with upper base surface: radius of lip adjacent to the base < 5mm, unless otherwise on Drawings.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.10 - Joints
label | REFERENCE / METHOD - R15 Cl 4
label | ACCEPTANCE CRITERIA - Untied joints in base must continue across kerb & gutter in same type and on same alignment.
label | ○ Tied joints need not continue into kerb. Seal joints with sealant used for base joints.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.11 - Kerb Constructed on Top of Concrete Base
label | REFERENCE / METHOD - R15 Cl 4
label | ACCEPTANCE CRITERIA - Align each joint in kerb with underlying base joint.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.12 - Kerb & Gutter with Rigid Pavement Placed Alongside Base Joints
label | REFERENCE / METHOD - R15 Cl 4
label | ACCEPTANCE CRITERIA - Where kerb and gutter is placed alongside the base joints in the kerb and gutter must intersect at the common longitudinal joint (± 15mm).
label | ○ For kerb and gutter placed integrally with the base, align joints with those in base. Otherwise, align joints at an angle of 90° ± 5° to line of kerb.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.13 - Removal of Kerb & Gutter
label | REFERENCE / METHOD - R15 Cl 5
label | ACCEPTANCE CRITERIA - Kerbs, gutters and vehicular crossings removed and excavations backfilled as per G40 Clause 2.5.
label | ○ Material from removed kerb & gutter will become Daracon property and must be removed and disposed off-site in accordance with the Waste Management Sub-Plan RMS G36
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - ENG SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.14 - No Fines Concrete Under Kerb & Gutter
label | REFERENCE / METHOD - R15 Cl 6
label | ACCEPTANCE CRITERIA - Place no fines concrete under kerb and gutter in accordance with RMS 3222 & geotextile comply with RMS R63
label | ○ Cure no fines concrete for 7 days with polyethylene sheeting ≥ 0.125mm thick or until covered by kerb and gutter. Place kerb & gutter after 5 days of placing concrete or until no fines concrete has sufficient strength. Surface voids to remain open, do not slurry surface.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
checkpoint | 3.15 - THSC “150mm Kerb & Gutter”
label | REFERENCE / METHOD - R15 Cl 7
label | ACCEPTANCE CRITERIA - Where shown on the Drawings, construct kerb & gutter in accordance with the Hills Shire Council specification SD14.
label | FREQUENCY - Per Lot
label | ACCEPTANCE BY: DG - ENG SS
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001
section | 4. CONFORMANCE
checkpoint | 4.1 - Identification and Control of Non-conforming Products or Services
label | REFERENCE / METHOD - Q6 Cl 8.3
label | ACCEPTANCE CRITERIA - NCR to be opened & closed prior to closing of construction Lot
label | FREQUENCY - After work completion
label | ACCEPTANCE BY: DG - PQR
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Non-Conformance Report
checkpoint | 4.2 - Verification that Rectified Work Conforms HOLD POINT
label | REFERENCE / METHOD - Q6 Cl 8.3
label | ACCEPTANCE CRITERIA - Verification that rectified works conform to accepted rectification method and specifications within the NCR
label | FREQUENCY - Prior to covering up the works
label | ACCEPTANCE BY: DG - PQR
label | ACCEPTANCE BY: TfNSW - HP
label | RECORD / COMMENTS - NCR #
label | ○ Refer to checklist 1680-CHK-R015-001
holdpoint | HOLD POINT
checkpoint | 4.3 - Final Verification of Construction Lot Records
label | REFERENCE / METHOD - Q6 Cl 8.2.4.3
label | ACCEPTANCE CRITERIA - To confirm that all inspections and tests have been carried out to completely verify conformity.
label | FREQUENCY - Prior to closing out each lot
label | ACCEPTANCE BY: DG - PQR
label | ACCEPTANCE BY: TfNSW - ✔
label | RECORD / COMMENTS - Refer to checklist 1680-CHK-R15-001