## Table 1
[6 empty] | PROJECT: |  |  |  | 101 – 121 Castlereagh Street, Sydney | [5 empty] | ITP No. | [5 empty] | 15 |  |  |  | Rev: |  |  |  | 1 |  |  | Page No 1 of 7
| Trade/Supply Item |  |  | Façade – Curtain Wall
Subcontractor
Location of Works
| Reviewed by: |  |  | Name | [6 empty] | Title | [19 empty] | Date:
ALL CLADDINGS MUST BE MECHANICALLY FIXED, ADHESIVES NOT PERMITTED REFER TO TECHNICAL STANDARD 009 SDC-NSD-DSN-TDC-009
| WORK ACTIVITY/ SEQUENCE |  | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | [5 empty] | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  |  | INSPECTIONS & VERIFICATION | [15 empty] | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
[12 empty] | By |  | Type of (Hold, Witness, Surveillance) | [5 empty] | Completed |  |  |  | Date
PRIOR TO CURTAIN WALL INSTALL WORKS
| Shop Drawings |  | Aconex – Façade Drawings | [5 empty] | Confirm correct For Construction Shop drawings available for the installation with the contractor. Refer to Plan located at core walls for approved reference (SDC site engineer to install reference plan) |  |  | SE/FN |  | Witness | [13 empty] | Record Shop Drawings available at time of installation from subcontractor.
| Survey & Site Measures | [7 empty] | Check minimum survey requirements provided for the installation (ie; intersecting grids and benchmarks). |  |  | FN |  | Hold | [13 empty] | Attach Photos of grids and benchmarks provided.
[9 empty] | Confirm opening sizes (widths and heights) correct per shop drawings. Check also that hobs & set down are level. |  |  | FN |  | Witness | [13 empty] | Record as-built slab/hob/set-down SSL on install floor and floor/soffit above for reference (Surveyor As- built).
| Storage/Installation Area | [7 empty] | Confirm curtain wall storage/staging area is available and ready. Confirm installation zones available and ready from previous trades. |  |  | FN |  | Surveillance | [13 empty] | Note: storage/staging and installation zones may be across multiple floors (ie; panel install on 1st floor, floor above to be panel laydown, 3rd floor for crane). Ensure plywood installed across set-downs for pallet trolley movements.
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [17 empty] | H = Hold Point Work cannot proceed without verification/approval by another party | [9 empty] | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  |  | S =Surveillance (Sign-off ) Verification of quality of work, conformance with specification etc
[6 empty] | PROJECT: |  |  |  | 101 – 121 Castlereagh Street, Sydney | [5 empty] | ITP No. | [5 empty] | 15 |  |  |  | Rev: |  |  |  | 1 |  |  | Page No 2 of 7
| WORK ACTIVITY/ SEQUENCE |  | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | [5 empty] | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  |  | INSPECTIONS & VERIFICATION | [15 empty] | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
[12 empty] | By |  | Type of (Hold, Witness, Surveillance) | [5 empty] | Completed |  |  |  | Date
| Product Review |  | Aconex – Façade Drawings | [5 empty] | Confirm all curtain wall panels are free from damages prior to installation. |  |  | FN/SE |  | Witness | [13 empty] | Take photos and record any damages prior to install with specific panels (reference shop drawings for panel identification). Panel sign-off walk to occur to after each shift to record damages (if required)
|  |  | Aconex – Façade Drawings | [5 empty] | Confirm panels are correct for the floor/area being installed, including colour, grade and thicknesses. |  |  | FN |  | Witness | [13 empty] | Record photos of panel identification marks on packaging for reference. Compare against install plan on Core Walls.
| Cast-in Façade Channel |  | Façade Contractor ITP | [5 empty] | Confirm façade channel installed per agreed detail and in correct locations per shop drawings. |  |  | FN/SE |  | Hold | [13 empty] | Attached façade contractor pre-pour inspection ITP for cast-in façade channel.
| Cast-in Façade Channel |  | Façade Contractor ITP | [5 empty] | Confirm Channel pull out testing has been conducted on cast-in elements prior to curtain wall installation. |  |  | SE |  | Hold | [13 empty] | Attached façade channel testing report showing compliance of brackets.
| Weatherproofing Pre-Works |  | AS 3740 | [5 empty] | Ensure all sub-structure has membrane installed and signed-off prior to curtain wall installation. |  |  | FN |  | Hold | [13 empty] | Ensure to check areas such as: hobs for starter panels, vertical interfaces such as curtain wall to core wall junctions, balcony set downs, etc… Attach waterproofing contractors ITP.
DURING CURTAIN WALL INSTALL WORKS
| Benchmark RL for Installation |  | Site Survey Marks | [5 empty] | Verify with curtain wall install contractor that they are working from the agreed benchmark to set panel positions/heights. |  |  | FN |  | Hold | [13 empty] | Record agreed benchmark:
| Installation / Operation Checks | [7 empty] | Review curtain wall panels installed plumb and level with panels below and adjacent. |  |  | FN |  | Surveillance | [13 empty] | Spot check 5 panels per floor and complete general visual check.
[9 empty] | Ensure curtain wall installed to the design façade line. Tolerance permissible is + / - 5mm per façade specification. |  |  | FN |  | Surveillance | [13 empty] | Check measure off grid as required, use level on panels to check plumb. Spot check 5 panels per floor and complete general visual check.
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [17 empty] | H = Hold Point Work cannot proceed without verification/approval by another party | [9 empty] | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  |  | S =Surveillance (Sign-off ) Verification of quality of work, conformance with specification etc
[6 empty] | PROJECT: |  |  |  | 101 – 121 Castlereagh Street, Sydney | [5 empty] | ITP No. | [5 empty] | 15 |  |  |  | Rev: |  |  |  | 1 |  |  | Page No 3 of 7
| WORK ACTIVITY/ SEQUENCE |  | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | [5 empty] | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  |  | INSPECTIONS & VERIFICATION | [15 empty] | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
[12 empty] | By |  | Type of (Hold, Witness, Surveillance) | [5 empty] | Completed |  |  |  | Date
[9 empty] | Check to ensure correct type of glass or non- vision panels, etc… installed per shop drawings. |  |  | FN |  | Surveillance | [13 empty] | Refer to shop drawings installed on core walls (curtain wall general arrangement & typical panel details) for reference.
[9 empty] | Review sub-head and sub-jamb installation to ensure required gap left for movement per shop drawings (ie; approx. 20-30mm). |  |  | FN |  | Surveillance | [13 empty] | Ensure to check wintergarden balcony panels (sub- head) and panels adjacent to core walls (sub-jamb). Spot check 5 panel per floor, attach photos with tape measure.
[9 empty] | Review sub-sill installation, ensure caulking to mechanical fixings where penetrating membrane installations. |  |  | FN |  | Surveillance | [13 empty] | All Mechanical anchors to be sealed. Spot check 5 panels per floor, attach photos of sealant works.
[9 empty] | Check installation of smoke flashing and required fire rated insulation (CSR Bradford Fire Seal Curtain Wall Batt) at slab to panel interface. Ensure insulation install to depth of slab. Ensure no gaps present in flashings. |  |  | FN |  | Surveillance | [13 empty] | Spot check 5 panels per floor. Attach photos to ITP prior to insulation being covered over. Attach photos of finished smoke flashing.
|  |  | Façade Specification | [5 empty] | Review fixings to ensure stainless steel per description noted below from façade specification. Fixings and Hardware: - Within panels to be grade 304 stainless steel - Internal fixings (including to structure) to be grade 304 stainless steel - External and visible fixings to be grade 316 stainless steel |  |  | FN |  | Surveillance | [13 empty] | Spot check for each floor installation the panels and subcontractor supplies being used on-site.
|  |  | FJC façade details | [5 empty] | Check secure installation of weatherproof sill flashings and membrane works completed accordingly per architect details. Check any pressure seals installed correctly. | [18 empty] | Review against each interface.
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [17 empty] | H = Hold Point Work cannot proceed without verification/approval by another party | [9 empty] | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  |  | S =Surveillance (Sign-off ) Verification of quality of work, conformance with specification etc
[5 empty] | PROJECT: |  |  | 101 – 121 Castlereagh Street, Sydney | [6 empty] | ITP No. | [5 empty] | 15 |  |  |  | Rev: |  |  |  | 1 |  |  | Page No 4 of 7
WORK ACTIVITY/ SEQUENCE |  | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) |  |  |  |  | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  |  |  | INSPECTIONS & VERIFICATION | [15 empty] | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
[11 empty] | By |  | Type of (Hold, Witness, Surveillance) | [5 empty] | Completed |  |  |  | Date
[7 empty] | Check secure installation of any façade sun hoods or louvre elements to panels during install. Check bolts have been secured to required torque (xxx) |  |  |  | FN |  | Witness | [13 empty] | Spot check at least 2 panels per floor and attach photos of torque measurements.
[7 empty] | Check all operable parts are working correctly (ie; sliding doors/windows, window winders/restrictors, door locks and hardware, etc…). |  |  |  | FN |  | Surveillance | [13 empty] | Specific Checks (2 full apartments per floor): - Manual awning windows are restricted to 125mm. - Check auto awning windows have cables pulled out and accessible & operating correctly. - Check sash windows to wintergardens and balcony sliding doors are operating smoothly. - Check awning window and sliding door handle hardware engaging correctly. - Swinging doors – check handle operation and restrictors to hold open door are working correctly.
|  | Acrylic Sash Handles |  |  |  |  | Check acrylic handle to sash window installed at 1900mm AFFL, level and to centre of panels. Check also that adhesive is free from bubbles |  |  |  | FN |  | Surveillance | [13 empty] | Complete full check of 2 apartments per floor.
[7 empty] | Check all silicone/caulking installed on-site is as per approved sample. |  |  |  | FN |  | Surveillance | [13 empty] | Product approved: Sikaflex-PRO (Concrete Grey Colour) – 961737 Spot check subcontractor supplies per floor installation.
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [16 empty] | H = Hold Point Work cannot proceed without verification/approval by another party | [10 empty] | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  |  | S =Surveillance (Sign-off ) Verification of quality of work, conformance with specification etc
[6 empty] | PROJECT: |  |  |  | 101 – 121 Castlereagh Street, Sydney | [5 empty] | ITP No. | [5 empty] | 15 |  |  |  | Rev: |  |  |  | 1 |  |  | Page No 5 of 7
| WORK ACTIVITY/ SEQUENCE |  | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | [5 empty] | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  |  | INSPECTIONS & VERIFICATION | [15 empty] | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
[12 empty] | By |  | Type of (Hold, Witness, Surveillance) | [5 empty] | Completed |  |  |  | Date
| Services – Mechanical (Kitchen/Toilet Exhaust) |  | Mechanical Shop Drawings & Curtain Wall Shop Drawings | [5 empty] | Review for adequate installation and sealant of the mechanical ductwork to the curtain wall panels. |  |  | FN |  | Surveillance | [13 empty] | Record photos for reference. NOTE: Flexible ductwork connections to backpan to be installed prior to panel installation and checked to ensure adequately sealed. Check all instances of mechanical interfaces per floor.
| Balcony Services – Hydraulic/Fire (Water/Gas & Sprinkler Lines) |  | Hydraulic/Fire Shop Drawings & Curtain Wall Shop Drawings | [5 empty] | Review correct placement of water/gas lines at sub-head zone and ensure adequately sealed for weathertightness & Acoustics. |  |  | FN |  | Surveillance | [13 empty] | Refer to curtain wall shop drawing: XXX for installation details. Check all apartments to ensure details installed correctly.
| Balcony Services – Hydraulic (Overflows) |  | Hydraulic Shop Drawings & Curtain Wall Shop Drawings | [5 empty] | Check overflows installed below slab and adequately sealed to curtain wall facade by hydraulic contractor. |  |  | FN |  | Surveillance | [13 empty] | Attach typical photos showing installations – check all balconies per floor (x2 overflow installations per balcony).
| Curtain Wall Defects (Pre-Installation) | [7 empty] | Ensure all protection removed from external face of curtain wall panels pre-installation and review aluminium and glass to ensure free from surface defects. |  |  | FN |  | Surveillance | [13 empty] | Record any defect photos as part of ITP. Check 10 panels per floor (approx. 10%)
| Curtain Wall Defects (Post-Installation) | [7 empty] | Ensure all protection removed from internal face of curtain wall panels post-installation and review aluminium and glass to ensure free from surface defects. |  |  | FN |  | Surveillance | [13 empty] | Record any defect photos as part of ITP. Check 10 panels per floor (approx. 10%)
| Façade Access Elements |  | Façade Access Shop Drawings | [5 empty] | Where relevant levels, review and ensure façade access elements are attached to curtain wall installation per shop drawings (ie; raptor rails & pig tails, etc…). |  |  | FN |  | Surveillance | [13 empty] | Location References: Level 30 sunshade (raptor rails), Level 31 – 35 sunshades (pig tails). Attach install and certification documentation from façade access contractor as required. Attached typical photos of the installation for reference.
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [17 empty] | H = Hold Point Work cannot proceed without verification/approval by another party | [9 empty] | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  |  | S =Surveillance (Sign-off ) Verification of quality of work, conformance with specification etc
[6 empty] | PROJECT: |  |  |  | 101 – 121 Castlereagh Street, Sydney | [5 empty] | ITP No. | [5 empty] | 15 |  |  |  | Rev: |  |  |  | 1 |  |  | Page No 6 of 7
| WORK ACTIVITY/ SEQUENCE |  | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | [5 empty] | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  |  | INSPECTIONS & VERIFICATION | [15 empty] | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
[12 empty] | By |  | Type of (Hold, Witness, Surveillance) | [5 empty] | Completed |  |  |  | Date
| Grouting to Façade Pockets | [7 empty] | Ensure grouting to façade pockets completed as per detail in shop drawings. |  |  | FN |  | Surveillance | [13 empty] | Obtain sign-off from curtain wall contractor that brackets have been checked prior to infilling pockets. Check all pockets are filled by formwork contractor.
POST CURTAIN WALL INSTALL WORKS
| Contractors ITP | [7 empty] | Attach façade contractors’ installation ITPs (Façade curtain wall & Window Walls (Balcony panels) & terrace awnings). |  |  | FN |  | Hold | [13 empty] | ITP required to be obtained per floor and prior to handover of level to subsequent trades.
| Design Deviations | [7 empty] | Attach any correspondence related to design deviations as required to show approval from relevant consultants. |  |  | SE |  | Surveillance | [13 empty] | Track with design manager as required and review inline with DBPA
| Façade Engineer Inspection | [7 empty] | Attach façade engineer inspection report/sign- off as required. |  |  | SE |  | Witness | [13 empty] | Ensure façade engineer inspects whole installation of first floor curtain wall (Lv14) – cast-in brackets, curtain wall installation, smoke flashings, window walls, etc… Ensure periodic inspections there after (every 3 floors) and any new installation details.
| Curtain Wall Protection | [7 empty] | Ensure protection installed to curtain wall glazing as required to prevent scratches during construction. |  |  | FN |  | Hold | [13 empty] | Ensure protection (coreflute) is installed on every floor, to every panel prior to handover to subsequent trades.
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [17 empty] | H = Hold Point Work cannot proceed without verification/approval by another party | [9 empty] | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  |  | S =Surveillance (Sign-off ) Verification of quality of work, conformance with specification etc
[6 empty] | PROJECT: |  |  |  | 101 – 121 Castlereagh Street, Sydney | [5 empty] | ITP No. | [5 empty] | 15 |  |  |  | Rev: |  |  |  | 1 |  |  | Page No 7 of 7
| WORK ACTIVITY/ SEQUENCE |  | REFERENCE (Aust. Standard No., Contract Clause, Dwg No, Manufacturers Recommendations, BCA, DA etc) | [5 empty] | ACCEPTANCE CRITERIA (Specific requirements of Aust. Standard, Contract Clauses, Specifications, Drawings, Manufacturers Recommendations BCA, DA etc) |  |  | INSPECTIONS & VERIFICATION | [15 empty] | Comments / Records Record changes required to meet specification eg variation #, RFI #, alternative (material, process etc) used, sample approved on (date), NCR #., test reports, survey data, written approvals (letter reference)
[12 empty] | By |  | Type of (Hold, Witness, Surveillance) | [5 empty] | Completed |  |  |  | Date
Note: Signatures & dates are required under “Inspections and Verification” column. Do not just tick ! When preparing the ITP, consider consequences of failure such as cost of remedial work, effect on construction program, accessibility for rectification, disruption to use of building, consequential damage to other elements, threat to safety of workers & public, breach of legal or other regulatory requirements. | [17 empty] | H = Hold Point Work cannot proceed without verification/approval by another party | [9 empty] | W = Witness A point where another party may inspect or test. (eg. contract requirements for |  |  |  | S =Surveillance (Sign-off ) Verification of quality of work, conformance with specification etc