## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1630-P200-SYM-QAC-ITP-0059 Landscape Works | itp |  |  |  |  | 1630-P200-SYM-QAC-ITP-0059 Landscape Works
section | ITP Details
checkpoint | ITP Details
label | ITP No. - 0059
label | Rev No. - 00
label | Date of Issue - 1/02/2024
label | ITP Type - New
section | 1.0 Pre-start activities
checkpoint | 1.1 - Check Survey Set-out and TCM’s
label | Ref docs - 720.06
label | Acceptance criteria - Record existing TCM’s on TCM offset sheet.
label | ○ Survey set out including frame, benchmark, and recovery points in place.
label | ○ The Contractor shall set out the location and shape of planting areas in accordance with the Landscape Drawings.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Prior to start of works
label | Key - H
label | Resp - SE/PE
checkpoint | 1.2 - Submission and Records
label | Ref docs - 720.03, 720.044, 720.045
label | Acceptance criteria - The following items shall be provided before commencement of the relevant landscape work (if requested):
label | Inspections:
label | ○ plant stock for all plant species
label | Samples
label | ○ mulch
label | ○ imported topsoil
label | Records
label | ○ evidence of origin of indigenous provenance plant material
label | ○ analysis certificates for grass seed
label | ○ details of suppliers
label | ○ soil tests on topsoil
label | ○ copies of fertiliser labels
label | Have any/all of the above material records been acquired/completed and signed off?
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Prior to start of works
label | Key - R
label | Resp - SE/PE
label | SI Key - R
section | 2.0 Site Preparation
checkpoint | 2.1 - Setting Out of Landscape Softworks
label | Ref docs - 720.06
label | Acceptance criteria - Set out the location and shape of planting areas in accordance with IFC Landscape Drawings.
label | ○ Plant density requirements and planting offsets comply as shown in the plant schedules.
label | ○ Individual plants shall be in accordance with VicRoads Road Design Guidelines, including clear zone and sight distance requirements.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Prior to start of works, Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 2.2 - Site Preparation
label | Ref docs - 720.07
label | Acceptance criteria - Soil preparation shall be as described in Table 720.071 (Refer to page 8 Fig #1).
label | Freq - Prior to start of works, Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 2.3 - Soil Additives including Gypsum, lime. (If applicable)
label | Ref docs - 720.07(a) AS 4419 5.11
label | Acceptance criteria - Soil additives, including any material used to modify the chemical properties of the soil, prior the physical ripping and cultivation and in accordance with results and recommendations from site topsoil analysis tests.
label | ○ Apply sufficient gypsum to ensure soils are not dispersive, incorporating gypsum during ripping to a minimum depth of 300 mm.
label | ○ Adjust soil pH if soil including subsoil, to a depth of 300 mm is not in the range of 5-8.
label | ○ Where salinity requirements for existing (unmoved) site subsoil or topsoil do not meet the acceptable range in AS 4419 5.6, shall notify the Superintendent.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - I
label | Resp - SE/PE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Site Topsoil Analysis Tests (If applicable) | Yes,No
checkpoint | 2.4 - Ripping
label | Ref docs - 720.07 (b), 720.071
label | Acceptance criteria - Each ripped planting area, individual tree planting and grassing area prior to mulching, planting, or grassing are is to be made available.
label | ○ Rock and rubbish brought to the surface shall be removed and disposed.
label | ○ Ripping shall be postponed when the soil is at or wetter than field capacity.
label | ○ Do not proceed until the Superintendent acknowledges requirements for ripping have been met. In areas where ripping is not practicable, submit alternative methods to achieve an equivalent result to the Superintendent for review.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - H, I
label | Resp - SE/PE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Topsoil Application
label | Ref docs - 720.07 (c)
label | Acceptance criteria - Topsoil shall be spread on planting areas and grassed areas. Topsoil is not compacted.
label | ○ Weedy site topsoil shall not be spread to other locations on the site. Weedy topsoil shall be handled in accordance with weed management procedures.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 2.6 - Cultivation
label | Ref docs - 720.07 (d)
label | Acceptance criteria - Cultivation shall be undertaken to break soil down to the tilth with 80% of the volume composed of clods less than 50 mm in diameter.
label | ○ Rotary hoes and other powered cultivators that might create a hard pan beneath the depth of cultivation shall not be used for cultivations.
label | ○ Cultivations shall not occur within the extent of existing vegetation areas marked for protection or the dripline of existing woody plants. Hand cultivation shall be used within root zones of trees to be retained.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 2.7 - Topsoil Finished Surface Levels
label | Ref docs - 720.07 (e)
label | Acceptance criteria - The finished level of grassed areas shall be:
label | ○ not higher than 125 mm below weep holes or damp-proof courses in adjacent walls
label | ○ level with the bottom of fence plinths
label | ○ level with adjacent pavements, kerbs, pits, and other structures.
label | The finished level of garden bed mulch and/or topsoil shall be tapered so that the finished mulch and/or topsoil levels meet flush with the adjacent surfaces.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - H, I
label | Resp - SE/PE
checkpoint | 2.8 - Topsoil Finished Surface Levels
label | Ref docs - 720.07 (e)
label | Acceptance criteria - After cultivation and trimming, topsoil for stability on slopes may be lightly compressed. Vibrating plate is not used. Dry bulk density does not exceed the following:
label | – – – – – – – – – – – – – –
label | Soil Texture (AS 4419) ¦¦ Max. Dry Bulk Density of Topsoils
label | – – – – – – – – – – – – – –
label | Clay Soils ¦¦ 1.3g/cm3 (1.4g/cm3 on slopes steeper than 3:1)
label | Loams ¦¦ 1.5 g/cm3
label | Sandy Soils ¦¦ 1.7g/cm3
label | – – – – – – – – – – – – – –
label | Freq - Each Lot
label | Key - S
label | Resp - SE/PE
checkpoint | 2.9 - Acceptance of Topsoil Placement
label | Ref docs - 720.07 (e)
label | Acceptance criteria - Each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area shall be made available for review by the Superintended prior to mulching, planting or grassing.
label | ○ In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - H, I
label | Resp - SE/PE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.10 - Removal of Unwanted Matter
label | Ref docs - 720.07 (f) Table 720.073
label | Acceptance criteria - All unwanted mater shall be removed from landscape areas.
label | Mown Grass Areas:
label | ○ Any weeds, plastic, metal, glass, or material toxic to plants.
label | ○ Surface stone, rock, building rubble greater than 25 mm in diameter
label | ○ Clay lumps, sticks and exposed tree roots greater than 50 mm diameter
label | Planting Areas:
label | ○ Any weeds, plastic, metal, glass, or material toxic to plants
label | ○ Any visible surface stone, rock building rubble greater than 75 mm in diameter
label | ○ Clay lumps, sticks, and expose tree roots greater than 100 mm diameter.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 2.11 - Existing Planting Areas
label | Ref docs - 720.07 (g)
label | Acceptance criteria - Obtain all necessary permits and obtain approval from the Superintendent prior to the pruning or removal of local native vegetation.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - H, I
label | Resp - SE/PE
label | SI Key - H
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 Mulching
checkpoint | 3.1 - Wood Mulch (Shredded or Chipped)
label | Ref docs - 720.08 (a)
label | Acceptance criteria - Install wood mulch to all Planting Areas unless otherwise specified. Mulch shall extend at least 1 m beyond plant centres at the outer edges of all Planting Areas.
label | ○ Install 2 m diameter mulch rings around all Individual Tree Plantings.
label | ○ Mulch Depth in all situations shall be a minimum 75 mm and maximum 125 mm.
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 3.2 - Weed Control Mat and Erosion Control Mat
label | Ref docs - 720.08 (b)
label | Acceptance criteria - Install weed control mat for planting areas steeper than 2:1 and in planting areas prone to flooding or within 2 m of waterways, swales, wetlands, and sedimentation ponds or elsewhere as specified.
label | ○ Weed control and erosion mat shall be laid and anchored in accordance with the manufacturer’s instruction.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
section | 4.0 Planting
checkpoint | 4.1 - Planting
label | Ref docs - 720.09 (a)
label | Acceptance criteria - Carry out planting to ensure healthy, vigorous growth of plants.
label | ○ Holes in heavy soils or on batters shall be prepared and to ensure adequate drainage.
label | ○ Holes shall not be left smooth sided in basalt or plastic soils. Drill or auger hole diggers only be used where soil has been cultivated.
label | ○ Planting holes shall be backfilled with friable topsoil free of debris, rocks, and clods greater than 50mm in diameter.
label | ○ In the event the specified plant is unlikely to be suited to the as constructed growing conditions, the Superintendent shall be notified.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 4.2 - Fertilising
label | Ref docs - 720.09 (b)
label | Acceptance criteria - Fertilise advance trees and where specified and/or identified by the soil analysis, other planting areas with fertiliser in accordance with the manufacturer’s recommendations.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 4.3 - Initial Watering
label | Ref docs - 720.09 (c)
label | Acceptance criteria - Saturate each plant within 8 hours after planting. Cells and tubes shall be irrigated with a minimum 3L of water per plant.
label | ○ Under no circumstance shall any plant be planted into a dry planting hole (soil moisture at wilting prior or drier). If the soil is dry, the planting hole shall be saturated with water prior to planting.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
section | 5.0 Grassing
checkpoint | 5.1 - Seeded Grassing
label | Ref docs - 720.10 (a)
label | Acceptance criteria - All areas indicated to be grassed on the IFC drawings.
label | ○ Seeding mix: 25% perennial rye, 35% annual rye, 15% cocksfoot, and 25% clover at 200kg/ha.
label | ○ All areas disturbed will not be a planting area or managed as remnant indigenous vegetation.
label | ○ Grass seed shall be sown at minimum 100 kg/HA (if drilled) or 200 kg/Ha (if broadcast), distributed evenly to achieve an even and dense grass cover.
label | ○ Germination rate shall be minimum 80% cover within 8 weeks and 95% cover within 3 months of sowing.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 5.2 - Hydromulch & Seed Layer
label | Ref docs - IFC Landscaping and Urban Design
label | Acceptance criteria - Hydromulch Treatment:
label | ○ min. 100mm cross-ripped subgrade
label | ○ min. 75mm ameliorated site top soil, over
label | ○ hydro-mulch & seed layer, over
label | Note: for hydromulch planting within swales refer to detail 01 / DRG 3001
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - I
label | Resp - SE/PE
checkpoint | 5.3 - Fertilising
label | Ref docs - 720.10 (b)
label | Acceptance criteria - Fertiliser shall be placed evenly over the prepared surface in accordance with the manufacturer’s recommendations.
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
checkpoint | 5.4 - First Mow
label | Ref docs - 720.10 (c)
label | Acceptance criteria - First cut when at least 50% of the grassing area to be cut has grown to a minimum 75 mm and maximum 150 mm height. Mow to a minimum height of 75 mm. Less than 1/3 the height of the grass shall be removed in the first cut.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE
section | 6.0 Completion
checkpoint | 6.1 - As Built Survey
label | Ref docs - VR Clause 720
label | Acceptance criteria - Finished level of grassed areas shall be no higher than 125 mm below weep-holes or damp-proof courses in adjacent walls and level with bottoms of fence plinths, kerbs, pavements and pits. Mulch shall extend at least 1m beyond plant centres at the outer edges of all
label | ○ Planting Areas with 2m diameter mulch rings around all Individual Tree Plantings.
label | ○ Mulch Depth in all situations shall be a minimum 75 mm and maximum 125 mm.
button | Has all of the above been completed? | Yes,No,N/A
label | Freq - Each lot
label | Key - S
label | Resp - SE/PE, SV
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | Survey conformance report | Yes,No
section | 7.0 Work Lot Closeout
checkpoint | 7.1 - Test Reports
label | Ref docs - VIC Roads Specifications
label | Acceptance criteria -
button | All Test reports received and Reviewed. | Yes,No
label | Freq - Each lot
label | Key - R
label | Resp - SE/PE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
button | NATA Endorsed Test Reports | Yes,No
checkpoint | 7.2 - Product Non-Conformance
label | Ref docs - CQMP
label | Acceptance criteria -
button | All Product Non-Conformance(s) recorded and closed (if applicable) | Yes,No
label | Freq - Each lot
label | Key - R
label | Resp - SE/PE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) -
textbox | NCR No:
button | NCR reports | Yes,No
checkpoint | 7.3 - Quality Representative to check the above criteria and records to confirm
label | Ref docs - CQMP Lot Records
label | Acceptance criteria -
button | All above criteria met, and records identified attached. | Yes,No
label | Freq - Each lot
label | Key - R
label | Resp - SE/PE
label | Remarks/record (eg. Test frequency reports, certificates, checklist etc) - Completed Checklist (if applicable) and reports and other compliance records attached.