## Breakdown
Roofing Smiths Christchurch (Kevin Hickman - Riccarton Park)
Stage 003 - THB11 & 13
THB11 (33, 34, 35, 36)
|  |  | Pitched Roof A | Pre-populate | FC - S - Roofing Iron/Flashings
|  |  | Pitched Roof B | Pre-populate | FC - S - Roofing Iron/Flashings
|  |  | Pitched Roof C | Pre-populate | FC - S - Roofing Iron/Flashings
|  |  | Pitched Roof D | Pre-populate | FC - S - Roofing Iron/Flashings
THB13 (37,38,39)
|  |  | Pitched Roof A | Pre-populate | FC - S - Roofing Iron/Flashings
|  |  | Pitched Roof B | Pre-populate | FC - S - Roofing Iron/Flashings
Pitched Roof C
Compliance Documentation
|  | Stage 003 - THB011 & 13 |  | Prep-populate | CST - S - Completion Documents

## Checklist
Type | Name | Value
checklist | FC - S - Roofing Iron/Flashings
checkpoint | Correct drawing revision checked, referenced and attached
text | Drawing number(s) & Revisions
checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
checkpoint | Roof underlay checked and accurate
checkpoint | Roofing Material fixed correctly/checked and accurate (2-3 photos attached)
checkpoint | Flashing/capping checked and accurate (2-3 Photos attached)
checkpoint | Area left clean and tidy (Photos attached)
label | Roof and gutters/surrounding area clean and rubbish/filings removed
checkpoint | All Roof works completed, reviewed and approved (Photos attached)
holdpoint | Request sign off
checkpoint | Inspections completed and issued to Foreman
holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
Type | Name | Value
checklist-flat | CST - S - Completion Documents
checkpoint | All relevant Compliance Documentation completed and attached above
button | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint | Request Signoff