## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | FC - S - Roofing Iron/Flashings |  |  |  |  | Yes | FC - S - Roofing Iron/Flashings | 0fe6d0ec-a534-437b-8538-770154a981d2
checkpoint-status |  |  | checkpoint | Correct drawing revision checked,referenced and attached
text | 56658650-138a-52b5-afb3-da4e52c66ac4 |  | textbox | Drawing number(s) & Revisions
checkpoint-status |  |  | checkpoint | Area Accessable, Substrate Acceptable & Approval to start work
checkpoint-status |  |  | checkpoint | Roof underlay checked and accurate
checkpoint-status |  |  | checkpoint | Iron laid fixed correctly/checked and accurate (2-3 photos attached)
checkpoint-status |  |  | checkpoint | Flashing/capping checked and accurate (2-3 Photos attached)
checkpoint-status |  |  | checkpoint | Area left clean and tidy (Photos attached)
label | d06b34a2-623c-5846-81a7-b8ffdb9e64c6 |  | note | Roof and gutters/surrounding area clean and rubbish/filings removed
checkpoint-status |  |  | checkpoint | All Roof works completed, reviewed and approved (Photos attached)
holdpoint |  |  | signoff | Request sign off
checklist-flat |  |  | checklist | Completion Documentation |  |  |  |  | Yes | SYS - Completion Documents | 19ad2d30-af05-4238-916e-99bf788d63f5
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | d1d794b8-b862-4996-83ef-36859a0f0ee4 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | YES, N/A
button | 99556594-3b35-45f1-81a3-c721a441a90b |  | button | Roof Warranties completed and attached | YES, N/A
button | e7ce89b5-616a-47c3-b65f-c4dd4d9e16b3 |  | button | Any Additional Compliance Documentation - Completed and Attached | YES, N/A
label | ba4e8255-83b3-4943-97f5-0451d59c6430 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | ST - S - Roof structure - Steel |  |  |  |  | Yes | ST - S - Roof structure - Steel | 47c98325-1d91-42de-97f0-1f4e028c14e7
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Hold down bolts in the correct location
checkpoint-status |  |  | checkpoint | Pre erection checks complete
checkpoint-group |  |  | section | Installation
checkpoint-status |  |  | checkpoint | Steel correct size and type
checkpoint-status |  |  | checkpoint | Welding certificates sited
checkpoint-status |  |  | checkpoint | Installed in the correct location and orientation
checkpoint-status |  |  | checkpoint | Installed in correct level, plumb, correct pitch and braced
checkpoint-status |  |  | checkpoint | All bolts secure/ correctly tensioned
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | CST - S - Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 56cd0def-c638-437f-8bc2-72018c6a504a
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | a1fea1f5-4978-5674-89d2-c25a70d96882 |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 30202a96-0fb6-50cd-87e9-2caab0b66fd5 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  | checklist-flat has incorrect meta.stepType checkpoint-group | checklist | Installation |  |  |  |  | Yes | SYS - Installation (section only) | 86326dc8-6a46-4ec0-b58a-f7002faf44f1
checkpoint-status |  |  | checkpoint | Steel correct size and type
checkpoint-status |  |  | checkpoint | Welding certificates sited
checkpoint-status |  |  | checkpoint | Installed in the correct location and orientation
checkpoint-status |  |  | checkpoint | Installed in correct level, plumb, correct pitch and braced
checkpoint-status |  |  | checkpoint | All bolts secure/ correctly tensioned
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | Roof - |  |  |  |  | Yes | QA – Roofing iron/flashings | f23df41e-283a-4a73-abc6-24e287c0bc1c
checkpoint-status |  |  | checkpoint | Correct drawing revision checked,referenced and attached
text | aca12a73-d65a-48dc-85e6-0794e58fb676 |  | textbox | Drawing number(s) & Revisions
checkpoint-status |  |  | checkpoint | Area Accessible, Substrate Acceptable & Approval to start work
checkpoint-status |  |  | checkpoint | Roof underlay checked and accurate
checkpoint-status |  |  | checkpoint | Iron laid fixed correctly/checked and accurate (2-3 photos attached)
checkpoint-status |  |  | checkpoint | Flashing/capping checked and accurate (2-3 Photos attached)
checkpoint-status |  |  | checkpoint | Area left clean and tidy (Photos attached)
label | 4f43ac8f-30cd-40da-a43b-f1b1ebc4cc68 |  | note | Roof and gutters/surrounding area clean and rubbish/filings removed
checkpoint-status |  |  | checkpoint | All Roof works completed, reviewed and approved(Photos attached)
holdpoint |  |  | signoff | Request sign off
checklist-flat |  |  | checklist | Compliance Documentation |  |  |  |  | Yes | SYS - CST - S - Completion Documents (old version) | ffca58cd-db2d-47a4-bc51-72b090fe1cdb
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
button | 8dcaf7cf-9467-4fe3-948d-19cb3f2fa216 |  | button | LBP Memorandum/ Record of works filled out, signed and attached | YES,N/A
button | 74fbe47b-0165-4aaa-8c44-8bc3e1426993 |  | button | Any Additional Compliance Documentation - Completed and Attached | YES,N/A
label | 9739dea4-5164-54b7-9c7f-2c0cb30927fb |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff