## Punch Windows
Sylvia Park Concretec QA checklist
checklist | Punch Windows Frames (unglazed)
sections | Joinery Install
label | Window # / Elevation / Level
checkpoint | Opening and Sill Acceptable, All elements approved as per drawings
checkpoint | Check the dimensions & Level (ADD survey drawings in here if not as per drawings)
checkpoint | Waterproofing ( Check that water proofing is over area where airseal is going to be) PHOTO REQUIRED
checkpoint | Sika Primer applied and cured as per Manufacturers specification PHOTO REQUIRED
checkpoint | Concretec Panel Number Visible Inside PHOTO REQUIRED
checkpoint | Check the joinery is free from damage
checkpoint | Check Frame and orientation is correct
checkpoint | Fixing is accordance with the Shop drawing
checkpoint | All fixings oversealed on frame and no tooling damage on frame PHOTO REQUIRED
checkpoint | Frames installed in correct position & level
checkpoint | Ensure no packers visible out of line where airseal is to be installed.
checkpoint | Internal Airseal is accordance to the shop drawing LIST SIZE in mm PHOTO REQUIRED
label | Internal Airseal Sealant Type & Batch Number
input
checkpoint | Metroglass supply glass free from defect for installation
checkpoint | Glass correct specification to the window type PHOTO REQUIRED of Label
checkpoint | Correct setting blocks installed and spacings applied PHOTO REQUIRED
checkpoint | Beads reinstated correctly and Wedged off completely PHOTO REQUIRED
checkpoint | Metroglass Glaziers sign off and hand over to WAL
checkpoint | Rainshield installed and no damage ( PHOTO REQUIRED )
checkpoint | Check Ventient strip Y / N ( PHOTO REQUIRED)
checkpoint | All infils installed and corners closed and tight/ no damage or scratched
checkpoint | All visable fixings touched up with dabstick/paint PHOTO REQUIRED
checkpoint | Water Test Conducted a/p WGANZ 501
checkpoint | Installation of Ventient cover & Acoustic Strip PHOTO REQUIRED
checkpoint | Trade clean / protected
sections | Wight Aluminium sign off
Check point | All elements completed correctly as per specification, reviewed and approved
Hold point | Raise Remedial / Request Signoff