## Checklists (2)
type | name | values | prefix | postfix | Template Name
Check List | HOBEC L2 FF
Section | FCU L2-KL-2.02
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L20WS1-2.03
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-R2.01
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-M6-2.05
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-M3-2.09
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-M5-2.17
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-M6-2.15
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-BR1-2.19
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-CM32.21
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-BR1-2.20
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L2-CM3-2.23
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | Supply Air from riser North to 5x FCU
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Main ducting seismic installed |  |  |  | Ventillation - First Fix
Check Point | Balancing dampers installed |  |  |  | Ventillation - First Fix
Section | Extract Air from riser North
Check Point | Main ducting installed into ceiling space |  |  |  | Ventillation - First Fix
Section | Supply Air from riser South to 6x FCU
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Main ducting seismic installed |  |  |  | Ventillation - First Fix
Check Point | Balancing dampers installed |  |  |  | Ventillation - First Fix
Section | Extract Air from riser South
Check Point | Main ducting installed into ceiling space |  |  |  | Ventillation - First Fix
Check Point | Balacing dampers installed |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boos installed installed |  |  |  | Ventillation - First Fix
Section | Extract ducting through riser to basment
Check Point | Main ducting installed
Section | Cross Talk attenuator 1
Check Point | CTU Installed
Section | Cross Talk attenuator 2
Check Point | CTU Installed
Section | Cross Talk attenuator 3
Check Point | CTU Installed
Section | Cross Talk attenuator 4
Check Point | CTU Installed
Section | Cross Talk attenuator 5
Check Point | CTU Installed
Section | Cross Talk attenuator 6
Check Point | CTU Installed
Section | Cross Talk attenuator 7
Check Point | CTU Installed
Section | Cross Talk attenuator 8
Check Point | CTU Installed
Section | Cross Talk attenuator 9
Check Point | CTU Installed
Section | ERH 1
Check Point | Electrical feed run
Section | ERH 1
Check Point | Electrical feed run
Section | ERH 1
Check Point | Electrical feed run