## Checklists (2)
type | name | values | prefix | postfix | Template Name
Check List | HOBEC L3 FF
Section | FCU L2-M10-3.16
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-N-01
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-03
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-E-07
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-WR1-3.02
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-W-03
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-I-10
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-R-3.22
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-WR2-3.05
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-W-04
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-I-13
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-OP-S-06
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-W-3.13
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-M4P-3.39
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-T-3.17
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-C-3.01
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU L3-C-3.02
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | Supply Air from riser North to 5x FCU
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Main ducting seismic installed |  |  |  | Ventillation - First Fix
Check Point | Balancing dampers installed |  |  |  | Ventillation - First Fix
Section | Extract Air from riser North
Check Point | Main ducting installed into ceiling space |  |  |  | Ventillation - First Fix
Section | Supply Air from riser South to 6x FCU
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Main ducting seismic installed |  |  |  | Ventillation - First Fix
Check Point | Balancing dampers installed |  |  |  | Ventillation - First Fix
Section | Extract Air from riser South
Check Point | Main ducting installed into ceiling space |  |  |  | Ventillation - First Fix
Check Point | Balacing dampers installed |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boos installed installed |  |  |  | Ventillation - First Fix
Section | L3 SF - 01
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Main ducting seismic installed |  |  |  | Ventillation - First Fix
Check Point | Balancing dampers installed |  |  |  | Ventillation - First Fix
Check Point | attenuator installed installed
Check Point | extirior grille boots installed
Check Point | duct heater installed
Section | Cross Talk attenuator 1
Check Point | CTU Installed
Section | Cross Talk attenuator 2
Check Point | CTU Installed
Section | Cross Talk attenuator 3
Check Point | CTU Installed
Section | Cross Talk attenuator 4
Check Point | CTU Installed
Section | Cross Talk attenuator 5
Check Point | CTU Installed
Section | Cross Talk attenuator 6
Check Point | CTU Installed
Section | Cross Talk attenuator 7
Check Point | CTU Installed
Section | Cross Talk attenuator 8
Check Point | CTU Installed
Section | Cross Talk attenuator 9
Check Point | CTU Installed
Section | Cross Talk attenuator 10
Check Point | CTU Installed
Section | Cross Talk attenuator 11
Check Point | CTU Installed
Section | Cross Talk attenuator 12
Check Point | CTU Installed
Section | Cross Talk attenuator 13
Check Point | CTU Installed
Section | Cross Talk attenuator 14
Check Point | CTU Installed
Section | Cross Talk attenuator 15
Check Point | CTU Installed
Section | Cross Talk attenuator 16
Check Point | CTU Installed
Section | Cross Talk attenuator 17
Check Point | CTU Installed
Section | Cross Talk attenuator 18
Check Point | CTU Installed
Section | ERH 1
Check Point | Electrical feed run
Section | ERH 2
Check Point | Electrical feed run
Section | ERH 3
Check Point | Electrical feed run
Section | ERH 4
Check Point | Electrical feed run
Section | ERH 5
Check Point | Electrical feed run
Section | ERH 6
Check Point | Electrical feed run
Section | BSF 01
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 02
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 03
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 04
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 05
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 06
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 07
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 08
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 09
Check Point | Fan Installed
Check Point | ducting installed
Section | BSF 10
Check Point | Fan Installed
Check Point | ducting installed