## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | HOBEC Fit Out L2 First Fix
section | FCU L2-KL-2.02
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L20WS1-2.03
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-R2.01
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-M6-2.05
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-M3-2.09
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-M5-2.17
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-M6-2.15
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-BR1-2.19
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-CM32.21
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-BR1-2.20
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L2-CM3-2.23
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | Supply Air from riser North to 5x FCU
checkpoint | Main ducting installed
checkpoint | Main ducting seismic installed
checkpoint | Balancing dampers installed
section | Extract Air from riser North
checkpoint | Main ducting installed into ceiling space
section | Supply Air from riser South to 6x FCU
checkpoint | Main ducting installed
checkpoint | Main ducting seismic installed
checkpoint | Balancing dampers installed
section | Extract Air from riser South
checkpoint | Main ducting installed into ceiling space
checkpoint | Balacing dampers installed
checkpoint | Flexible ducting installed
checkpoint | Grille boos installed installed
section | Extract ducting through riser to basment
checkpoint | Main ducting installed
section | Cross Talk attenuator 1
checkpoint | CTU Installed
section | Cross Talk attenuator 2
checkpoint | CTU Installed
section | Cross Talk attenuator 3
checkpoint | CTU Installed
section | Cross Talk attenuator 4
checkpoint | CTU Installed
section | Cross Talk attenuator 5
checkpoint | CTU Installed
section | Cross Talk attenuator 6
checkpoint | CTU Installed
section | Cross Talk attenuator 7
checkpoint | CTU Installed
section | Cross Talk attenuator 8
checkpoint | CTU Installed
section | Cross Talk attenuator 9
checkpoint | CTU Installed
section | ERH 1
checkpoint | Electrical feed run
section | ERH 1
checkpoint | Electrical feed run
section | ERH 1
checkpoint | Electrical feed run
checklist | HOBEC Fit Out L2 Second Fix
section | FCU L2-KL-2.02
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L20WS1-2.03
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-R2.01
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-M6-2.05
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-M3-2.09
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-M5-2.17
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-M6-2.15
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-BR1-2.19
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-CM32.21
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-BR1-2.20
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L2-CM3-2.23
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | Extract Air from riser South
checkpoint | Grilles Installed as per plans
section | ERH 1
checkpoint | Fan installed and hung level
section | ERH 1
checkpoint | Fan installed and hung level
section | ERH 1
checkpoint | Fan installed and hung level
checklist | HOBEC Fit Out L3 First Fix
section | FCU L2-M10-3.16
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-N-01
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-03
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-E-07
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-WR1-3.02
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-W-03
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-I-10
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-R-3.22
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-WR2-3.05
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-W-04
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-I-13
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-OP-S-06
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-W-3.13
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-M4P-3.39
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-T-3.17
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-C-3.01
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | FCU L3-C-3.02
checkpoint | Indoor hung Level and with Seismic and anti vibration mounts
checkpoint | Pipe work installed and insulated as per plans to Main pipe run
checkpoint | Valves installed as per plans
checkpoint | Drain pipe installed and tested as per ABC
checkpoint | Plenums installed
checkpoint | Ducting installed
checkpoint | Grille boots installed
checkpoint | Electrical wires run to fan, heater and coms and wired up
section | Supply Air from riser North to 5x FCU
checkpoint | Main ducting installed
checkpoint | Main ducting seismic installed
checkpoint | Balancing dampers installed
section | Extract Air from riser North
checkpoint | Main ducting installed into ceiling space
section | Supply Air from riser South to 6x FCU
checkpoint | Main ducting installed
checkpoint | Main ducting seismic installed
checkpoint | Balancing dampers installed
section | Extract Air from riser South
checkpoint | Main ducting installed into ceiling space
checkpoint | Balacing dampers installed
checkpoint | Flexible ducting installed
checkpoint | Grille boos installed installed
section | L3 SF - 01
checkpoint | Main ducting installed
checkpoint | Main ducting seismic installed
checkpoint | Balancing dampers installed
checkpoint | Attenuator installed installed
checkpoint | Exterior grille boots installed
checkpoint | Duct heater installed
section | Cross Talk attenuator 1
checkpoint | CTU Installed
section | Cross Talk attenuator 2
checkpoint | CTU Installed
section | Cross Talk attenuator 3
checkpoint | CTU Installed
section | Cross Talk attenuator 4
checkpoint | CTU Installed
section | Cross Talk attenuator 5
checkpoint | CTU Installed
section | Cross Talk attenuator 6
checkpoint | CTU Installed
section | Cross Talk attenuator 7
checkpoint | CTU Installed
section | Cross Talk attenuator 8
checkpoint | CTU Installed
section | Cross Talk attenuator 9
checkpoint | CTU Installed
section | Cross Talk attenuator 10
checkpoint | CTU Installed
section | Cross Talk attenuator 11
checkpoint | CTU Installed
section | Cross Talk attenuator 12
checkpoint | CTU Installed
section | Cross Talk attenuator 13
checkpoint | CTU Installed
section | Cross Talk attenuator 14
checkpoint | CTU Installed
section | Cross Talk attenuator 15
checkpoint | CTU Installed
section | Cross Talk attenuator 16
checkpoint | CTU Installed
section | Cross Talk attenuator 17
checkpoint | CTU Installed
section | Cross Talk attenuator 18
checkpoint | CTU Installed
section | ERH 1
checkpoint | Electrical feed run
section | ERH 2
checkpoint | Electrical feed run
section | ERH 3
checkpoint | Electrical feed run
section | ERH 4
checkpoint | Electrical feed run
section | ERH 5
checkpoint | Electrical feed run
section | ERH 6
checkpoint | Electrical feed run
section | BSF 01
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 02
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 03
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 04
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 05
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 06
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 07
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 08
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 09
checkpoint | Fan Installed
checkpoint | ducting installed
section | BSF 10
checkpoint | Fan Installed
checkpoint | ducting installed
checklist | HOBEC Fit Out L3 Second Fix
section | FCU L2-M10-3.16
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-N-01
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-03
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-E-07
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-WR1-3.02
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-W-03
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-I-10
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-R-3.22
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-WR2-3.05
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-W-04
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-I-13
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-OP-S-06
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-W-3.13
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-M4P-3.39
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-T-3.17
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-C-3.01
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | FCU L3-C-3.02
checkpoint | Grilles Installed as per plans
checkpoint | Access Panels in correct location
checkpoint | Controllers installed as per plans
section | Extract Air from riser South
checkpoint | Main ducting installed into ceiling space
checkpoint | Balacing dampers installed
checkpoint | Flexible ducting installed
checkpoint | Grille boos installed installed
section | L3 SF - 01
checkpoint | Main ducting installed
checkpoint | Main ducting seismic installed
checkpoint | Balancing dampers installed
checkpoint | Attenuator installed installed
checkpoint | Exterior grille boots installed
checkpoint | Duct heater installed
section | ERH 1
checkpoint | Duct heater installed
section | ERH 2
checkpoint | Duct heater installed
section | ERH 3
checkpoint | Duct heater installed
section | ERH 4
checkpoint | Duct heater installed
section | ERH 5
checkpoint | Duct heater installed
section | ERH 6
checkpoint | Duct heater installed
section | BSF 01
checkpoint | Grille installed
section | BSF 02
checkpoint | Grille installed
section | BSF 03
checkpoint | Grille installed
section | BSF 04
checkpoint | Grille installed
section | BSF 05
checkpoint | Grille installed
section | BSF 06
checkpoint | Grille installed
section | BSF 07
checkpoint | Grille installed
section | BSF 08
checkpoint | Grille installed
section | BSF 09
checkpoint | Grille installed
section | BSF 10
checkpoint | Grille installed