## Checklists (2)
type | name | values | prefix | postfix | Template Name
Check List | Basement
Section | IU-01 HI-wall
Check Point | Pipes run to correct locations |  |  |  | Ventillation - First Fix
Check Point | Interconnecting installed |  |  |  | Ventillation - First Fix
Check Point | Drain installed |  |  |  | Ventillation - First Fix
Section | FCU A Installation
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU B Installation
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | FCU B Installation
Check Point | Indoor hung Level and with Seismic and anti vibration mounts
Check Point | Pipe work installed and insulated as per plans to Main pipe run
Check Point | Valves installed as per plans
Check Point | Drain pipe installed and tested as per ABC
Check Point | Plenums installed
Check Point | Ducting installed
Check Point | Grille boots installed
Check Point | Electrical wires run to fan, heater and coms and wired up
Section | EF-02
Check Point | Fan installed with seismic |  |  |  | Ventillation - First Fix
Check Point | Main ducting installed with seismic |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Check Point | Electrical feed run |  |  |  | Ventillation - First Fix
Section | EF-05
Check Point | Fan installed with seismic |  |  |  | HighWall pre pipe
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Check Point | Electrical feed run |  |  |  | Ventillation - First Fix
Section | EF-13
Check Point | Fan installed with seismic |  |  |  | HighWall pre pipe
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Check Point | Electrical feed run |  |  |  | Ventillation - First Fix
Section | EF-14
Check Point | Fan installed with seismic |  |  |  | HighWall pre pipe
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Check Point | Electrical feed run |  |  |  | Ventillation - First Fix
Section | Supply Make up for Bathroom block 1
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Section | Supply Make up for Bathroom block 2
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Flexible ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Section | Supply Air from riser to Foyer
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | HCD-2 |  |  |  | Ventillation - First Fix
Check Point | HCD-3 |  |  |  | Ventillation - First Fix
Check Point | HCD-4 |  |  |  | Ventillation - First Fix
Check Point | FD-R18 |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Section | Extract Air from riser to GF
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Section | Extract ducting through riser to basment
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Section | Louvre 1 North
Check Point | Through wall ducting installed |  |  |  | HighWall pre pipe
Section | Louvre 2 North
Check Point | Through wall ducting installed |  |  |  | HighWall pre pipe
Section | Louvre 3 North
Check Point | Through wall ducting installed |  |  |  | HighWall pre pipe
Section | Louvre 1 West
Check Point | Through wall ducting installed |  |  |  | HighWall pre pipe
Section | Louvre 2 West
Check Point | Through wall ducting installed |  |  |  | HighWall pre pipe
Section | Louvre 3 West
Check Point | Through wall ducting installed |  |  |  | HighWall pre pipe
Section | Louvre 4 West
Check Point | Through wall ducting installed |  |  |  | HighWall pre pipe
Section | Radiant heater 01
Check Point | Electrical feed run |  |  |  | Ventillation - First Fix
Section | Radiant heater 02
Check Point | Electrical feed run |  |  |  | Ventillation - First Fix