## Checklists (2)
type | name | values | prefix | postfix | Template Name
Check List | Basement
Section | IU-01 HI-wall
Check Point | Indoor unit installed level |  |  |  | Ventillation - First Fix
Check Point | outdoor unit installed level |  |  |  | Ventillation - First Fix
Check Point | Indoor model |  |  |  | Ventillation - First Fix
Check Point | outdoor model |  |  |  | Ventillation - First Fix
Check Point | Drain and pipes connected indoor unit |  |  |  | Ventillation - First Fix
Check Point | Drain and pipes connected Outdoor unit |  |  |  | Ventillation - First Fix
Check Point | Unit pressure tested 400PSI |  |  |  | Ventillation - First Fix
Check Point | Units holding Vac |  |  |  | Ventillation - First Fix
Section | FCU A Installation
Check Point | Grilles Installed as per plans
Check Point | Access Panels in correct location
Check Point | Controllers installed as per plans
Section | FCU B Installation
Check Point | Grilles Installed as per plans
Check Point | Access Panels in correct location
Check Point | Controllers installed as per plans
Section | FCU B Installation
Check Point | Grilles Installed as per plans
Check Point | Access Panels in correct location
Check Point | Controllers installed as per plans
Section | EF-02
Check Point | Grilles Installed |  |  |  | Ventillation - First Fix
Check Point | Louvre/cowl installed Installed |  |  |  | Ventillation - First Fix
Section | EF-05
Check Point | Grilles Installed |  |  |  | Ventillation - First Fix
Check Point | Louvre/cowl installed Installed |  |  |  | Ventillation - First Fix
Section | EF-13
Check Point | Grilles Installed |  |  |  | Ventillation - First Fix
Check Point | Louvre/cowl installed Installed |  |  |  | Ventillation - First Fix
Section | EF-14
Check Point | Grilles Installed |  |  |  | Ventillation - First Fix
Check Point | Louvre/cowl installed Installed |  |  |  | Ventillation - First Fix
Section | Supply Make up for Bathroom block 1
Check Point | Grilles Installed |  |  |  | Ventillation - First Fix
Check Point | Louvre/cowl installed Installed |  |  |  | Ventillation - First Fix
Section | Supply Make up for Bathroom block 2
Check Point | Grilles Installed |  |  |  | Ventillation - First Fix
Check Point | Louvre/cowl installed Installed |  |  |  | Ventillation - First Fix
Section | Supply Air from riser to Foyer
Check Point | Grilles Installed |  |  |  | Ventillation - First Fix
Check Point | Louvre/cowl installed Installed |  |  |  | Ventillation - First Fix
Section | Extract Air from riser to GF
Check Point | Main ducting installed |  |  |  | Ventillation - First Fix
Check Point | Grille boot installed |  |  |  | Ventillation - First Fix
Section | Louvre 1 North
Check Point | Louvre installed |  |  |  | HighWall pre pipe
Section | Louvre 2 North
Check Point | Louvre installed |  |  |  | HighWall pre pipe
Section | Louvre 3 North
Check Point | Louvre installed |  |  |  | HighWall pre pipe
Section | Louvre 1 West
Check Point | Louvre installed |  |  |  | HighWall pre pipe
Section | Louvre 2 West
Check Point | Louvre installed |  |  |  | HighWall pre pipe
Section | Louvre 3 West
Check Point | Louvre installed |  |  |  | HighWall pre pipe
Section | Louvre 4 West
Check Point | Louvre installed |  |  |  | HighWall pre pipe
Section | Radiant heater 01
Check Point | Heating installed |  |  |  | Ventillation - First Fix
Section | Radiant heater 02
Check Point | Heating installed |  |  |  | Ventillation - First Fix