## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
44a58f07-47a7-473d-a3c1-53e1d35c870b | checklist | 03.22 - Subsoil Drainage | itp | 03.22 - Subsoil Drainage
4f56bcfb-c7e3-4e67-ba1d-20be95fd09fd | section | Details
| checkpoint | Once the initial set out is complete the Administrator will determine the design appropriateness of the set out with regard to the actual site conditions
| note | Acceptance Criteria and Frequency (Project Specific) - Visual
| note | Check Item - Hold Point 1
| note | Reference - MRTS01 Cl8
| signoff | Administrator Sign Off
7c84288e-7178-42b5-84ec-362cfa568c2a | checkpoint | Subsoil Drains constructed to appropriate dimensions, inspect trench prior to backfill
6fb67174-e585-5603-8980-be8e0fc985d9 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
3b272c2c-bf7b-51da-a770-dd01d93c1c54 | note | Check Item - Check Item
df47e23a-aeb1-421a-a20d-fe52bd590c19 | checkpoint | Backfill materialshall be damp when placed in trench. Material shall be carefully placed in layers not exceeding 200mm loose thickness. Shall be compacted to achieve effective mechanical interlock between particles.
6f332fe4-1553-5eea-8cdb-90a1ec5865d5 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f850f03a-fb57-52b9-9102-b8bd28d9157e | note | Check Item - Check Item
61334697-44be-546e-9904-84b8b6208242 | note | Reference - MRTS03 Cl 22.3
15227d65-4af9-4b0a-a4af-6d0f88e0f47b | checkpoint | Subsoil Drains shall be constructed in the locations and in accordance to the drawings. Subsoil Drains shall be installed to the grades specified in the drawings. Where the grades are not specified, the bottom of trenches shall be trimmed to provide not less that 0.5% longitudinal fall towards outlets for pipe type drains and not less that 1% longitudinal fall towards outlets for strip filter type drains.
8991f4b6-9686-5675-afc6-5e24a5bda13f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
126d570b-089a-5bee-9c1d-678d8fa4b811 | note | Check Item - Check Item
5777bd12-9a00-5a86-b6af-3d51424b1631 | note | Reference - MRTS03 Cl 22.3
c76b4b66-7316-43e6-a5a6-953c5369b56b | checkpoint | Cleanout and outlet pipes, Geotextiles, trench backfill, concrete for headwalls and surrounds, marker posts shall be as per specification
72f6a6f2-1f25-5e31-ac4a-0b36f5ff2731 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
6e132a7a-1a7e-5ca3-b22e-ed07bfac8a78 | note | Check Item - Check Item
154c23b4-2c3e-546e-8b3f-90636a43f8f0 | note | Reference - MRTS03 Cl22.2
e109dabd-102d-462c-8b0f-170f11b24a4e | checkpoint | Clean-outs shall be located at the heads of all subsoil drains and at subsequent spacings not exceeding 60m for Type B subsoil drains and 50m for Type D subsoil drains. Cleanouts shall be constructed in accordance with the details shown on Standard Drawings 1116.
8699cd97-311f-5392-a3c1-426ce83e5128 | note | Acceptance Criteria and Frequency (Project Specific) - Visual
fbabfd3a-4804-5158-aee2-9e38d88e8105 | note | Check Item - Check Item
e27a58cd-6db6-574b-93eb-b5ba57c85d5b | note | Reference - MRTS03 Cl22.3 TMR SD 1116
cb9477f8-47c3-4540-8337-e6a8ed0ac7bd | checkpoint | Marker posts installed where and when required as shown in the project drawings or standard drawings.
ab143219-d904-53a6-95db-e809ec6bf6fa | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f5a8c0ab-4d02-5af5-92ff-de90aa170a35 | note | Check Item - Check Item
e180d967-472e-5aae-9aec-987a4f221332 | note | Reference - MRTS03 Cl22.2.7 TMR SD 1116
8d7d1227-2d26-4bfb-98e0-1479c082296b | checkpoint | Where directed by Administrator, drains shall be flushed until outlet water is clean and flows consistently
fa4075e0-ffcb-5819-aaa2-b4ecf55cab8f | note | Acceptance Criteria and Frequency (Project Specific) - Visual
f05ed798-bb31-5bc8-a8d9-1c12048e2074 | note | Check Item - Witness Point
0b6b4107-7354-5c0d-9221-a64c14a48344 | note | Reference - MRTS03 Cl22.3
68d750af-5274-4586-ab4f-66b581452554 | checkpoint | As Constructed drawings prepared
08bb419a-ebc3-50b3-9782-545d925fa392 | note | Acceptance Criteria and Frequency (Project Specific) - As constructed drawings submitted to administrator
96d1898e-242b-5508-8000-107fc3d6f7c5 | note | Check Item - Witness Point
de4dc569-89b0-4f63-8d52-e54b3f2d2c73 | checkpoint | All geometric tolerance requirements met
3d0b71b9-5b6c-54fd-a252-a7f2b900ab9d | note | Acceptance Criteria and Frequency (Project Specific) - Survey
9f297059-7ee3-562d-81ac-4e6e5c2ea82e | note | Check Item - Check Item
e033f933-5c32-4bb9-9e1c-779a8f3fa6d0 | checkpoint | Final Verification
35357d4a-ab67-5597-8284-a5ab6ee4a231 | note | Supervisor/QA Verify that the Above has been Constructed according to Specification
874eb93e-428a-5022-ad46-584261743b31 | textbox | Print Name:
a7720170-3612-509e-a885-2be00994bbf8 | date | Date:
dc6c7656-be8f-5868-9417-260e651c2f75 | note | Project Manager Verify that the Above has been Constructed according to Specification
85733598-cc8c-5417-9750-4ff0f4e7c8a3 | textbox | Print Name:
e7dce7bf-b617-5645-98d9-5a76f258bdcc | date | Date:
aa7d37f2-6393-45e1-a5ff-636eddffdaee | signoff | Signature
ab027d0e-dbc9-41a1-a1f8-13fec0733e14 | section | Final Sign Offs (to be completed at closure of Lot)
51adbf7b-2fe6-4efd-9948-6d8ec46f094b | checkpoint | Agreed Quantities
cb201608-9dd2-4d60-97f7-2539addda41c | signoff | Agreed Quantities Sign Off
9ebc5217-206d-47ef-ae2e-a8c3df038e2b | checkpoint | Closure of Lot
056d7f88-ea05-4021-896c-fa899aaeebb8 | signoff | Closure of Lot Sign Off