## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Drawing upload |  |  |  |  | Yes | Drawing upload | 06132cdb-99a0-4eb1-9f6e-029e837db301
checkpoint-no-status |  |  | checkpoint | Drawing attached
checklist-flat |  |  | checklist | Drain Checklist |  |  |  |  | Yes | Drain Checklist | 0712b478-9f54-4104-b394-65e9b02beaa6
checkpoint-status |  |  | checkpoint | Drain completed / connected & photo uploaded below
checklist-flat |  |  | checklist | Rough In Checklist |  |  |  |  | Yes | Rough In Checklist | 2f55a659-a1fc-4580-af1d-6790fa9ed357
checkpoint-status |  |  | checkpoint | Drain complete
checkpoint-status |  |  | checkpoint | Lagging complete
checkpoint-status |  |  | checkpoint | Downpipe on
checkpoint-status |  |  | checkpoint | Overflow exposed and chopped down
checkpoint-status |  |  | checkpoint | Un-used peno's sealed
checkpoint-status |  |  | checkpoint | Rough in complete
checkpoint-status |  |  | checkpoint | Header pipes fire caulked
checkpoint-status |  |  | checkpoint | Tmv accessible to a/p
checkpoint-status |  |  | checkpoint | Hot water meters installed
checkpoint-status |  |  | checkpoint | Cross connections
checkpoint-status |  |  | checkpoint | Mixer straight, set back correct
checkpoint-status |  |  | checkpoint | Water pressure tested
checkpoint-status |  |  | checkpoint | Roll overs complete and secure
checkpoint-status |  |  | checkpoint | Apartment clean of materials
checkpoint-status |  |  | checkpoint | D/p clipped
checkpoint-status |  |  | checkpoint | Fw cleanned, covered and clear of debris
button | e55daffc-ca7d-594e-8fdb-c5de1ca861cb |  | button | Aav required? | Yes,No
checkpoint-status |  |  | checkpoint | Fixture set out correct
checkpoint-status |  |  | checkpoint | Client variation checked against schedule
checklist-flat |  |  | checklist | Slab Penetrations Checklist |  |  |  |  | Yes | Slab Penetrations Checklist | 6e489543-232a-4e4b-9ce3-3a4e35cc2e5c
checkpoint-status |  |  | checkpoint | Penetration installed as per plan
checklist-sectioned |  |  | checklist | Commissioning Checklist |  |  |  |  | Yes | Commissioning Checklist | 790c0846-75a4-4ddf-ad2c-1225d313a966
checkpoint-group |  |  | section | Kitchen
checkpoint-status |  |  | checkpoint | Kitchen sink
checkpoint-status |  |  | checkpoint | Sink mixer
checkpoint-status |  |  | checkpoint | Dishwasher
checkpoint-status |  |  | checkpoint | Dishwasher ran
checkpoint-status |  |  | checkpoint | Hot plate
checkpoint-status |  |  | checkpoint | Sink waste
checkpoint-status |  |  | checkpoint | Coverplates
checkpoint-status |  |  | checkpoint | Test cooktop
checkpoint-group |  |  | section | Bathrooms & Powder
checkpoint-status |  |  | checkpoint | W.C
checkpoint-status |  |  | checkpoint | Basin
checkpoint-status |  |  | checkpoint | Clean basin fw
checkpoint-status |  |  | checkpoint | Shower mixer
checkpoint-status |  |  | checkpoint | Shower rose
checkpoint-status |  |  | checkpoint | Shower waste cleaned
checkpoint-status |  |  | checkpoint | Temp valve
checkpoint-status |  |  | checkpoint | Aav
checklist-flat |  |  | checklist | Door Headers Checklist |  |  |  |  | Yes | Door Headers Checklist | a9c93d72-65da-4ff4-86eb-3f4367e94d32
checkpoint-status |  |  | checkpoint | fire rated with Hilti 611A intumescent
label | 238ed7fb-f5b9-5019-83cb-27fbb4a9365b |  | note | Photo of door entry and exit uploaded below
checklist-sectioned |  |  | checklist | Fit Off Checklist |  |  |  |  | Yes | Fit Off Checklist | c0a45859-5a52-4f64-97e4-47bc07b1adfb
checkpoint-group |  |  | section | Kitchen Sink
checkpoint-status |  |  | checkpoint | Joinery
checkpoint-status |  |  | checkpoint | Stone
checkpoint-status |  |  | checkpoint | Mixer
checkpoint-status |  |  | checkpoint | Waste
checkpoint-status |  |  | checkpoint | Dw connect
checkpoint-group |  |  | section | Bathrooms & Powder - Basin
checkpoint-status |  |  | checkpoint | Joinery
checkpoint-status |  |  | checkpoint | Stone
checkpoint-status |  |  | checkpoint | Basin
checkpoint-status |  |  | checkpoint | Mixer
checkpoint-group |  |  | section | Bathrooms & Powder - WC
checkpoint-status |  |  | checkpoint | Tile
checkpoint-status |  |  | checkpoint | Grout
checkpoint-status |  |  | checkpoint | Wc
checkpoint-group |  |  | section | Bathrooms - Shower
checkpoint-status |  |  | checkpoint | Tile
checkpoint-status |  |  | checkpoint | Grout
checkpoint-status |  |  | checkpoint | Rail
checkpoint-group |  |  | section | Laundries
checkpoint-status |  |  | checkpoint | Tile
checkpoint-status |  |  | checkpoint | Trough
checkpoint-status |  |  | checkpoint | Mini Stop
checkpoint-status |  |  | checkpoint | Standpipe
checklist-flat |  |  | checklist | Plant Checklist |  |  |  |  | Yes | Plant Checklist | e355e3c0-3dde-42d8-93d8-f4ffe6769742
checkpoint-status |  |  | checkpoint | All plant and Equipment installed
checklist-flat |  |  | checklist | Corridos/Risers Checklist |  |  |  |  | Yes | Corridos/Risers Checklist | f15f29e4-6dd1-4fd8-9a97-c20fa99d11a6
checkpoint-status |  |  | checkpoint | Services installed
checkpoint-status |  |  | checkpoint | Riser complete